Evaluation of Norway's Support to Capacity Development in Vietnam

Country Report

Final

September 2015

Joe Bolger

Stein-Erik Kruse

Dang Ngoc Dung

Tran Nam Binh

Acknowledgements

The Itad Evaluation team would like to acknowledge and offer thanks to the various individuals who helped to facilitate this evaluation process.  This includes Ragnhild Dybdahl, Minister Councillor, Norwegian Embassy Hanoi, Vu Minh Duc, Development Adviser, Norwegian Embassy Hanoi, Øyvind Eggen, Policy Director, Evaluation Department, Norad, Le Hong Thai, National Project Director, General Manager, Health Safety Environment (HSE) Division, Petro Vietnam (PVN), Dinh The Hung,  Project Coordinator and Manager of Emergency Standing Office, HSE Division, PVN, Mr. Tran Mac Quan, General Manager, HSEQ Division, PTSC Headquarter in HCM, Professor Mai Trong Nhuan, Program Director, Program Management Unit, Vietnam National Institute (VNU), Dr. Do Minh Duc, Program Deputy Director, Program Management Unit, VNU, Thang Trung Khong, Director Department of External Cooperation, Nha Trang University (NTU), Nguyen Thi Ngan, Vice Director - Department of External Cooperation, NTU, Phan Thi Van, Director, RIA-1 and Pham Duc Phuong, Team Leader Component 1 in Khanh Hoa, RIA-1.

As always, responsibility for the content of the report lies with the authors.

Table of Contents

Acronyms …………………………………………………………………………………………………………………………………………3

Introduction ……………………………………………………………………………………………………………………………………..6

1	Country Capacity Development Overview	6

1.1	Norwegian CD Support to Vietnam—the overall picture	6

1.2	Central Government Priorities, Perspective on National Needs for CD	7

1.3	Central Government Perspective on Donor Role in CD (including Norway)	8

1.4	Governance of ODA and CD	8

1.5	Monitoring, Accountability and Adaptation	9

1.6	Donor Coordination	10

1.7	National Context for Public Sector CD	11

2	Capacities of the Norwegian Embassy and its Partners	12

3	Summary Description of Individual Interventions	13

3.1	Development of Management Systems on Safety and Working Environment and Environment Pollution Control in the Vietnamese Petroleum Industry, Project SRV-0020 (PVN Project)	13

3.2	Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, Project SRV- 07/056 (VNU Project)	14

3.3	Building Advanced Research and Education Capacity for Research Institute for Aquaculture No. 1 in Vietnam (RIA-1 Project)	14

3.4	Improving training and research capacity of the University of Fisheries, Vietnam, Project SRV2701 (NTU Project)	14

4	Findings	15

4.1	Relevance of Strategies and Initiatives	15

4.2	Fit with Context-specific Factors	16

4.3	Perception of Donor’s Role in CD	20

4.4	Results-orientation, Learning and Improved Effectiveness	21

4.5	Capacities to Manage CD processes	21

4.6	Achievement of Planned Results and Improvements in Capacity	23

4.7	Unintended Effects of Support to CD	25

4.8	Efficient Use of Money in Contributing to CD outcomes	25

4.9	Characteristics of Relevant and Effective CD Interventions	26

4.10	Circumstances Under Which Donor Support to CD Appropriate and Effective	27

4.11	Situations in Which Agencies Should Refrain from Being Involved in CD	29

4.12	Theory of Change	30

Acronyms

AEF		Aid Effectiveness Forum

CCBP		Comprehensive Capacity Building Programme for ODA Management

CD		Capacity development

CG		Consultative Group

CPRGS		Comprehensive Poverty Reduction and Growth Strategy

CSO		Civil Society Organization

CTA		Chief Technical Advisor

DNV		Det Norske Veritas

EIA		Environmental Impact Assessment

FERD		Foreign Economic Relations Department

GDP		Gross Domestic Product

GoN		Government of Norway

GoV		Government of Vietnam

HSE                      Health, safety and environment (including both the natural environment and the working environment)

HUMG		Hanoi University of Mining and Geology

IMRG		Institute of Mineral Resources and Geology

INGO		International Non-governmental Organizations

JICA		Japan International Cooperation Agency

Klif		Norwegian Environment Agency

MDG		Millennium Development Goal

M&E		Monitoring and Evaluation

MOIT 		Ministry of Industry and Trade

MPI		Ministry of Planning and Investment

NCA 		Norwegian Coastal Administration

NCFS		Norwegian College of Fisheries Science

NDRMPP	Natural Disaster Risk Management Program Project (World Bank)

NGI		Norwegian Geological Institute

NOK		Norwegian kroner

NORAD		Norwegian Development Agency

NORHED             Norwegian Programme for Capacity Development in Higher Education and Research for Development

NPD 		Norwegian Petroleum Directorate

NTNU		Norwegian University of Science and Technology

NTP		National Target Program to Respond to Climate Change.

NTU		Nha Trang University

NVE		Norwegian Water Resources and Energy Directorate

ODA		Official development assistance

OfD		Oil for Development Programme

PECC1		Power Engineering Consulting Company 1

PFM		Public Financial Management

PSA		Petroleum Safety Authority

PSU		Project Support Unit

PVN		Petrovietnam

RIA-1		Research Institute for Aquaculture No. 1

SC		Steering Committee

SEDP		Socio-Economic Development Plan

SIA		 Social Impact Assessment

ToC		Theory of Change

ToR		Terms of Reference

UiO		University of Oslo

UiT		University of Tromsø

UoB		University of Bergen

VNU		Vietnam National University

# Introduction

This report brings together key evaluation findings and lessons from four projects in Vietnam that were part of a broader evaluation of Norwegian capacity development (CD) support internationally. Those four projects were:

- Development of Management Systems on Safety and Working Environment and Environment Pollution Control in the Vietnamese Petroleum Industry (1996-2011) (hereafter referred to as the Petrovietnam or PVN project)

- Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change (2008-2014) (hereafter referred to as the Vietnam National  University or VNU project)

- Building Advanced Research and Education Capacity for Research Institute for Aquaculture No. 1 (RIA-1) in Vietnam (1998-2016) (hereafter referred to as the RIA-1 project)

- Improving Training and Research Capacity of the University of Fisheries, Vietnam (2003-2011) (hereafter referred to as the Nha Trang University or NTU project)

Separate reports have been written on each of these four projects – two members of the evaluation team (Stein-Erik Kruse and Tran Nam Binh) prepared the reports on the fisheries projects, while the other two team members (Joe Bolger and Dang  Ngoc Dung) wrote the reports on the PVN and VNU projects.  The broader international evaluation of Norwegian CD support also covers projects in Mozambique and Malawi as well as desk reviews of additional projects from a variety of countries.  Findings from the three country studies and desk reviews are being consolidated in a joint report on Norwegian support for CD.

# Country Capacity Development Overview

## Norwegian CD Support to Vietnam—the overall picture

Norwegian development cooperation with Vietnam dates back 40 years. Norway's current sector or thematic priorities in Vietnam are: climate, the environment and forest cooperation; renewable energy; technical cooperation; women and gender equality, and; culture. Collaboration in higher research and education are also priority areas for Norway’s development cooperation as are institutional strengthening and capacity building. Beyond these priorities, Norway supports the work of UN agencies in Vietnam as well as Norwegian voluntary organisations.

As indicated in the Introduction, two of the four projects covered in this paper are in the fisheries sector, while one is in the oil and gas sector and the final one deals with geo-disaster mitigation.

Once Norway initially decided to support the fisheries sector in Vietnam, one of the areas of support identified was building research capacity and technology to support development of the sector. The two projects identified above emerged from this decision. They are described in further detail in Section 3, along with the other projects covered in this report. Between 1999 and 2006, the approximate period of these two fisheries projects, Norwegian expenditures on fisheries support in Vietnam totalled NOK 65 million.

Norway committed to supporting Vietnam’s oil and gas sector in the 1990s. In 2005, this support came under Norway’s broader Oil for Development (OfD) program which was initiated by the Government of Norway (GoN) that year. Support for the mitigation of geo-disasters in Vietnam reflects the Norwegian Government’s commitment to climate change and renewable energy. Vietnam was also one of the three priority countries in Asia selected by the GoN for collaboration on preventive measures for natural disaster risk reduction and one of  four countries to concentrate on for climate change related programming.

## Central Government Priorities, Perspective on National Needs for CD

The two fisheries projects reviewed are in line with Vietnam’s national and sectoral plans and strategies which emphasize the role of fisheries in the country’s social and economic development. This is reflected in, among other things, Vietnam’s Fisheries Plan Towards 2020. Total production from fisheries in Vietnam had reached 5,300,000 MT by 2014 with a value of 4% of GDP. There was also a rapid increase in production from aquaculture from 3,481,000 MT in 2013 to 3,620,000 in 2014 while the export value of aquacultural products increased from USD 6.7 to 7.92 billion. It is thus evident from these figures that fisheries is playing an increasingly important role in Vietnam´s economic development and is a priority for the Government. It was recognized before the Norwegian funded projects were initiated that further development in the sector would require enhanced capacity in various areas, from human resources to technology, investment, financial services, business models, management, and an institutional framework for effective involvement of poor farmers, as well as the private sector, in supply or value chains.

The RIA-1 review highlights that the identification and design of the project was, to a large extent, driven by country demands and thus reflected the relevance of the initiative to Vietnam’s development priorities. However, some initiatives and documentation were initially developed by Norwegian partners and then directed through the appropriate channels to request assistance. This approach was seen as helping to strengthen the collaborative nature of the cooperation between Vietnamese and Norwegian partners.

For the PVN project, the goal, objectives and activities were clearly in line with national/sector strategies and plans, including the Oil and Gas Industry Development Strategy to 2015 and Vision to 2025 which included the goal of developing the sector based on environmental protection. PVN also came to realize that in order to work more effectively with other partners, and to meet its clients’ requirements, it needed to have operational and management systems that met international standards, especially in relation to health, safety and environmental management (HSE) practices. This reflected the projects overall objective which was to “establish a sustained process of further development of health, safety and environment in the Vietnamese oil and gas industry, so that major accidents and environmental damage are avoided.”

Finally, the priorities addressed in the geo-disaster project were directly in line with Vietnam’s national priorities. For example, the project supports two of the main objectives of Vietnam’s National Socio-Economics Development Plan 2011-2015 which are:

- Clearly improve and enhance quality of education, training and human development, and

- Strengthen the protection of natural resources and environment, and actively respond to climate change impacts.

## Central Government Perspective on Donor Role in CD (including Norway)

The Vietnamese government welcomed the support offered by Norway in the projects reviewed. As noted above, Norway has a long history of development cooperation programming in Vietnam, including in the areas covered in this report. In several of the initiatives highlighted in this document, the engagement with Norwegian partners pre-dated the project start up. In some projects, including the PVN project, Vietnam drew on Norway’s experience early on, e.g. Norway’s “HSE model” for the oil and gas sector, to establish regulations for the sector but increasingly took over more responsibilities as the project advanced. Similarly with the RIA-1, the Norwegian Embassy was less involved in the third phase compared to the first two phases as it increasingly took more of a hands-off approach.

In the projects reviewed, there was no evidence that any specific guidelines or tools were used for reviewing aspects of or approaches to capacity development by Norway, the Government of Vietnam (GoV), or local implementing partners, although dialogue was maintained through annual meetings and informal exchanges which, in theory, would have at least provided opportunities to review such matters. There also appears to have been limited links between project-based interventions at the organisation/local level and policy dialogue at the national level. And dialogue between the Embassy and various government Ministries did not seem to draw on or benefit from CD lessons from other projects.

Specifically in terms of the donor role, for all of the projects reviewed, the Norwegian Embassy was formally responsible and the contractual partner to the national and local coordinating and implementing partners. The Embassy played a role in the design phase, follow up on the appraisal, annual meetings – reviewing and commenting on narrative and financial reports and plans and budgets for the upcoming year – as well as commissioning independent reviews and evaluations.

While the projects were largely shaped around institutional collaboration arrangements between Norwegian and Vietnamese institutions, there was no explicit demand from the Vietnamese partner in the RIA-1 project for collaboration with Norwegian universities which was simply perceived as part of the agreement with Norway. For example, Norwegian support in the sector focused more on fisheries-related academic and research capacity, with connections to Norwegian and other international academic networks, but with less attention to issues such as strengthening market-oriented approaches. Nevertheless, the technical support provided by Norway through this and the other projects was, as suggested, valued by Vietnamese partners.

## Governance of ODA and CD

Arrangements are in place to oversee governance of official development assistance (ODA) in Vietnam. For example, in 2010, an Aid Effectiveness Forum (AEF) was established to focus on aid policy, aid effectiveness and implementation of Vietnam’s Socio-Economic Development Plan 2011-2015 (SEDP). The forum brings together diverse stakeholders, including the GoV, donors, Vietnamese agencies, international non-governmental organizations (INGOs) and Vietnamese civil society organizations (CSOs).  At the outset in 2010, the AEF was co-chaired by the Director General of the Foreign Economic Relations Department (FERD), Ministry of Planning and Investment (MPI) and the Chief Representative of JICA in Vietnam.

Progress Reports on aid effectiveness have been prepared for 2010 and 2011 to review the implementation of aid effectiveness activities and to identify priorities for the following year.  The 2010 report noted “tangible progress” in: GoV ownership and leadership in development strategies and policies (SEDS 2011 – 2020 and SEDP 2011 - 2015); strengthening country systems (Public Financial Management (PFM), Pubic Investment Reform, etc.); harmonization and alignment (Public Procurement, Social and Environment Impact Assessment (SIA/EIA); results-based management (Viet Nam’s MDGs Report), and; mutual accountability (PD/HCS Independent Evaluation (2nd Round).

Vietnam also has a Comprehensive Capacity Building Programme for ODA Management (CCBP) which is co-funded by the World Bank and the Like-Minded Donor Group. It seeks to develop ODA management and implementation capacity in the Vietnamese administration.  Recent efforts include reforming Vietnam’s legal framework for ODA management and training government officials on project management and aid effectiveness. The AEF Thematic Working Group on Capacity Development also organized a series of workshops on CD in 2010. The workshops were facilitated by a CD expert from the EU and brought together a number of line-ministries to take stock of the current situation and to identify appropriate approaches for advancing the CD agenda in Vietnam.

To monitor investments in country, Vietnam has developed a standardised monitoring and reporting tool which most major donors now use.  The tool developed helps to monitor progress towards Vietnam’s national development goals and is seen as a step towards the development of a standardised M&E system for ODA activities.

Based on the projects reviewed, it appears that the needs are usually identified by Vietnamese institutions but in the case of the fisheries sector at least, the project designs grew out of Norad assessment missions. The proposals were then reviewed by Norwegian Embassy staff, with input from Oslo-based Norad staff, and then approved by the Embassy which signed the project agreements on behalf of the Norwegian Ministry of Foreign Affairs, with the Government of Vietnam, who signed on behalf of the local executing partners.

While the GoV had a strong interest in the various projects reviewed, their involvement during implementation was relatively modest. Decision making rested largely with the Norwegian and Vietnamese implementing partners operating under the direction of Project Steering Committees that usually met annually.

## Monitoring, Accountability and Adaptation

Like some of the other projects reviewed, the PVN project was weak in monitoring & evaluation and in terms of systematically applying a results-based approach. For example, the project initially lacked a baseline to effectively monitor project implementation, although a baseline survey was conducted at the beginning of Phase III. The Project Support Unit (PSU) was responsible for day-to-day management of the PVN project, including monitoring progress. All activities and outputs, including the dates of completed activities, were reported in the regular progress reports. Project reviews and interviews suggested that the PVN project was substantially successful in achieving expected results, even though it did not use indicators routinely to verify expected results and reporting was mainly at the activity/output level. In addition to ongoing monitoring, the project had regular independent audits, reviews and appraisals.

The evolution over the course of the three phases suggests the PVN project benefited from ongoing learning which allowed adaptation by the project team to the evolving needs and priorities of Vietnamese stakeholders. The step-by-step approach also allowed project stakeholders to lay the required building blocks which would help to ensure sustainability of results beyond the term of the project, and the Project Steering Committee provided a forum for sharing and making decisions about adaptation or adjustment of approaches, as necessary.

The Desk Appraisal for the original VNU project proposal noted weaknesses in the proposal in terms of the results logic, e.g. not outlining the overall goal, outcome, outputs and associated activities in a Logical Framework format with indicators, which made it difficult to get a clear sense of how the various activities were linked and would contribute to higher level results. The appraisal went on to note that with these shortcomings it would be difficult to monitor progress towards expected results. During implementation, progress reports lacked detail in terms of reporting on specific results achieved against planned results, and deviation analyses. And performance indicators were not used systematically in monitoring and reporting within the project. It wasn’t until later in the project that the project explicitly reported progress against expected results, albeit at the activity/ output level.

However, the VNU project has demonstrated flexibility over time, e.g. changing implementing partners and extending more support to community level beneficiaries after Phase I which saw the results of pilot activities not extend beyond local authorities.  Phase II also followed up on 5/7 recommendations from the evaluation at the end of Phase I, including strengthening participatory approaches.

Ensuring effective monitoring was among the planned outputs for Phase I and II of the RIA-1 project. However, the part of the review team looking at the fisheries projects noted that, as with the other projects, there were gaps and limitations in the project’s M&E system. Furthermore, no external independent evaluation of Phase 1 was carried out, although a mid-term review of Phase 2 was conducted and a mid-term review of Phase 3 was planned for the latter part of 2015. As such there was weak documentation and assessment of the implementation and results of the project, including the capacity development aspects. Indicators were identified in the RIA-1 project proposal, but no monitoring system was described – how and when data and information would be collected. As a result, targets and indicators have not been used for regular and systematic monitoring of progress and achievements. Furthermore, there is no M&E unit in the project or staff designated as being responsible specifically for monitoring.

There has, however, been a logical and sound progression in the RIA-1 project from Phase 1 through Phase 2 and 3. Phase 1 focused on human resources development – training a critical mass of staff at RIA-1 to a higher technical and academic level. Phase 2 continued with developing and strengthening internal human capacity, but also included extension activities – reaching out beyond RIA-1 as an institution. Phase 3 focuses on marine fish farming in a wider context. The last phase not only builds on strengthened capacity of RIA-1, but involves stakeholders, such as investors, supply industry, vocational schools, research institutes and universities in the practical implementation of the three closely interlinked components. All of the preceding suggests the project was adaptive and adjusted as it unfolded, including CD aspects, even if the approach to results-based management was weak and the orientation wasn’t based on careful assessment of alternatives.

The Chief Technical Advisor (CTA) on the NTU project was responsible for providing technical assistance on project management, including monitoring and evaluation. As with the other projects though, this one had problems with the results-based orientation, and accordingly with systematic monitoring. For example, the development goal for the project was more at the output/outcome level, performance indicators did not have clear targets and were not measured or used in monitoring and reporting.

## Donor Coordination

Vietnam has demonstrated strong country ownership of its development cooperation programs, led by the Ministry of Planning and Investment (MPI). Coordination is based on the five-year Socioeconomic Development Plan, the Hanoi Core Statement on Aid Effectiveness and the Vietnam Partnership Document, which adapt the Paris Declaration on Aid Effectiveness and the Busan Partnership agreement to the Vietnamese context. The government has driven the poverty reduction agenda, sometimes based on priorities that differ from donors. Overall, as a result of the strong country ownership, donor support has tended to be well aligned with country priorities.

Vietnam has an effective model for donor coordination at the policy level, although that wasn’t evident in the four projects reviewed.  Donor coordination is carried out through multiple fora that provide opportunities to exchange information, agree on common priorities and develop joint plans. All of the major donors and development partners are actively engaged in the GoV’s donor consultative group coordination process. The Government (MPI and Line Ministries) and members of the donor community officially conduct Consultative Group (CG) Meetings annually to review the aid effectiveness and provide the aid commitments for the following year. As noted in Section 1.4, an annual Progress Report on aid effectiveness is prepared covering poverty reduction and each main sector and presented at the annual meeting. Furthermore, CG meetings are held at mid-year intervals, organized at the local level which creates opportunities for donors engage more closely with communities and to get a sense of their needs.

Other donors were already supporting or gearing up programming in the area of geo-disaster mitigation at the time the proposal for the VNU project was submitted to the Norwegian government. The support from Norway was intended to complement those efforts. However, the desk appraisal of the initial proposal by Norad referred to short-comings in the coordination and cooperation among on-going programs and activities on geo-disaster mitigation while cautioning that how the proposed project would relate to them and add value was not well defined. The actual point of departure for the project was supposed to be the World Bank’s Natural Disaster Risk Management Program Project (NDRMPP), but it wasn’t apparent from the proposal how that would be done as there was no analysis of how gaps in the NDRMPP would be addressed. Nor did it describe how it would complement other donor-supported initiatives (e.g. supported by Care Denmark and the Government of the Netherlands).

In Vietnam’s fisheries sector, several other donors provide technical and financial support. Amongst others, FAO and DANIDA are considered important donors, the latter in particular through its Fisheries Sector Programme Support. However, Norway has been the most important external donor to NTU and will continue to be so through the new Norwegian Programme for Capacity Development in Higher Education and Research for Development (NORHED) programme.  There are no references in NTU documents though to other donor projects that helped inform investments in this particular project, even though there were many at the time of project implementation.  Furthermore, coordination with other donors involved in the fisheries and education sectors, or in policy dialogue with the relevant ministries, was not reflected in the design and implementation of the NTU project. Similarly, no other donors are mentioned in any of the planning documents for the RIA-1 project. And there is no evidence of any formal donor coordination in support of RIA-1, although most likely some informal consultations have taken place as well as annual donor meetings.

## National Context for Public Sector CD

Vietnam provides a good example of what has been described as a “mature development partnership”.  The country’s development agenda has a high level of national ownership, backed up by a predictable policy environment, relatively strong public sector institutions and high rates of economic growth. It now has reached Middle Income Country status (GDP of US$1,000 per capita) and has an enviable record on poverty reduction (among the most successful in the developing world). Vietnam is one of the top ten recipients of ODA with pledges of US$5.4 billion in 2008.  Japan, the World Bank and the Asian Development Bank account for 80% of ODA.

Despite these high levels of ODA, Vietnam is not considered ‘aid dependent’ as ODA represents less than 12% of the budget, i.e. less than foreign direct investment, remittances or tourism revenues. For Vietnam, international exposure, knowledge transfer, and development of specialised capacities seems to be more of a priority than money – something that need be reflected in CD strategies. Vietnam has also demonstrated a high level of commitment to the aid effectiveness agenda with strong leadership from the Ministry of Planning and Investment.

Nevertheless, aid in Vietnam is still seen as being fragmented given the number of donors and the correspondingly large numbers of projects with the public sector, often delivered through parallel management arrangements.  In addition, donor disbursement rates remain low and inconsistencies persist between Vietnamese and donor rules.

Despite these challenges, the interventions reviewed as part of this exercise generally demonstrated high levels of political and bureaucratic support with legislative and often financial backing from Vietnamese partners. These were considered important pre-conditions for effectiveness.  The one-party system in Vietnam also means that there is clarity on policy matters and support from the central government once initiatives have been agreed to.

# Capacities of the Norwegian Embassy and its Partners

The Norwegian embassy in Hanoi has experienced and capable personnel (Norwegian and Vietnamese) but is stretched in terms of its ability to identify, design and take overall implementation decisions (and responsibility) on CD.  The process on the projects reviewed usually started, as outlined above, with local partners identifying the need, developing a proposal (sometimes in concert with Norwegian stakeholders) and then submitting it to the Embassy for review and eventually approval.  Embassy staff involved reviewed the proposals and shared them with Norad staff for their inputs and advice.

From a limited selection of exchanges viewed, it appeared that the Norad staff offered advice to the Embassy on ‘developmental’ concerns which were either accepted or not by the Embassy before approval was granted. In the case of the VNU project, for example, Norad staff raised concerns regarding the lack of clarity on VNU’s own capacities with respect to geo-disasters and to manage a project of this nature, the “technical (engineering) approach to geo-disaster mitigation management”, and the lack of details on how the project would deal with social and socioeconomic dimensions of geo-disaster mitigation and planning. A revised proposal submitted by VNU addressed some of these concerns but was still considered by Norad to be “weak”, e.g. the link between proposed activities and expected results, and lack of clarity on how socio-economic aspects would be dealt with during implementation. Nevertheless, the revised proposal was approved by the Norwegian Embassy which subsequently signed a project agreement with VNU.

Further in terms of Norad’s role, members of the review team were told that in years past Norad had more influence in embassies overseas as decision-makers on development programming. Now, it appears, as the example above suggests, that Norad offers inputs through long distance advice from staff based in Oslo. Most of this input is ‘technical’ in nature, e.g. education, health, climate change, seemingly with less attention to cross-cutting issues such as capacity development. The net result, it would seem, is that embassies are now less involved in substantive programmatic issues, including planning and implementation of projects, essentially keeping more of a ‘hands-off’ approach.  That would seem to include approaches to capacity development, despite the fact that Norad reportedly has CD guidelines.

As to the capacity of Norwegian partners to oversee and implement CD activities, the VNU case suggested that some of the partners involved in the institutional collaborations have essentially taken on Norad´s historical role between the embassy and local partners, leaving them with the technical/programmatic responsibility. Such a role leads to the potential for self-interest, e.g. Norwegian universities forcing Nha Trang to change from using Vietnamese to Norwegian supervisors – meaning that PhDs should be taken in Norway, rather than Vietnam with associated benefits for Norwegian universities.  Most Norwegian partners were seen as being strong in terms of their technical skills and abilities, however, they do not appear to have been bound by any specific Norwegian guidelines on issues such as capacity development which has meant, in practice, often limited attention to pre-implementation assessments of local capacity, a tendency towards activity-based approaches, limited tracking of capacity results (especially at the institutional level) and lack of clarity regarding the relationship between  capacity improvements that are realized and their resultant impact on performance.

# Summary Description of Individual Interventions

## Development of Management Systems on Safety and Working Environment and Environment Pollution Control in the Vietnamese Petroleum Industry, Project SRV-0020 (PVN Project)

In 1995, the petroleum industry in Vietnam was regulated by the Petroleum Law and associated regulations. Vietnam did not have its own health, safety and environmental (HSE) standards for the sector and HSE legislation that did exist was broad and generally applicable rather than being specific to the challenges of the petroleum industry. As a result, HSE concerns were regulated by Soviet-influenced standards and standards set by the international oil companies operating in Vietnam at that time.

With the intent of operating as an international entity, PVN, Vietnam’s leading state owned oil and gas company, identified the need to improve its HSE standards.  PVN reached out to Norway for support given its long history in the sector and its well established HSE systems. A three phase project followed from 1996-2011. The implementing parties on the Norwegian side were the Norwegian Petroleum Directorate (NPD) (later the Petroleum Safety Authority - PSA), SFT (later Norwegian Environment Agency - Klif) and the Norwegian Coastal Administration (NCA). The Vietnamese counterpart throughout has been PVN.  Over the three phases, Norway contributed approximately NOK 54.125.000 (USD 8 million) to support implementation of the project.

The first two phases focussed substantially on establishing guidelines, developing tools, enhancing relevant knowledge, and exposing Vietnamese stakeholders to relevant experiences elsewhere. Phase III was designed more to support implementation of the management system and to provide more advanced training, e.g. technical audits, and provision of support for specific “practices” relating to HSE.

## Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, Project SRV- 07/056 (VNU Project)

Vietnam faces a number of challenges relating to the potential impacts of geo-disasters triggered by climate change, earthquakes, typhoons, landslides or subsidence. However, the country has had insufficient capacity (e.g. knowledge, skills, capable institutions) to deal with such challenges effectively.  In response to this, Vietnam National University (VNU) prepared a project proposal seeking support from the Government of Norway to improve its capacity, and that of selected partners, in geo-disaster mitigation and in the process to assist the country to deal with potential geo-disasters.

Norway responded positively to the proposal and the result was a two phase project which commenced in 2008 and was still ongoing at the time this report was written. VNU is the lead implementing agency for the project but collaborates with other Vietnamese agencies and is supported by various Norwegian entities: Norwegian Geological Institute (NGI), University of Oslo (UiO) and Norwegian Water Resources and Energy Directorate (NVE).  The overarching objective of the project has been to “reduce the impact of Geohazards in Vietnam in the context of changing climate”. This was to be done by enhancing the capacity of VNU, and other institutional actors in Vietnam, and by supporting pilot projects in ‘at-risk’ communities.

## Building Advanced Research and Education Capacity for Research Institute for Aquaculture No. 1 in Vietnam (RIA-1 Project)

Since 1998, the Government of Norway has provided financial and technical assistance to Vietnam for developing the aquaculture sector. One important component has been support to the Research Institute of Aquaculture (RIA-1). Phase 1 was undertaken from November 1998 til October 2002. The overall goal of the project was “to contribute to poverty alleviation through increased use of sustainable aquaculture in Vietnam” and the stated objective was ‘to attain improved capacity of RIA-1 in research, education and extension based on demand and appropriate needs of small scale aquaculturists in Northern Vietnam”.  Phase 2 commenced in late 2003. It differed from Phase 1 as it had a stronger emphasis on participatory research with farmers. The project sites were planned to cover three provinces and to include extension activities. The Vietnamese Government cash contribution was equivalent to NOK 2,667,655 while the Norwegian contribution was NOK 17 million.

The original plan for the third phase was for it to be carried out from January 2011 through December 2014, but it did not start until 2013 and will come to an end in 2016.  Phase 3 has sought to focus on marine fish farming in a wider context. The third phase was named “Capacity Building in Marine Fish Farming of Vietnam”, indicating the broader approach and involvement of stakeholders, such as investors, supply industry, vocational schools, research institutes and universities in the practical implementation of three closely interlinked components.

The project was executed by the Ministry of Fisheries (which was merged into the Ministry of Agriculture and Rural Development from 2007) and implemented by RIA-1 with technical assistance contracted from different international sources including an institutional agreement with SINTEF Fisheries and Aquaculture, Norway.

## Improving training and research capacity of the University of Fisheries, Vietnam, Project SRV2701 (NTU Project)

The Governments of Vietnam and Norway signed an agreement in June 2003 to support “Improving training and research capacity of Nha Trang University (NTU)”. Norway offered a grant of 17 Million NOK for the period 2003-2008. Several Norwegian partner universities were involved: the University of Tromsø (UiT), Norwegian University of Science and Technology (NTNU) and University of Bergen (UoB).  With a commitment to continued support, NTU and the Norwegian universities developed a phase 2 proposal (2008-2011).  A Phase 2 agreement was signed in January 2008, with a grant of 16.798 Million NOK and in December 2008, a contract was signed between the Norwegian College of Fisheries Science (NCFS) – University of Tromsø as the coordinator of Norwegian technical support and Nha Trang University regarding “Improving Training and Research Capacity of NTU”.

The project goal for both phases was expressed as follows: “Improved training and research at Nha Trang University makes significant contribution to meet human resource needs in the fisheries and aquaculture sector in Vietnam”. The objective was: “Nha Trang University delivering improved research and training services to fisheries and aquaculture in Vietnam”. The ultimate beneficiaries of the project were to be students at NTU and people in the fishery sector, while most of the project activities also benefited teaching staff, researchers and managers at the university. Institutional cooperation between universities in Norway and Vietnam was an essential feature of the project.

# Findings

## Relevance of Strategies and Initiatives

The Oil and Gas Industry plays a very important role in Vietnam’s economy. It accounted for nearly 10% of Gross Domestic Product (GDP) during the past decade with outputs of 3.96 million tons of oil in 1991 growing to 17 million tons in 2014. PVN has contributed, on average, about 20% of the country’s total budget revenue for the past decade (the highest contribution being 30% in 2006). Vietnam’s oil and gas sector grew dramatically from the early 1980s onward.  With that growth came demands for the sector to enhance its capacity with respect to HSE issues. The PVN project was thus clearly relevant to Vietnam and, more specifically, responsive to needs within the petroleum sector, especially as it engaged more international actors and sought to embrace international HSE  standards.

For the VNU intervention, natural disaster risk reduction is a declared priority of the Vietnamese Government in Socio-Economic Development Plans (SEDPs) 2006-2010 & 2011-2015, the Governmental Action Plan Framework for Adaptation and Mitigation of Climate Change in the Agriculture and Rural Development Sector Period 2008 -2020 and the National Target Program (NTP) to Respond to Climate Change. The World Bank has also ranked Vietnam first in terms of the potential impact of climate change on population, GDP, urbanization and wetland areas which further underlines this area of investment as a national priority. The project was approved in response to these concerns and based on a perceived need to enhance scientific knowledge on geo-disasters in Vietnam, and with a view to “develop methodologies and models to help reduce the vulnerability of the country with respect to natural disasters.”

In terms of the relevance of the VNU project to participating institutions, the geo-disaster training and research activities funded by the project have not only benefited students, lecturers and researchers of the main implementing partners such as VNU (one of the biggest educational institutions in Vietnam), Hanoi University of Mining and Geology (HUMG) and Power Engineering Consulting Company 1 (PECC 1), but has also benefited others such as the Institute of Mineral Resources and Geology (IMRG), the Institute of Geotechnics, University of Civil Engineering, University of Transportation and the Ho Chi Minh City University of Architecture. Indications from project reports and interviews are that the training and research opportunities afforded through the project have been relevant to the needs and interests of the students/researchers associated with these various institutions, and have contributed to personal/institutional learning.  The project pilot activities also targeted relevant entities and issues in various regions of the country, e.g. hydropower plants and communities subject to coastal erosion.

Both the RIA-1 and NTU projects have been relevant to Vietnam’s development priorities as they are in line with national and sectoral plans and strategies in Vietnam which emphasise the role of fisheries in social and economic development. Fisheries and aquaculture were identified as priorities in various government policy documents, including Vietnam’s Comprehensive Poverty Reduction and Growth Strategy (CPRGS, 2002). In the latter, development of the coastal economies, including marine aquaculture, were seen as one way of reducing poverty. Marine fish farming was also seen as a potentially lucrative industry with export and domestic seafood market opportunities which could bring direct and indirect support businesses and job opportunities related to production, processing, transportation, marketing, sales and maintenance.

Ultimately though, the RIA-1 and NTU projects were only able to respond to a small part of the national priority and demand, i.e. only technical capacity of production at small scale and mainly in the North and Central parts of Vietnam, research work and human resource development. With limited resources the project could not touch other important demands in terms of providing qualified people, technologies, and research support for processing, transportation, branding, marketing, sales and maintenance, etc., which became more important later on.

## Fit with Context-specific Factors

Analysis of Context and Capacity Needs

In the PVN project, Norwegian authorities carried out a fact finding mission in Vietnam in order to gain background information to help assess the initial proposal from PVN. The Itad evaluation team didn’t see the report from the fact finding mission, so it’s not clear the extent to which or how capacity or other issues were addressed at that stage. Further along in the project, a report from Norske Veritas (DNV) commented on training provided in Phase II suggesting that further analysis and surveys (should be) made “to verify the benefit to PVN’s organisation”. It also called for a training needs assessment to start up Phase III of the project.  Based on that recommendation, a Baseline Assessment was undertaken in 2009 as the first activity of Phase III which reportedly was broadened to include not only a training needs assessment but also a capacity assessment and analysis. The Baseline Assessment led to several findings on capacity weaknesses and recommendations for follow up. While it is a positive that that the assessment was carried out, it appears that the project didn’t benefit from having a similar exercise to inform strategies in the first two phases.

Norad’s Desk Appraisal of the initial VNU project proposal noted how VNU described itself in the proposal as one of the ”nodal points in Vietnam for geohazard studies” without being clear on its own capacities and shortcomings or those of other relevant stakeholders in Vietnam. And as far as the Itad review team was able to determine, no formal assessment of capacity needs or shortcomings (for VNU, and/or other institutions) was undertaken at the outset to give more precision to the proposed interventions outlined in the project proposal. Having said that, specific interventions, e.g. through the pilot projects built on research undertaken on potential risks in the communities engaged.  The bottom line though is that the project lacked formalized ‘evidence’ on the nature or scope of the capacity challenges to be addressed through the project.

In the RIA-1 project, lessons learned from the second phase fed into planning of the third phase. For the third phase of the project, a concept note was developed which focused on developing greater output from marine fish farming, e.g. including support for demonstration and vocational training. The concept note was circulated among government and provincial officers, the Norwegian Embassy, Norad and other stakeholders. The concept note then served as input to a Logical Framework Approach Workshop which involved 35 stakeholders, including RIA management and senior staff, the Chief Technical Advisor for Phase 2, GoV officials from various ministries and departments, one representative from the Vietnamese private sector, and two international resource persons with expertise in marine aquaculture sector development in Asia and the Mediterranean.  However, no broader, systematic economic analysis or assessment was carried out as a basis for the new phase of the project e.g. an analysis of the needs and opportunities among stakeholders such as investors, the supply industry, vocational schools, research institutes and universities in the three interlinked components.

The planning process for Phase II of the NTU project was described in the Desk Appraisal as being of high quality. A participatory approach was applied. Prior to the planning workshop, a comparative institutional assessment was commissioned to map the University within the broader national education system. The assessment provided information on the strengths and weaknesses of the University. The planning workshop involved all key stakeholders from Phase I, including decision makers from NTU and representatives from Norwegian partners and central ministries, including MOIT and MPI. The participatory approach was found to be effective as it helped to accelerate the planning process. However, the institutional component (component 6) wasn’t informed and guided by a proper assessment of NTU´s internal capacity.  And no broader, systematic economic analysis of the sector or of needs and opportunities among stakeholders was carried out as a basis for the project.

In sum, the strategies and designs for the various interventions did not seem to be based on formal analyses of the project contexts, including assessments of prevailing institutional dynamics, or the social, cultural, political and legal environment. However, as noted earlier, they were all consistent with the political priorities of the GoV and either helped to buttress or strengthen the legal and/or institutional environments within which they were operating.  Relatively little was done, however, through the projects to influence factors external to the partner institutions, such as demand and accountability mechanisms, due in part to the scope or mandate of the projects which tended to focus on internal institutional priorities, an exception being the engagement of local authorities and communities potentially at risk with respect to geo-disasters in the VNU project.

Theory of change

None of the projects reviewed in Vietnam, with the exception of the RIA-1 project, had an explicit theory of change (ToC). Rather, they relied on results frameworks to guide implementation. However, each of them had what are described in the individual reports on each project as ‘implicit’ ToCs.  The implicit theory for the PVN project, for example, appeared to be (in brief) as follows: With appropriate policies, regulations, guidelines, management systems and trained personnel, developed with the support of external partners, Vietnam would be in a position to incorporate and rely on international level health, safety and environmental standards and practices on an ongoing basis in its petroleum sector to avoid major accidents and environmental damage.  In the NTU project, the implicit TOC, in simplified terms, was that more and better training, research and policy advice from NTU would result in improved human resources in the fisheries and aquaculture sector.

What consideration of possible or implicit ToCs reveals though is that while the projects may have had ‘logical’ results frameworks, they were built on assumptions which may or may not hold over time.  For example, in the NTU project, it was assumed that better trained staff would produce more and better qualified graduates and that they subsequently would become absorbed in the fisheries sector after graduation. It was also assumed that the skills of the students who graduated, and the research carried out, are relevant and eventually will improve the quality of skills and experience more broadly in the sector. In the case of the PVN project, it was assumed that development and implementation of HSE standards would succeed if key sector stakeholders had the requisite political and organizational support to advance this agenda, if oil and gas remained centrally important to the Vietnam economy, and if sufficient capacity was developed or strengthened (in PVN and beyond) to ensure full application of the appropriate standards.

In the case of PVN, those implied assumptions held, by and large, throughout the project period and the result was the development and implementation of HSE standards to a fairly high level in a relatively short period of time.  In other projects, it’s too early to declare if the implicit assumptions, held or not, although questions were raised, for example, in the VNU report about the assumptions that support provided to individuals for training or research would necessarily lead to change at the institutional level absent appropriate strategies for institutional change.

Learning how CD has worked elsewhere

None of the project designs or implementation strategies reflected learning specifically about how CD (e.g. methods, strategies) worked elsewhere. However, they all drew, to different extents, on experiences in and outside of Vietnam to inform their approaches to the technical issues addressed in the projects concerned, e.g. about fisheries, or how to mitigate environmental disasters.  In the case of the PVN project, for example, participants were exposed to formal learning and practical exposure opportunities in Norway to enhance their skills and knowledge on HSE issues.  Under the VNU project, Vietnamese participants benefited from sharing of experiences/materials with Norwegian partners, training in Norway (at University of Oslo (UiO) or at the Norwegian Geotechnical Institute (NGI)), and by participating in international conferences.  In the process, they learned from international experiences about, for example, hazard and risk assessment techniques for mitigation of natural disasters, use of appropriate technology (e.g. remote sensing) while enhancing their skills in areas such as mapping.

The RIA-1 project has not directly used evidence or models from other countries – partly because Vietnam was considered a pilot country. However, exposure to different academic environments, such as Norway, was highly valued, as it was seen as essential for new perspectives, learning new practices, and gaining important insights into how to develop one’s own institution. Further with respect to RIA-1, there are no references to other projects in Vietnam in the available documents although there were many international donor-funded projects being implemented by RIA-1 at the same time. It wasn’t clear the extent to which lessons learned from other projects have served as inputs for the planning of the RIA-1 project, but references were made to similar projects in Thailand and the Philippines in RIA-1 project documents.

The Norwegian implementing partners in each of the projects also had considerable prior overseas experience which they would have drawn upon to support CD efforts in Vietnam. Furthermore, the fisheries projects were important “brokers” to international exposure e.g. supporting study trips to countries other than Norway.

Local Ownership

There was a high level of national ownership in the PVN project which helped to drive capacity development efforts throughout the three phases.  Ownership was evident at different stages in different ways.  For example, it was PVN that identified the need to improve its HSE standards, and Vietnamese stakeholders participated actively in the Phase I design. However, implementation in Phase I relied significantly on Norwegian expertise. Responsibility for implementation shifted in the subsequent phases such that by Phase III Norwegian experts were relied upon mainly for technical back up and provision of advice on an as required basis.  Ownership was also evident though in the governance of the project as PVN effectively chaired the Project Steering Committee which played a key role in the project.

Having said that, the nature of the institutional collaboration was such that Norwegian partners, according to some sources, sometimes “came with their own agenda” or way of doing things with the attendant risk of supply-led approaches. By and large though, the Vietnamese partners were sufficiently confident that they were able to ensure that their priority interests were being served through the project.

The VNU Project also had a high level of national ownership as VNU submitted its own proposal to the Norwegian Embassy, established partnerships with Vietnamese and Norwegian partners, specified its own needs and those of local communities, and took leading roles in project design, planning, management and reporting. VNU also housed and led the Program Management Unit. The review paper on VNU though argues that “ownership” in this project may have been too focused on VNU, not extending sufficiently to other partner institutions or the community level.

In RIA-1, the project identification and approval processes were clearly defined and participatory in nature, but were done without the necessary strategic planning capacity, including understanding and techniques, especially for CD purposes. In general, Norwegian support in the project was demand-driven, with the Vietnamese government identifying needs and approaching Norway for support. Responsibility for implementation and management was delegated to the Vietnamese implementing organization. Technical support has been provided by institutions or persons contracted by RIA-1. However, it was reported that RIA-1 did not have a choice in selecting the Norwegian technical partners.

The NTU project was developed in close cooperation between NTU and Norwegian Universities and based on clear demands and interests articulated by NTU pertaining to the substance of training and research. However, Norwegian Universities engaged through the institutional collaboration had their own interests in how the project was designed, according to the Mid-term Review (2010). The review also noted that the research interests of the Norwegian advisors played a part in defining areas for research and technical training – rather than being purely defined by the needs of the sector in Vietnam. There was also a serious dispute between NTU and the Norwegian universities before the signing of the Phase 2 agreement. NTU had suggested that all PhD students should be registered at NTU using Norwegian professors as co-supervisors, but the Norwegian consortia of universities stated that it was not possible for them to sign the contract under such conditions as Vietnamese students had to be registered at a Norwegian university either as full time or as sandwich PhD students alternating between Norway and Vietnam. Ultimately, NTU had to accept the Norwegian conditions.

Donor Fit

As noted earlier in this paper, Norway has a long history of development cooperation programming in Vietnam. The sectors of involvement in the four projects under review are consistent with Norway's current priority areas for development programming and Vietnam’s sectoral priorities.

When Norwegian development aid was initiated more than fifty years ago fisheries was an obvious sector choice. Being a “country of fishermen”, or at least with high-level academic competence and technical/practical experience in aquaculture placed Norway in a good position to assist poorer countries to develop and modernize their fish industry. Despite several failures and shortcomings, the fishery sector has remained an important part of Norwegian development cooperation (Evaluation 2008). Specifically in the RIA-1 project, the standard of technical assistance provided was considered to be generally high and RIA-1, as a local institution, clearly benefited from the skills of the Norwegian advisors on the project team.

The NTU project in general, and the institutional cooperation in particular, have been a good fit, not only for Vietnam, but also for Norway and Norwegian universities. As with RIA-1, the standard of technical assistance has been considered to be generally high and NTU has benefited from the skills of the Norwegian advisors in the areas of fisheries economics, fish disease, fish nutrition, and biopolymer research – all highly relevant to the needs of the University and the fisheries sector in Vietnam.  However, feedback from interviewees suggested that the project could have been designed in a way that Norwegian skills could have been complemented with technical assistance from other institutions in Vietnam, the region and other parts of the world resulting in strengthened relationships for NTU with a greater range of institutions and broader collaborative research opportunities.

With respect to the PVN project, Norway has vast experience in the oil and gas sector and was able to share that effectively with Vietnamese stakeholders through the three phases of the PVN project.  Reliance on the Norwegian partners (e.g. PSA, NCA, Klif) was a good fit in terms of the needs of PVN as they provided the technical expertise required to advance PVN’s HSE agenda.  As noted in the 2012 End Review, “The Norwegian “HSE model” for offshore petroleum industry is regarded as leading internationally and had already spurred developments in other countries.  The Norwegian institutions involved have all played a key role in developing the Norwegian model and possess unrivalled expertise thereon.”

As noted earlier, climate, the environment and forest cooperation is one of Norway’s priority programming areas.  With respect to this priority area, Vietnam is described on Norad’s web sites as “as one of the country's most important partners in the area of climate and forests.” This stems, in part, from Vietnam’s commitment to reduce greenhouse gas emissions by 2020. Furthermore, Norway has also recognized that Vietnam is one of the countries most vulnerable to climate change due to rising sea levels which could have a significant impact on, among other things, the country’s food security. Norway’s commitment to climate change, environmental issues, and prevention of natural disasters follows from these realities. It also builds on historical relationships between VNU and NGI which were carried forward in the VNU project.  The donor fit is thus seen as a positive one given Norway’s history of engagement in Vietnam, its current commitment to the areas addressed in this project and the institutional capacity and experience Norway has been able to share with Vietnam through the two phases of this project.

## Perception of Donor’s Role in CD

Partner institutions didn’t have strong views on the donor’s role in CD. This was mainly because their primary relationships, especially on CD matters, were with the institutional partners from Norway.  Nevertheless, they could potentially have engaged with the donor on such issues in Steering Committee or annual project meetings, if not during the appraisal process. Nobody indicated to evaluation team members though that CD issues were prominently discussed in such fora.  Overall though, local partners had a strong sense of trust in the donor and were grateful for the flexibility afforded, when necessary, and for the quality and duration of the support.

In terms of the “appropriate role of donors’, partner institutions in Vietnam tended to see the donor as a source of funding and technical support that played a relatively modest and non-directive role in project implementation.  As far as the review team was able to determine, the donor was not relied upon to pay a significant role in dialogue with government, or other donors.

## Results-orientation, Learning and Improved Effectiveness

The PVN project did not use an indicator set to verify expected results. However, the results of the project were deemed to have been achieved when the project realized expected outputs associated with specific activities included in the logframe. The review team was informed that the project regularly monitored all activities and outputs in each phase and the dates of completed activities were reported in the regular progress reports. Reviewing progress on implementation was mostly conducted by project stakeholders through regular consultations and Steering Committee meetings. However, the baseline survey was only conducted, as noted, at the beginning of Phase III. Despite this late start, it outlined the prevailing capacity status before this phase was rolled out and identified starting points for the phase as well as benchmarks for measuring project success in the latter part of the project.

The 2011 End Review for Phase I of the VNU project highlighted lack of a results-based approach in the first phase of the project and shortcomings in project reporting. Some project results were measurable and reported on, e.g.  # of training participants and # of Masters students and PhD candidates graduated with project support. However, the impacts of training and education on beneficiaries' performance (e.g. in teaching and researching) have not been documented systematically. Other changes, e.g. in institutional capacity, have not been measured or reported routinely.

The NTU project used a results-based approach, but the development goal for the project does not refer to any expected social, economic, institutional or environmental impacts and the goal was stated more at the output or outcome level – meeting human resource needs in the fisheries and aquaculture sector in Vietnam. The project did develop indicators and means of verification for each component covering specific and aggregated indicators. However, the performance indicators expressed direction, without clear targets and were not measured or used in monitoring and reporting.  Very few outcome indicators were included. The various reports provided necessary and useful information about project progress, but not on performance and little on capacity. And there appeared to be little recognition of the difference between output, outcome and impact indicators.

## Capacities to Manage CD processes

As noted previously, the four projects reviewed highlight the role of the Norwegian Embassy in Hanoi which usually entailed: receiving and commenting on project proposals, commissioning appraisals, making sure that formal legal requirements are met, signing agreements with local partners, and providing general oversight during implementation, including participation in the project annual meetings. The Embassy is also responsible for commissioning independent reviews and evaluations during and post implementation. In addition, the Embassy maintains informal dialogue with Norwegian and Vietnamese partners.  The Embassy furthermore engages government ministries but the two fisheries reports undertaken as part of this review indicated that lessons/ results from the projects have not played into any dialogue agenda.

Norad also reviews project proposals and offers feedback to the Embassy staff and is involved in project reviews and evaluations. Beyond that, the Embassy and Norad have generally taken a relatively hands-off approach and haven’t gotten involved significantly in change management or other CD processes.  An exception may be in the RIA-1 project when the Embassy played an important role during project planning. According to the RIA-1 evaluation report, it changed the approach from “involvement of the private sector and focused Component 1 (farm component) into a pure training, trial and demonstration farm operated only by RIA-1”.

Specifically with respect to CD, the review team was told that Norad has guidelines for CD but there was no evidence that they were being used in Vietnam, although some of the written feedback from Norad on project proposals did address CD issues, among others.  There are likely a number of reasons why the Embassy and Norad are not more deeply involved in projects in Vietnam, and CD issues specifically, but several reasons would appear to be the limited staff available in-country to address such matters, and the fact that Norad no longer has an Institutional Capacity Building Advisor position at HQ. As a result, Norad inputs appear to be: limited to specific requirements (e.g. engaging in appraisals and evaluations), technical in nature, and constrained by the fact that they have no field presence.

Through the ‘institutional collaboration’ arrangements, Norwegian partners (e.g. PSA, Klif and NCA in the case of the PVN project) provided technical expertise to their Vietnamese counterparts, supported study tours, and exposed Vietnamese participants to Norwegian practices, while participating in administration of the project.  Vietnamese stakeholders were largely positive about the institutional collaboration arrangements suggesting that the support provided by Norway was at a “very high level” and yielded “good results”.

In Phase I of the PVN project, the majority of training was in Vietnam, provided by Norwegians. In Phase II, more CD support (e.g. training) was provided by local resources. Exposure visits to Norway, as well as training opportunities there, reportedly helped to deepen professional skills for key Vietnamese staff.  One of the most important impacts, according to a number of respondents, was how engagement in the project (through the institutional collaboration) changed people’s thinking and behaviour regarding HSE issues, a change which was reflected in the significant reduction in accidents in the work environments touched by the project.

As noted in Norad’s Desk Appraisal of the VNU proposal, not much was known up front about the capacity of VNU to manage a project of this nature. Nor was much known about their capacity strengths and shortcomings in relation to geo-disasters. Nevertheless, VNU was known to be a credible and important tertiary institution in Vietnam’s education sector. The Phase I End Review gave positive marks to the Program Management Unit (PMU) housed in VNU for keeping track of overall progress and pilot study sub‐contracts. However, beyond basic management competency, nothing was said in progress reports or project reviews about VNU’s capacity to “manage CD processes”.  CD support offered by the Norwegian partners was highly valued but tended to be, as suggested earlier, of a technical nature rather than addressing organizational change issues, with the possible exception of support for the establishment of a Centre of Excellence (for Geohazard Mitigation) at VNU.

The approach to capacity development in the RIA-1 project has involved, in part, strengthening of national project ownership. RIA-1 staff has managed and executed the project. However, salaries have been a challenge as they are too low to provide a living wage. As a result, government staff often have to be involved in other ‘unofficial’ activities to survive. This problem has not been solved in this project.

The Norwegian partners in RIA-1 provided, first and foremost, short-term training and technical support for trials and demonstrations at RIA-1, but also supervision to doctoral students. The sandwich programmes for doctoral students were valued as CD processes for various reasons: the uninterrupted time for well supervised research with no teaching obligations; the international environment with plenty of chances for networking with peers and professors; access to article databases they could not access previously; and access to laboratories and equipment not available at RIA-1. The sandwich programmes also contributed ultimately to the quality of research undertaken as did the exposure to different academic environments which was seen as essential for gaining new perspectives, learning new practices, and acquisition of important insights into how to develop one’s own institution.

The Rectorate Board of NTU was responsible for project implementation on the NTU project and accountable to the Norwegian Embassy. The Norwegian partners appointed a lead agency (University of Tromsø) and nominated the Chief Technical Advisor (CTA). The CTA has been responsible for coordinating the Norwegian partners, providing technical assistance on project management including planning, budgeting, reporting, monitoring and evaluation. The Advisory Board, including the CTA, representatives of each Norwegian partner and component leaders advised the Rectorate Board. The Project Management Unit, including a coordinator, secretary and accountant, was responsible for assisting the Advisory Board and the Director in regular implementation of the project. Norad and the fisheries expert in Norad have provided technical advice and support mainly to the Embassy, but also directly to NTU and the Norwegian universities. Until the end of 2014, a Programme Officer was responsible at the Embassy for following up the support to NTU. Overall though, it did not seem that the implementing partners had a clear and strong view on organisational capacity issues and didn’t seem to rely on tools to support them in this respect.

In sum, the proceeding suggests that Norway’s capacity (Embassy and Norad) to manage CD processes is modest as personnel and structures are not built into the system, beyond approval processes and routine monitoring and oversight. The projects reviewed further suggest Norwegian partner institutions are highly competent in terms of their technical expertise, but may be less well equipped to facilitate organizational change processes, for example, or to support capacity assessments. Vietnamese partners are, by and large, capable in terms of administering project interventions but their strengths mainly lie in their respective areas of technical expertise rather than ‘softer’ areas such as change management or internal CD, although PVN, as one example, has been successful at internalizing staff development processes relating to HSE.

## Achievement of Planned Results and Improvements in Capacity

The results achieved through the three phases of the PVN project were significant and substantially in line with expected results, e.g. development and implementation of HSE regulations, strengthening of management systems.  Most importantly, indications suggest that a “culture of safety” has been institutionalized in PVN institutions engaged through the project.

Specific results achieved include the following:

- Environmental database established, e.g. sensitivity maps

- Development of environmental regulations

- Development of technical guidelines

- Oil spill contingency plans now required for each project

- Stronger committees dealing with HSE issues with higher level representations, e.g. CEO or VP of PVN now Chair annual HSE meetings

- All PVN corporations now have HSE policies and plans and are subject to annual HSE audits

One of the important results to note from the project is the reduction in accidents at PVN and associated work sites.  As a result of the project investments, and other factors, PVN is now seen as being on the same level as other Asian countries in terms of HSE issues.

Overall, the VNU project has been ‘successful’ in terms of delivering on planned activities. In fact, in Phase I some of the performance indicators ended up being higher than targeted.  However, the Phase I End Review raised some concerns about the training offered suggesting that “the depth of gained knowledge from attended training is relatively modest”, mainly due to the short duration of the sessions organized. Phase II in the project is still ongoing so there is no final tally of accumulated results. The most recent report available covers the period from June 2013 to May 2014 and despite earlier concerns with reporting, it still focused on Activities during the reporting period with no reference to cumulative results or progress towards Outcomes or the Overall Project Goal. As a result it is difficult to objectively assess improvements in capacity of the partner institutions involved.

According to reviews and evaluations, the RIA-1 project has contributed to building the human and organisational capacities of RIA-1, but it is difficult to assess its impact on the broader fishery sector and its contribution towards long-term development goals. The project has contributed substantially to building training and research capacity at RIA-1 in a range of disciplines related to aquaculture such as: genetics, selective breeding technologies, aquatic animal health, advanced diagnostic procedures, vaccine development, situation appraisals and on-farm trials, marine finfish aquaculture, hatchery production technology, cage farming technology, nursing and transportation of juveniles and feed formulation and assessment. In other words, the project has contributed to building internal technical and academic capacity related to aquaculture which are important preconditions for strengthening and sustaining coastal economies.

The RIA-1 project had no separate component for organisational capacity building, but the approach to implementation contributed to RIA-1’s institutional capacity. This was achieved by giving Vietnamese staff responsibility for implementation, while supporting the process with short-term inputs from Norwegian technical assistance. The CTA played a supporting role for senior management and the project also provided laboratory equipment and books for the library. The training has de facto contributed to building RIA-1’s institutional capacity. It is difficult to assess long-term economic impacts, but the project has directly and indirectly contributed to increased rural incomes through the expansion of aquaculture production and the creation of new jobs. Both freshwater and marine aquaculture production are contributing to livelihoods diversification in rural and coastal areas including expansion of tilapia production.

According to the final report and external reviews, the two phases of the NTU project made significant contributions to building the capacity of NTU in terms of teaching and research quality. The project has strengthened the Department of Economics in terms of the academic qualifications of staff, research experience and international profile. It has further strengthened the Department of Aquaculture in the two key areas of fish nutrition and fish disease. The project strengthened and helped to sustain the Institute of Biotechnology. It has also fortified the Department of Fishing Technology and Navigation. Teaching methods and teaching materials have been adapted to meet the needs of a credit based system, and a more active and student-focused mode of tuition. The library has been further developed with project support and English language competence of both teachers and students has been strengthened. The project has been less successful in terms of improving the effectiveness of University management and some of its support services.

In brief, the NTU project has been most successful in human capacity building (individual level) and has also contributed to strengthening organisational capacities, although the results are less clear at that level. There are also wider systemic effects (on the fisheries sector), but they have not been systematically assessed or documented. However, the majority of people trained have been retained in the country, in the fisheries sector and within the University itself. The University has also strengthened its international profile through the project, in part through project funded activities, but according to respondents more could have been done in this area. In addition, the project has contributed to improvements in infrastructure, e.g. classrooms equipped with modern teaching facilities, upgrading of labs and the library.

## Unintended Effects of Support to CD

A positive unexpected result arising from the PVN project was the quick rise within PVN of some of the Vietnamese staff trained through the project. This was clearly beneficial to the individual staff involved but it also helped to ensure that HSE expertise was retained within the system and that HSE issues remained in the forefront of thinking among PVN senior staff.

In the VNU project, the capacity of the lead institution (VNU) was strengthened but arguably without sufficient regard to the conditions required to sustain the changes facilitated, including how to grow and then sustain the proposed Centre of Excellence. Similarly, expectations were enhanced through the project that participating ‘at risk’ communities would be protected from potential disasters. The unintended ‘effect’ in the latter case may be difficulties in sustaining the advances made.

In the case of NTU, the Government is under pressure to reduce recurrent expenditures of universities. As a result NTU, like most of the universities in Vietnam, has to generate more income by taking on an increasing number of undergraduate students. In the short term, increasing quantity, versus quality, might be effective in terms of income generation, but the pressure might lead to the recruitment of unqualified staff leading to poor quality training service; or on-going lecturers being pressured by training hours rather than spending appropriate time on research. Reduction in the quality of service may threaten NTU´s position in the competitive tertiary education market. There is a risk therefore that the quality gains achieved under the project will prove to be of a temporary nature, unless the incentive systems can be revised.

## Efficient Use of Money in Contributing to CD outcomes

The 2012 End Review of the PVN project concluded that the Project has “by and large been efficient”. Vietnamese stakeholders were also aware that improvements in HSE standards was “good for business” and reduced risks of lost time at work due to injuries or accidents while also reducing the risk of costly environmental accidents at sea.  However concerns were raised with respect to the high level of travel costs in the project, delays in making payments for invoices from the Norwegian parties, as well as delays between the different phases. A broader concern though was the cost effectiveness of the ‘institutional collaboration’ model itself, including the high cost of overseas Advisors, although most interviewees didn’t have a strong view as to whether that was the most cost efficient approach to CD or not as alternatives, it seems, were rarely discussed.

Similar concerns were expressed under the VNU project with respect to the cost of personnel from Norway. As the Phase I End Review noted: “The use of personnel from the Norwegian Geological Institute (NGI) and other Norwegian consultants is expensive, but decisions to use it are based on thematic requirements rather than on cost‐efficiency criteria.” The review went on to say that Vietnamese stakeholders saw the value‐for‐money of Norwegian advisors as “high”, although that didn’t appear to be based on any comparison of alternative approaches.  However, the Project Management Unit did assess intermediate results of sub-contractors before committing to funding the remaining portion of contracts which was seen as one way of ensuring cost efficiency. The VNU team also sought out local contractors where possible as a way of managing overall costs.

Early evaluations of the RIA-1 project have been positive on the issue of overall efficiency. As with the other projects reviewed though, the cost effectiveness of the institutional collaboration with Norwegian universities is seen as costly, although it was seen by RIA-1 as an accepted part of the project with Norway. Nevertheless, the cost of technical assistance has decreased in the project from 35% of the overall budget in Phase I to 16% in Phase III.

The structure of the NTU project – with a large number of components, national and Norwegian component leaders and advisors and multiple stakeholders created a complex planning and management structure. Following from that, various reviews noted that transaction costs were at times high.  Substantial sums were spent, for example, on professional training, a significant part involving experts from Norway, and to some extent from other countries. The latter strengthened national and international connections and upgraded skills, and the main evaluation indicated that project funds were, in general, well spent.

However, Norwegian professors and advisors did represent a major project expense. PhD sandwich training, for example, is costly. Since NTU is the project holder and receives all funds, Norwegian universities claim all expenses from NTU. Hence, the actual cost of the collaboration with Norway became visible and amounted to approximately 75 to 80% of the total budget (all sandwich expenses and Norwegian TA). This was considered very high by NTU management. But would alternative models have led to more and better results for the same amount of money? The Mid-term Review in 2010 noted that in some cases – for example in the area of biopolymer research where Norway clearly excels – there were hardly any alternatives.

## Characteristics of Relevant and Effective CD Interventions

The reviews of the individual interventions in Vietnam highlighted a number of features that either contributed to their effectiveness or took away from it.  In the PVN project, factors that contributed to its overall effectiveness included its relevance to Vietnamese stakeholders (e.g. the practical focus on needed HSE regulations and systems), the commitment of top Vietnamese management (including their effective participation in the Project Steering Committee), the ability to draw on Norway’s world class expertise in oil and gas (and HSE issues specifically), and the quality of relationships amongst various stakeholders, including the project leaders. Factors which were mentioned as potentially undermining effectiveness included the poorly constructed project matrix which led to weak application of results-based management, and aspects of the institutional collaboration model which were, as noted, recognized as being expensive and could potentially have been dealt with in a more cost effective manner.

Factors influencing effectiveness in the VNU project were similar to those in the PVN project, e.g. high level of ownership, relevance of the interventions to stakeholder needs. However, considerations which may have limited effectiveness to varying degrees included, delays in project implementation, the lack of ‘depth’ of some of the knowledge gained through some of the training and problems in discerning “measurable impacts”, partly due to a lack of clarity between expected Outputs and Outcomes.

As with the other projects, local ownership (supported by participatory processes) and relevance were key contributing factors to overall effectiveness in the RIA-1 project. The project was seen as having contributed substantially to building internal technical and academic capacity related to aquaculture which are important preconditions for strengthening and sustaining coastal economies, the higher level result. In the process, the number of MSc holders and PhD students among RIA-1 scientific staff has increased significantly, RIA-1 staff is increasingly used as international consultants in regional development projects and committees or as key persons in research and management.  Another contributing factor was the “good fit” in the project between what Vietnam required and what Norwegian partner institutions could offer.

Contributory factors to effectiveness in the NTU project included the participatory planning process for Phase II which was preceded by a comparative institutional assessment to map the University within the broader national education system. However, while the participatory approach helped to accelerate the planning process, the institutional component didn’t seem to be informed and guided by a proper assessment of NTU´s internal capacity. And a report on the NTU initiative noted that while Norway is technically strong in relation to fish pathology and nutrition, and the experts from Norway were technically excellent, in some cases their expertise did not relate particularly well to the immediate or medium term needs of the fisheries sector in Vietnam.

## Circumstances Under Which Donor Support to CD Appropriate and Effective

Circumstances:

The Norwegian-sponsored projects reviewed in Vietnam suggest the following circumstances under which donor support to CD may be appropriate and effective:

- High levels of ownership - The initiatives covered in this review displayed, as previously noted, a relatively high level of ownership, particularly among stakeholders whose engagement was key to success. This sense of ownership was usually associated with demonstrated commitment of political and/or bureaucratic leadership and a common vision in terms of key objectives being pursued.

- Relevance, Readiness, and Receptivity – The projects reviewed highlighted how ”success” was more likely when externally-sponsored CD interventions were linked to processes and priorities seen as highly relevant to local stakeholders. They also revealed a high level of readiness on the part of local partners, many of whom advanced the original project idea. Receptivity to change was also evident in most of the cases as key stakeholders embraced change which built on government and/or institutional priorities, and worked hard to advance the shared vision.

- Enabling Environment -  The ”success” of some of the projects reviewed can be attributed, to a considerable degree, to factors in the enabling environment, many of which have already been referred to in the sections directly above, or elsewhere in this paper, e.g. committed leadership, appropriate policies, organizational readiness. In the fisheries sector and with the PVN project, for example, the projects were undertaken at a time when both areas were high national priorities which inevitably helped to enable and drive the reforms being advanced.

- Absorptive capacity – This was demonstrated in the projects reviewed, although in some circumstances some of the project inputs appeared to be somewhat supply driven so were less readily absorbed or effectively utilized. In at least several of the projects, it was evident that the absorptive capacity of local partners and their ability to take the lead on the initiatives in question increased over time as enhanced capacity led to more confidence, greater clarity regarding priorities, stronger managerial/governance oversight etc.

- Effective Use of Technical Advisors – While criticisms of aspects of the institutional collaboration ‘model’ have already been noted, effective use of technical advisors was generally a feature of the various projects reviewed as they contributed to increased skills and knowledge of project participants as well as enhanced systems, policies and regulations. Some advisors “advised,” while others trained, mentored, or facilitated; some served as change agents; while others focused on systems development or regulatory reform. In many cases, it was a combination of roles and approaches.

- Long-term engagement- All of the projects reviewed were of significant duration which helped to build up trust among partners, and allow for reforms to unfold at a pace which could be managed effectively by local partners.

Aspects:

The projects reviewed suggest that focusing on different aspects of capacity may be appropriate, depending on circumstances and need, including:

- Skills development (e.g. technical, managerial, awareness raising)

- Leadership development

- Organizational reform (e.g. procedures, systems, regulations)

- Support for strategy development

- Strengthening of networks, or

- Community engagement

In some of the cases reviewed, e.g. PVN, the aspects requiring attention were fairly clear from the outset.  PVN was already an established and growing public corporation, but needed to enhance its capacity (knowledge, skills, systems and regulations) relating to HSE.  Those needs were identified readily by key stakeholders and were supported in a step-by-step manner over the course of the project.  There was less need to focus on broader institutional issues in PVN as HSE standards were identified as the clear priority in the project, PVN was otherwise in ‘good shape’ and growing and support for HSE issues was assured from within the corporation.

In the case of the VNU project, the primary focus, especially early on, was on enhancing individual knowledge and skills. However, over time it was recognized that more attention need be given to institutional issues.

These experiences, and others, suggest that the specific level or aspect of capacity to be focused on really depends on the need, the state of the partner organization, its potential to benefit from the support provided, among other factors.  Usually these factors would be determined following some kind of an assessment process.  However, in most of the cases reviewed, formal assessment processes, including capacity assessments, were not undertaken, and assumptions were made about the aspect of capacity needing support.  More often than not, although not exclusively, this led to a focus on enhancing knowledge and skills with an implicit assumption that improvements in organizational or sectoral practices or behavior would follow.  It was the view of the review team though that the cases reviewed could have benefited from a more rigorous assessment of what aspects of capacity needing support in order to sustainability address the challenge facing the project.

Specific Inputs:

The cases reviewed in Vietnam relied on a number of inputs to support CD processes. These included:

- Long-term technical assistance

- Short-term technical assistance

- Exposure visits/ study tours

- Scholarships

- Infrastructural support

Most of these were under the umbrella of institutional collaboration arrangements between Norwegian and Vietnamese institutions. And most interventions, especially in the fisheries area, were at the individual level, with less at the organizational level and only a few at the systems level, such as the fisheries law project.

Regarding the “appropriateness” and “effectiveness” of specific CD inputs, several general comments can be made based on the review of the four Vietnamese projects: stakeholders prefer inputs that are ‘practical’ and directly contribute to enhanced performance; they also respond positively to inputs that benefit them as individuals.  However, it’s difficult to assess relative effectiveness since the various projects usually didn’t report on results above the Activity/Output level.  Progress reports often included information on #s of courses/workshops attended, or the #s of faculty members who gained a higher degree, with less, if anything being reported on the effectiveness of the training (or other inputs) in changing institutional practices.

## Situations in Which Agencies Should Refrain from Being Involved in CD

The four projects reviewed as part of the broader Norwegian evaluation exercise did not highlight any particular situations where Norway, or its partners, should “refrain from being involved in CD”.  This is due mainly to the circumstances or ‘success factors’ identified in the previous section. They highlighted that the CD support provided in Vietnam was, among other things, relevant, supported by highly committed stakeholders, and generally implemented in an ‘enabling environment’ which included supportive policies and organizational readiness. The only rationale for not being involved in CD efforts in Vietnam would be, as with anywhere, if insufficient financial controls were in place in the partner institution, if the organization didn’t have the absorptive capacity to benefit from CD inputs, or where interests were clearly being driven by political or narrow organizational/personal interests. None of these circumstances held to any serious degree in the cases reviewed.  A broader overriding issue though is how to deal with Vietnam as a middle income country which is increasingly capable of addressing its own needs independently. That, of course, doesn’t mean that there aren’t areas where ongoing engagement, as part of a broader relationship with Norway, is not merited.  It does give reason though to pause and think more strategically about types of support to be offered and to be more creative in terms of new strategies for CD.

In terms of “modalities and approaches (that) should no longer apply”, it would be wrong-headed to be categorical about this since the modality or approach to CD taken should be determined by the circumstances and the specific need. For example, while overseas training may be appropriate in some circumstances, it may be considered costly and relatively ineffective in other situations in terms of potential impact on organizational performance, for example. Two cautions arise though from the Vietnam experience with respect to modalities: 1) modalities or approaches embraced should be based on systematic consideration of alternatives taking into account, among other things, potential for contributing to the project’s expected results, including positive changes in organizational or sector performance. It wasn’t apparent that this was done in any of the Vietnamese projects with the result that training was often chosen as the default modality, often without full consideration of how it would contribute to higher level results, or how it might be combined with other inputs or approaches to achieve those results; 2) assessment of cost effectiveness should be part of the systematic consideration of CD options. Once again, this wasn’t done in the case of Vietnam, as far as the review team was able to determine, seemingly because training or provision of technical advisors was seen as a ‘given’ as part of the institutional collaboration arrangement with the Norwegian partner institution.

Finally with respect to modalities, this report has already highlighted concerns with the institutional collaboration ‘model’ as a mechanism for supporting CD.  The primary concern noted has been its cost effectiveness. A second concern though that merits deeper consideration is the potential for the mechanism to lead to supply-led approaches that may not be responsive to local need and therefore may not maximize Norway’s contribution to the desired development result. This is likely a manageable risk but one that nevertheless, merits closer consideration.

## Theory of Change

It’s not 100% clear to the review team that “a generic TOC for support to CD (can) be formulated that would enhance the effectiveness of support to CD”. The main reason is that each project or intervention is unique, as is the situation or context in which it is implemented. Nevertheless, the projects reviewed in this evaluation exercise suggest it is possible to think of a ‘generic TOC template’ or approach which could be used as a basis for most projects, if modified to meet the particularities of the given intervention and associated contextual considerations.

The section below seeks to outline what a ‘generic’ (and rather general) TOC might look like. First of all though, what do we mean by theory of change? Theory of change is about what results Norway and its partner are seeking to achieve, why those results are seen as important, and the specific role of the project or program in achieving those results. The theory of change for the planned intervention should give rise to the goal and objectives of the program in relation to intermediate outcomes to be achieved.

The theory of change is often presented as a series of ‘if-then’ statements. It starts with the point at which the donor commences engagement with strategically selected local partner organizations and leads through to the intended outcomes and overall goal of the project (the example below includes Assumption and However statements following the first If /then statement for illustrative purposes).

- If Norway assists Vietnamese partner organisations to identify and make better use of existing and new organisational capacities and individual competencies then there is increased likelihood that partner organisations will more effectively use that capacity and those competencies to change their practices and improve the quality of services they deliver, e.g. teaching, research, establishment and monitoring of regulations, support for fishermen.

- The assumption is that, for such organisations current practices have been limited, at least to a certain degree, by lack of competency and organisational capacity, e.g. systems, policies, procedures, that relate to the priority organisational functions identified.

- However, many other conditions would need to be in place for competencies and organisational capacities that have been developed with Norway’s support to have the potential to make a difference. For example, the organisation would also need to have appropriate policies and well-functioning relationships with other stakeholder organizations, markets etc. Part of the assessment of what competencies and capacities could be usefully developed and how widely they should be developed, when to do so and whether doing so would be a good investment of scarce resources must give consideration to these other factors.

- If these practices improve programs of local partners, related GOV reform agendas and priorities will be better positioned with respect to implementation and realization of outcomes, e.g. by identifying, removing or reducing obstacles, including ineffective use of existing strengths and opportunities that have stood in the way of optimal delivery of relevant programs.

- If organisations see the benefits of capacity development interventions then they will have a greater commitment to internal organisational development and other aspects of CD on an ongoing basis.

- If the commitment to CD within partner organisations improves then they will build on that development and institutionalise further changes resulting in virtuous cycles of positive change. They will also become increasingly independent of external support for CD assistance.

- If organisations and participants are encouraged by Norway to do so, then they will share what they have learned within and beyond their organisations and lessons will be made available to a wide range of stakeholders including GoV policy makers, GoN and other relevant stakeholders.

- If there are improvements in the commitment of organisations to new practices, and if multiplier effects occur through building relationships amongst partners, sharing lessons learned and through research and knowledge synthesis then there will be even greater and more sustainable benefits with respect to Norway’s programs, and related GOV reform agendas and priorities.

The Theory of Change may include further If/then statements or assumptions which touch on some of the success factors addressed in the previous section, e.g.  the importance of ownership, relevance, readiness, receptivity, an enabling environment, absorptive capacity, effective use of technical advisors and long-term engagement. The overall point is to lay out the conditions and steps required to affect the desired change, and the associated assumptions.

The Theory of change would be accompanied by an intervention theory which describes what the program will do and how it will achieve or contribute to the planned results outlined in the theory of change. The intervention theory would include various considerations, e.g. how to prioritise, target and engage organisations, how to identify and prioritise capacities to be developed, most appropriate CD modalities to address the need identified, and how to manage, monitor and evaluate the program.

http://www.miljodirektoratet.no/old/klif/publikasjoner/2870/ta2870.pdf

See ‘Aid Effectiveness Report to Consultative Group’ for 2010.

Data in this section is from the Aid Effectiveness Portal: http://www.aideffectiveness.org/index.html as well as the World Bank web site.

The review team was of the overall view that while Vietnamese partners had many internationally supported projects, there were few links among them, and there was weak internal coordination. Furthermore, the projects would not have likely come to fruition without Norway’s initiative.

The review team was told that Norad no longer has the position of ‘Institutional Capacity Building Advisor’ which it had in headquarters up until several years ago. It was not clear to the team what the absence of that position has meant in terms of advisory support or guidance on capacity development in overseas projects.

Data source from National Account of General Statistics Office’s Website www.gso.gov.vn/

Data source from Petrovietnam’s Website www.pvn.vn/

Data range from General Statistics Office’s Website

Final Report, End-Review of the Project entitled “Development of Management Systems on Safety and Working Environment and Environment Pollution in the Vietnamese Petroleum Industry”, Arntzen De Besche Advokatfirma As, Oslo, 11 June 2012, p. 21.

Nha Trang was an exception as this was an issue there and was discussed.

Final Report, End-Review of the Project entitled “Development of Management Systems on Safety and Working Environment and Environment Pollution in the Vietnamese Petroleum Industry”, Arntzen De Besche Advokatfirma As, Oslo, 11 June 2012, p. 19.

The description of Theory of Change in this section draws on the work of Sue Funnell and Patricia Rodgers, “Purposeful Program Theory: Effective Use of Theories of Change and Logic Models’, 2011