Environmentally Sound Management of Hazardous and Industrial Wastes in Cement Kilns in China

Project CHN-2150

A desk review in the evaluation of Norwegian support to capacity development

Final

Sept 2015

Greg Gleed

Stephen Peterson

Table of Contents

1.	Introduction	1

2.	Limitations	1

3.	Overview of the Project	1

3.1.	General background	1

3.2.	Objectives and planned outcomes	1

3.3.	Characteristics of institutions addressed	2

3.4.	Characteristics of the intervention:	2

3.5.	Implementation arrangements, including budgets	3

4.	Relevance	4

5.	Design and Implementation	4

5.1.	Responsiveness to context specific factors	4

5.2.	Factors external to the targeted partner institution	5

5.3.	Experience and lessons learned elsewhere	5

5.4.	Theories of change	5

5.5.	Capacity needs assessment	6

5.6.	Donor fit (Norwegian comparative strengths and historical relationships)	6

5.7.	Involvement of partner institutions	6

5.8.	Continuous learning and adaptation	7

5.9.	Results (Outcomes and sustainability of Outcomes)	7

5.10.	Likely sustainability	9

5.11.	Factors influencing effective CD	9

6.	Conclusions	10

7.	Annexes	11

7.1.	References	11

# Introduction

This desk review of Norwegian CD support for Environmentally Sound Management of Hazardous and Industrial Wastes in Cement Kilns in China was conducted by a two-person team comprising two international consultants. A review of available documentation and an interview with staff from the Norwegian embassy in China and Foundation for Scientific & Industrial Research (SINTEF) were at the core of the desk review approach. The desk review study is a secondary data source for the wider evaluation of Norway’s support to capacity development.

# Limitations

This desk study is based on a review of selected project documents associated with this intervention. As a desk review, this paper does not draw on data from site visits or direct observation of project activities. As a result, it tells only part of the story of this project, without the benefit of more detailed review of project activities, and interviews with a broader range of stakeholders. Nevertheless, consistent with the broader evaluation it is part of, it seeks to highlight key lessons learned about Norway’s support to capacity development in the industrial sector in China.

# Overview of the Project

## General background

The co-processing of hazardous and industrial waste in cement kilns offers a solution for treatment of most types of hazardous wastes that are damaging to the environment. This intervention aims to strengthen China’s capacity for complying with the Stockholm and the Basel conventions by establishing the foundations for large scale treatment and recovery of hazardous and industrial waste in the Chinese cement industry. In so doing, the initiative will provide a potentially cost efficient ‘fuel’ for the cement industry with potential for significant economic and environmental benefits in China once it is brought to scale.

Prior to the intervention China did not have the policies, regulations and expertise to adequately address the issue of hazardous and industrial waste. The project was intended to address those shortcomings by building capacity through training, developing industry standards and guidelines, practical demonstrations and creating enabling conditions for the co-processing of waste. This intervention can be seen as highly complex as it is trying to influence the capacity of the cement industry as a whole to co-process industrial waste through various modalities (e.g. training, support for guideline development, study tours)

## Objectives and planned outcomes

The overall goal for this project evolved from Phase I to Phase II from “strengthening China’s compliance with the Stockholm Convention and the Basel Convention” to (Phase II) ensuring that the “guidelines and standards developed in the first phase are properly tested, disseminated and implemented on a large scale basis.”

The purpose also evolved from “establishing a basis for large scale implementation of safe and environmentally sound treatment and recovery of hazardous and industrial waste in the Chinese cement industry” to “continuing to build capacity and to establish awareness about the possibilities and limitations of co-processing of waste materials in cement kilns through extensive information dissemination, to amend the technical information basis to cover pre-processing and pollution prevention, and to implement the guidelines and standards developed in Phase I into daily practice.”

## Characteristics of institutions addressed

The Ministry of Commerce (MOFCOM) of the Government of the People's Republic of China, has the overarching responsibility for coordination of this intervention and is signatory to the agreement “Environmentally Sound Management of Hazardous and Industrial Wastes in Cement Kilns in China” with the Norwegian Ministry of Foreign Affairs (MFA).  The Ministry of Commerce is the executive agency of the State Council of China and has responsibility for formulating policy in areas of, but not limited to, foreign trade, market competition, and has responsibility for negotiating bilateral and multilateral trade agreements.

The Chinese Ministry of Environmental Protection (MEP), has responsibility for the supervision of the intervention. More broadly, the Ministry has responsibility for protecting China's air, water, and land from pollution and contamination. It is required by law to implement environmental policies and enforce environmental laws and regulations.

The Foreign Economic Cooperation Office of China (FECO), which is an institution affiliated to MEP, has the direct responsibility for implementation of the intervention in cooperation with Norway’s Foundation for Scientific and Industrial Research (SINTEF). The collaboration between SINTEF and FECO is enshrined in an agreement between the two institutions in both phases. FECO is mandated to coordinate and manage the projects with international organizations and with the implementation of multilateral and bilateral agreements. SINTEF is the largest independent research organisation in Scandinavia. It is a multidisciplinary research institute with expertise in technology, medicine and the social sciences. It is an independent, not-for-profit research institute.

SINTEF has directly carried out a number of activities including providing technical inputs, designing intervention training, lecturing, and conducting research. FECO on the other hand has subcontracted various organisations to carry out specific tasks. The most significant subcontractor is the Chinese Research Academy of Environmental Science (CRAES). It is a national non-profit institute for environmental protection that undertakes scientific research on environmental issues. It is also dedicated to providing strategic advice and recommendations based on scientific research.

## Characteristics of the intervention:

The main modalities for this intervention involved: research, training, exposure to co-processing techniques through practical demonstrations and study tours, as well as improving enabling conditions for adaptation and utilisation of new methods through new guidelines, policies and regulations. The various modalities were intended to lead to enhanced awareness and capacity for eventual implementation of a national plan and strategy for larger scale co-processing of industrial and hazardous waste.

Chinese stakeholders have played a significant role in the implementation of project activities through the subcontracting of national research institutions, in particular CRAES, and the involvement of cement producers. Norway is primarily involved through SINTEF which plays a technical advisory role.

The planned outputs for Phase I & II are detailed in Table 1 below.

Table 1 – Planned Outputs

Phase I

- A baseline study with a report on current HWM system and recommendations. - A baseline study with a report on description of the cement industry and evaluation on co-processing. - Pilot tests have been conducted in up to five cities or provinces and evaluated. - 2 workshops and seminars have been conducted with more than 100 participants. - Training courses have been conducted in up to 5 cities/provinces - 20 participants from relevant organisations participate in the study tour. - Final guideline adopted

Phase II (Revised outputs, 2012)

- Optimise Standards and Guidelines developed in phase I - Develop Guidelines for pre-processing and pre-treatment - Demonstrate co-processing of problematic high volume wastes such as fly-ash from waste combustion, sewage sludge, municipal solid waste (refuse derived fuel - RDF), POPs and POPs contaminated soil, preferably in Western and Southern regions of China, and the results are evaluated and reported - Establish a quantitative estimate of the CO2-reduction potential which can be accomplished by the cement industry through co-processing and proposed measures for further emission reduction - Establish a quantitative estimate of the release contribution of mercury from co-processing of wastes in the cement industry and proposed measures for further emission reduction - Establish a quantitative estimate of the release contribution of dioxins and furans from co-processing of wastes in the cement industry and proposed measures for further emission reduction - Provide input for a national plan and a strategy for the implementation of large scale co-processing in China - Conduct two study tours to other countries for a total of 20 people - Conduct a series of National conferences on the ‘possibilities and limitations of co-processing of waste materials in cement kilns’ and disseminate learnings - Hold one International scientific high level conference focusing on sharing of experiences and building capacity - Produce six papers on co-processing in National Chinese technical journals and disseminate findings to the entire Chinese cement industry - Produce three articles describing the findings of the Sino-Norwegian project in international peer-reviewed Scientific Journals - Develop a practical video explaining co-processing in Chinese and disseminate to the entire Chinese cement industry and relevant authorities

## Implementation arrangements, including budgets

MOFCOM had overall responsibility for the Project with MEP supervising the implementation of the Project. On the Norwegian side, the Norwegian Embassy in Beijing represented the Ministry of Foreign Affairs. MEP and FECO, as well as SINTEF served as the main project implementing partners. SINTEF was engaged through an Institutional cooperation contract funded by GON and SINTEF and MEP/FECO were authorized to enter into subcontracts as necessary to support implementation of the Project.

The overall budget for Norway in Phase I was NOK 14,514,700 through a grant from MFA. In Phase II, the NOK 18,900,000 MFA grant was complemented by a reported NOK 9,600,000 contribution from the Chinese.

| Cost Sharing | Phase I | Phase II |
| --- | --- | --- |
| Government of Norway (MFA) | 14,514,700 | 18,900,000 |
| SINTEF (Norway) | 2,800,000 |  |
| MOFCOM/SEPA | 2,700,000 |  |
| MEP/FECO |  | 9,600,000 |
| TOTALS | 20,014,700 | 28,500,000 |

# Relevance

China faces serious challenges relating to the recovery and treatment of hazardous and industrial waste, especially given its rapid urbanisation and industrialisation. The Chinese Government is placing increasing emphasis on environmental issues and is keenly aware of the consequences of pollution on local populations. Project stakeholders are convinced that the intervention can make a significant contribution to China’s waste problem. And NORAD’s Phase II Decision Document outlines the perceived relevance of this intervention, highlighting the fact that China is the biggest cement producer in the world. The growing prominence given to environmental issues is also reflected in China’s commitment to the Stockholm and Basel Conventions. Environmental issues are also clearly a priority of the Norwegian Government. Another factor that makes this intervention particularly relevant is that hazardous and industrial waste offers a potentially ‘cost efficient’ fuel for the production of cement. Given that, if the intervention contributes meaningfully to large scale implementation of co-processing, there could be significant future economic benefits for China arising from enhanced cost savings in the production of cement.

# Design and Implementation

## Responsiveness to context specific factors

As suggested above the project is clearly responsive to growing environmental challenges in China, while also being responsive to Chinese treaty obligations (compliance with Stockholm Convention and the Basel Convention) and policies. The intervention is distinguished by its ability to reduce the environmental impact of the cement industry while also being responsive to the cement industries need to remain competitive through potential reduced energy consumption and lowering of production costs. It should be noted though that due to the lack of a developed ‘waste market’ all participating companies are participating on their own initiative. In the interview with a representative from SINTEF, it was ascertained that this was because the companies clearly see the long-term benefits of such intervention.

The engagement of a diverse range of stakeholders to undertake specific activities associated with this project is indicative of the complexity of this enterprise, but it also reflects the existence of incentives in favour of engagement of stakeholders with mutually reinforcing interests. For example, the cement kiln operators who adopted the technology are hoping to reap significant economic benefits in the long-term, while national authorities involved will be able to build on the project to make progress towards their international obligations. However, there was not a clear rationale outlined in the project documents reviewed to explain how capacity issues should be addressed (or not) in the project and how proposed activities were intended to respond to specific factors in the project context, e.g. the incentives of key stakeholders, the potential to strengthen relationships among institutional actors.

## Factors external to the targeted partner institution

China’s international treaty obligations (Stockholm and Basel) represent the most significant ‘international’ factor to influence and shape this intervention, including the necessity to enhance capacity to regulate and otherwise address waste management issues. Other factors (more local or national) taken into account in the design and implementation were the growing environmental challenges China faces and the growing recognition of the need to address them at multiple levels (e.g. operational, policy, regulatory). These ‘internal’ contextual factors are implicitly integrated into the intervention through the various activities aimed at bolstering operational capacity, shaping policy and enhancing China’s regulatory framework. There are, however, two key external factors that are not implicitly or explicitly factored into the design or implementation of this intervention. The first is the availability of a ‘sufficient waste market’ with adequate quality materials to sustain the upscaling of co-processing, while the second is the absence of financial incentives for cement kilns to commence co-processing, making the intervention totally reliant on the interest and willingness of individual cement producers to be involved.

Another notable factor highlighted in Phase I progress documents was the delay in issuing permits for co-processing that resulted in a limited number of test sites. This, in turn, limited the ability to promote and share learning on co-processing in a practical manner, and to take it rapidly to scale. This issue was later addressed however, the lack of specific consideration of such factors in the broader waste management ‘system’, and the absence of relevant activities to mitigate or actively address them early on, does highlight a shortcoming in terms of the initial assessment of critical contextual factors that could influence or limit realization of planned outcomes, including capacity results.

## Experience and lessons learned elsewhere

The documentation suggests the intervention managed to integrate learning from external/international sources combined with the learning and expertise from Chinese counterparts that formed the core of activities of the intervention. Learning and practical demonstrations have been central to the intervention. In both phases various activities have been supported to expose stakeholders to relevant experiences in China, and internationally. Specific activities undertaken to draw on experiences and lessons learnt from elsewhere included: the development of documentation on international best practices, and learning tours to Norway and Belgium where officials visited the European Environment Agency, National Waste Management Departments, and co-processing enterprises in Obourg and Lixhe in Belgium. Phase II also included plans to undertake study tours, and facilitate participation in international conferences. Another notable demonstration of the desire to learn from and share lessons from elsewhere was the plan to develop a video that would highlight international best practice on co-processing.

## Theories of change

The inception report and other project documents suggest an ‘implicit’ theory of change (ToC) that follows a linear path commencing with the initial studies and fact finding, followed by a series of activities to build awareness, promote the adoption of guidelines and bring co-processing to scale in the Chinese cement industry. The ‘implicit’ ToC is based heavily on a model of learning, demonstrating, and providing an enabling environment for co-processing. However, as suggested above, this implicit ToC was also based on certain assumptions and lacked due consideration of the full range of factors that might specifically affect the project’s objectives relating to scaling up.

The documentation reviewed also highlighted the absence of a clear and coherent ‘programme logic’ that could serve as an informal ToC and provide a basis for monitoring progress and attributing causality, in particular, for Phase I of the intervention.  The Midterm Review for Phase I, for example, pointed out that the project documents, agreements and annual reports all have different sets of outputs. Further the Phase I Logical Framework Analysis (LFA), which was as a result of a workshop, is described as incoherent and with inconsistent linkages between Outputs, Activities and Indicators. The Midterm questions the prepatory work and the LFA workshop in terms of the formulation of and design of the intervention. What can be ascertained though is that the goal and purpose of the intervention remained consistent throughout.

The experience of Phase II also offers insights into the potential difficulty faced in the design and formulation of an intervention logic and/or an ‘implicit’ theory of change, with a two year delay in the developing of an inception report. The Phase II inception report was much more clear and coherent and the implementation plan provided much improved programme logic. However, one aspect that could have improved the intervention logic/ToC would have been a more intensive reflection on the lessons learnt from Phase I.

## Capacity needs assessment

There is no indication that any formal capacity assessments were carried out, either prior to Phase I or before the start-up of Phase II. The process of identification and articulation of priorities appears to have been through meetings, workshops, and discussions, with primary responsibility for identification of needs being with the Chinese partners. However, the Chinese institutions engaged were not seen as necessarily having the capacity or experience to undertake formal assessments leading to a clear and coherent intervention logic.  Two baseline study reports on the state of hazardous and industrial waste management in China and on the feasibility of cement kiln co-processing were produced during the initial phase of the intervention. The Mid-term review noted that the reports were very comprehensive in detailing information on the current situation, but somewhat weaker in terms of summarizing and evaluating this information. The lack of formal assessments in this project and limited apparent capacity or incentives by the local partner to analyse and evaluate baseline information could be indicative of a need for more support in these areas to help ensure  identification of strategically important  capacity needs to be addressed and development of a coherent programme logic.

## Donor fit (Norwegian comparative strengths and historical relationships)

‘Institutional cooperation’ has been a central feature of Norway’s capacity development support in China in recent years. The shift from ‘traditional’ approaches to aid also reflects changes in China as a Middle Income aid recipient with interests in strategic and increasingly specialized partnerships. The documentation reviewed lends weight to the idea of a strong donor fit (Norwegian) in the Chinese context with the Design Document for Phase II highlighting that the second phase is in line with “Norway’s development cooperation strategy in China and globally, which regards environmentally friendly management of Hazardous wastes as a top priority.” The relationships arising from this initiative are also predicated on substantive Norwegian strengths that are valued by the Chinese partners.  And while MFA has funded this initiative through its embassy in Beijing, it would seem that NORAD has played a relatively modest role on the Norwegian side.

## Involvement of partner institutions

In 2003, SEPA (now China’s Ministry of Environment Protection), communicated an interest in technical collaboration to the Royal Norwegian Embassy in Beijing. This subsequently led to a proposal for technical collaboration being submitted to the Embassy in 2005. The proposal was developed taking into account Norway’s long standing experience in burning hazardous waste in cement kilns. After an appraisal of the proposal, and an LFA workshop, the final project document was presented in August 2006 with the initial agreement being signed between MOFCOM and the Norway later in the year. The contract allowed for subcontracts with the MEP having overall responsibility for the intervention with FECO and SINTEF having the responsibility to implement and administer the intervention. SINTEF and Chinese partner institutions subcontracted by FECO had the overall responsibility for the delivery of the intervention. The most significant partner institution has been the Chinese Research Academy of Environmental Sciences (CRAES) that collaborated on the finalisation of co-processing guidelines and standards, compilation of pre-treatment guidelines, conducting technical studies and evaluating and reporting on demonstration activities. Other notable subcontracted institutions included the Chinese Building Material Academy (CBMA) which conducted a study on a national plan and strategy.  Both phases of the intervention also involved a number of cement kilns. The progress reports for Phase II indicate a thorough process of scoping and selection of cement kilns for demonstration. The second phase also sought to ensure more extensive involvement of Local Environmental Protection Bureaus (EPBs).

## Continuous learning and adaptation

This intervention is based in large measure on technical collaboration, e.g. building capacity at the Ministry and provincial level, with a premium on learning. It has also been distinguished by its apparent ability to deliver high volumes of quality technical outputs. However, the design and planning documents focus heavily on activities and outputs giving very little scope for appraisal of information, evidence in relation to the context, and learning about co-processing which can be shared more broadly. Another notable feature of Phase II is the lack of reflection on what worked and what worked less well in Phase I of the intervention and how this learning can be integrated into the design of Phase II.  And there is no or little evidence of systematic learning on capacity development approaches during implementation – e.g. what approaches work, why, what is likely to be sustained and how.

## Results (Outcomes and sustainability of Outcomes)

As previously discussed, this intervention seems to be distinguished by a high level of outputs. However, it also proceeded without any formal capacity assessments or overarching CD strategy and with what the mid-term review described as an “inconsistent” design. The main outputs of Phase I included baseline studies, reports on international best practice in co-processing, the development of standards and guidelines, training/capacity building, and test burns with hazardous materials in several cement plants. The most detailed and accurate description of outputs and outcomes can be found in the proposal for Phase II. The document attributes the following outcomes to Phase I of the intervention:

- Raising awareness and disseminated information on co-processing among national and local government and in the cement industry

- Building the capacity and understanding within key research institution

- Laying the foundations for the regulatory and legislative basis for co-processing in China

- Building capacity for the use of technology in cement plants

- Establishing the basis for development of new management systems within the cement industry and the local Environmental Protection Bureaus.

A number of the documents allude to the interest that the intervention generated amongst the cement producers, but progress was hampered by the authorities not issuing permits for co-processing, which was ultimately limiting progress towards the overarching goal of the intervention, “establishing a basis for large scale implementation of safe and environmentally sound treatment and recovery of hazardous and industrial waste in the Chinese cement industry”. This impasse has been resolved and now nearly 30 cement kilns are relying on co-processing of hazardous waste, at least to a certain degree.

The Phase III proposal document also details the most comprehensive list of outputs (Table 2)

Phase 1 Outputs

Training and capacity building undertaken

- More than 30 technical seminars - 4 large scale training courses with 100 participants - 5 small scale training courses with 10-20 participants - 5 on-site training courses

Studies completed

- Baseline study on current industrial and hazardous waste generation and management practice in China - Baseline study on the status of the cement industry and the feasibility for co-processing in China - A report on the pilot demonstrations during Phase I - Trial burns with hazardous chemicals in five cement plants - Study tour with representative from the MEP to Norway and Belgium - A review of international practices in co-processing of alternative fuels and hazardous wastes in cement kilns - An international review of environmentally sound management of hazardous and industrial wastes as alternative raw materials in cement kilns - An international review on occupational health and safety during pre-processing of waste for co-processing

Training material developed

- The project has prepared comprehensive training material covering: - Technology basis for co-processing in cement kilns - International experiences and practices of co-processing - Cement quality analysis - Effects of AR on cement compositions and chemical reactions - Effects of heavy metals from AR on Cement - Environmental safety evaluation on cement produced from co-processing - Waste pre-treatment and feeding technologies during co-processing - Categories of AFR - Occupational safety and health protection during co-processing in cement kilns - BAT-BET of dioxin control in cement kilns

Technical Guidelines and publications

- Guidelines for co-processing hazardous wastes in cement kilns - Environmental protection technical specifications for co-processing of hazardous wastes in cement kilns - Standard for pollution control on co-processing of hazardous waste in cement kiln - Standard for pollution control on construction materials produced from solid wastes - Several articles in Environmental Journals in China and one international have been published; - China Daily and China Environment News, have continuously reported about the main activities and outcomes of phase I in exclusive coverage

As suggested earlier though, the project reporting reflects an ‘activity-based’ orientation, e.g. with considerable emphasis on training, seminars etc. but with modest regard to ‘higher level’ results, including longer-term changes in institutional capacity, although development and implementation of regulations in the project does represent a higher level result with potential for enduring benefit if enabling conditions and relevant capacities are developed and maintained.

## Likely sustainability

The Mid-term Review of Phase 1 notes the high quality of guidelines produced by Chinese partners and the high level of ownership of the intervention on the Chinese side which allowed development and delivery of key outputs independently of Norwegian partners. Strong ownership appears to have continued into Phase II of the intervention which was underlined in the process of redefining the activities and outputs of the intervention in that phase. The high level of ownership and involvement from the Chinese was also on display through the significant investment of financial resources which was almost equal to the monetary support provided by the Norwegians suggesting an environment conducive to the sustainability of results.

As mentioned above, the 2013 Inception Report reports two potential factors that could affect the ultimate sustainability of the intervention:

- “Such industry developments will depend on the availability of sufficient waste materials with adequate quality, i.e. the "waste market"; the right climate for investments by having in place a long term predictability with a robust regulatory framework and flexible permitting conditions; and of course, adequate technical infrastructure and competence”

- “this project does not offer any financial contribution for implementation of co-processing activities in the cement industry, or any other financial incentives, the project team is dependent of the industries willingness to involve us and to share information through their technological developments”

The above are key issues that suggest despite the intervention’s ‘successes’, e.g. in terms of people trained, test burns carried out, laying the foundation for a national plan and strategy, and the uptake of the methods promoted, the long term success of co-processing in Chinese cement kilns will likely be driven more by the economics and viability of co-processing than the quality of the design and implementation of the Norwegian co-funded intervention. The upshot is that while successful implementation of planned activities has led to successful realization of the project’s output level results, e.g. new guidelines in place, it may or may not lead to higher levels of co-processing of hazardous waste on a sustained basis in the Chinese context.

## Factors influencing effective CD

Key factors influencing the overall success of the project included the high level of Chinese ownership and the capacity of participating Chinese institutions to effectively take on new responsibilities in relation to safe management of hazardous and industrial wastes. The latter included development of high quality guidelines, as noted in the MTR.

As discussed above with respect to the design and planning processes, the lack of a clear baseline and indicators of capacity development make it difficult to clearly assess capacity results and, in turn, to discern specific factors that may have influenced the effectiveness of  CD initiatives within the project.  Nevertheless, factors influencing the effectiveness of CD in the project appeared to include: the quality of inputs, e.g. technical advisors; the compelling need to address emerging environmental challenges in the Chinese context, and; the economic benefits associated with adaptation of the technology (e.g. reducing costs of energy for cement companies) which appeared to be a driver of change, including enhanced interest in developing relevant capacity.

On the less positive side (especially earlier on), the limited commitment to awareness raising seemed to be a limiting factor as the uptake of the new methods was not as strong as it might have been had more stakeholders been informed, e.g. of the potential benefits to communities in terms of health, well-being etc., as well as industry (potential for a stronger bottom line).

# Conclusions

Overall, the project was seemingly very successful in delivering on expected outputs. The intervention made significant contributions in areas of need by increasing the awareness of the viability of co-processing of hazardous waste in cement kilns, the development of guidelines for co-processing, laying foundations for a national plan and strategy, training many sector actors, and exposing them to different experiences through study tours, workshops, and conferences. The experience with the second phase highlighted the growing ownership of the Chinese authorities in the intervention over time which was displayed in various ways, including their active involvement in the development of the inception report and the increased allocation of monetary resources to the intervention.

The project documentation reviewed highlighted some of the challenges in ‘moving to scale’ on reforms of this nature, even with policy support from national authorities. Ultimate success for the Chinese in this area will be highly dependent on the co-processing being economically viable and attractive to cement producers in addition to there being a conducive ‘waste market’. Given the importance of these challenges, and the recognition of these issues in Phase II, it could be argued that they should have figured more prominently in the initial design, at minimum as risks for project stakeholders to be aware of and hopefully mitigated. Another blockage to the objective of ‘moving to scale’ was the delay in issuing permits for the co-processing of hazardous waste.  This situation was addressed after project start up, but wasn’t acknowledged in the design nor did it lead to incorporation of specific strategies to address the concern in the early stages of the project.

The preceding points raise the question as to whether both phases were adequately informed by capacity and/or contextual analyses to identify potential constraints, and to help develop strategies to deal with them, e.g.  working with authorities responsible for issuing permits, offering support to strengthen relationships among relevant institutional actors, or ensuring that programming efforts were informed by an understanding of economic incentives that might affect broader use of the technology supported through the project.

Finally, the project, despite its successes, appears to have not had an overarching strategy for capacity development to clearly underpin a guiding intervention logic; rather there was a focus on specific capacity development activities (e.g. training, workshops), addressing specific ‘pieces of the puzzle’ but without an explicit, broader view of the ‘system’ within which guidelines would be developed and applied. This suggests that the intervention, despite its successes, could have benefited from a more systematic capacity mapping/assessment during the design stage, and support in the development of an intervention logic or theory of change.

# Annexes

## References

- Annual Report of the Sino-Norway Project on Environmentally Sound Management of co-processing of Hazardous and Industrial Wastes in Cement Kilns in China (2007 – 2008)

- Application for Grants from the Norwegian Ministry of Foreign Affairs (MFA)

- Decision Document: Project and Programme Support – Phase I

- Environmentally Sound Management of Hazardous and Industrial Wastes in Cement Kilns in

- China, Extension and Implementation, 2010-2013

- Environmentally Sound Management of Hazardous and Industrial Wastes in China –

- Extension and implementation, 2011 – 2015.

- Environmentally Sound Management of Hazardous and Industrial Wastes in China, Phase II,

- Annual Project Progress Report (Jan. 2012-Dec. 2012)

- Midterm Review of Environmentally Sound Management of Hazardous and Industrial Wastes in China – Phase 1

- Midterm Review of Environmentally Sound Management of Hazardous and Industrial

- Wastes in China – Phase 2

- Project Final Report: “Environmentally Sound Management of Hazardous and Industrial

- Waste in Cement Kilns in China” – Phase I

- Sino-Norway Project on Environmentally Sound Management of co-processing of Hazardous and Industrial Wastes in Cement Kilns in China – Phase II

Interview with Embassy Staff