Save the Children, Nicaragua – Children’s Rights

Project GLO-0605

A desk review in the evaluation of Norwegian support to capacity development

Final

February 2015

Greg Gleed

Joe Bolger

Table of Contents

1.	Introduction	1

2.	Limitations	1

3.	Overview of the Project	1

3.1 Background	1

3.2	Objectives and planned outcomes:	2

3.3	Characteristics of institutions addressed:	2

3.4	Characteristics of the intervention:	3

3.5	Implementation Arrangements, including Budgets:	5

4	Relevance	5

5	Design and Implementation	6

5.2	Responsiveness to context specific factors	6

6	Experience and lessons learned elsewhere	6

6.1 Theories of change /champions	7

6.2	Capacity needs assessment	8

7	Donor fit (Norwegian comparative strengths and historical relationships)	8

7.1	Continuous learning and adaptation	8

8	Results	9

8.1	Results (Outcomes and sustainability of Outcomes)	9

8.2	Likely sustainability	11

9	Factors promoting effective CD	11

10	Conclusions	12

11	Annexes	13

11.1	References	13

# Introduction

This desk review of Norwegian CD support to Save the Children in Nicaragua was conducted by a two-person team comprising two international consultants. A review of available documentation and interviews with staff from Save the Children in Norway and Nicaragua were at the core of the desk review approach. The desk review study is a secondary data source for the wider evaluation of Norway’s support to capacity development.

# Limitations

This desk study is based on a review of selected project documents associated with the Save the Children 2010-2014 Strategic Plan. As a desk review, this paper does not draw on data from site visits or direct observation of project activities. As a result, it tells only part of the story of this project, without the benefit of more detailed review of project activities, and interviews with a broader range of stakeholders. Nevertheless, consistent with the broader evaluation it is part of, it seeks to highlight key lessons learned about Norway’s support to capacity development in the not for profit sector in Nicaragua.

# Overview of the Project

## 3.1 Background

Norway provided support to Save the Children (SC) Nicaragua in the form of grant funding between 2006-2014 to build capacity of 16 national partners, including public bodies, to monitor children’s rights and to enhance participation in areas relevant to SC’s mandate. This review focuses in particular on the period 2010-2014 and the ‘4 Year Plan’ outlined by SC Nicaragua for that period.  SC Nicaragua’s four year plan represents the first Strategic Plan (SP) developed after the unification of Save the Children International (SCI) which took place in July, 2008. Prior to 2008 a number of Save the Children units delivered programming simultaneously in the country. Under the unification a single country office has taken responsibility for delivering on Save the Children’s mandate.

As the 2010-14 plan notes, Nicaragua has been moving towards more of a “democratic, representative and participatory political system” since the overthrow of the Somoza dictatorship in 1979. However, there have been setbacks including the municipal elections of November 2008 which the European Parliament suggested reflected “massive and systematic fraud, meaning that the results of the local elections lack any credibility whatsoever.”  The European Parliament also expressed concerns regarding the Ortega administration’s respect for freedom of expression, judicial independence, and the rule of law.  The preceding led to reductions in foreign aid.

In terms of the Nicaraguan economy, indicators were declining in the mid-2000s with various implications, including for exports, family remittances and poverty rates. At the same time, advances were made in a range of areas from education, health, nutrition, literacy, housing and children’s rights.  However, specifically regarding children’s rights, SC Nicaragua’s 2010-14 SP noted that: “Since it assumed power in January 2007, the current government has not followed up on the commitments, plans and policies in favour of children forged by prior governments, ignoring and failing to comply with the legal framework established in the Code for Children and Adolescents. What’s more, there is inadequate follow-up of the recommendations made by the Geneva Committee.” These are among the important contextual factors affecting SC’s efforts in Nicaragua in recent years.

## Objectives and planned outcomes:

SC Nicaragua’s SP outlines the key objectives for each of the six thematic areas in its programme. These are listed, in summary, below:

- Education: Fulfill Children’s right to education

- Health, Nutrition: Fulfill the right to a healthy life for children within program areas of intervention

- Child Rights Governance: To strengthen the fulfillment and monitoring of children´s rights.

- Child Protection: To fulfill children´s right to protection against violence and abuse

- Disaster preparation and emergency response: To fulfill children´s right to be protected in the event of disasters.

- Food Security: Children Thrive in Food Secure and Economically Viable Households

The SP further describes capacity development as a cross-cutting issue and an integral part of its mandate. The Results Table in the 4 Year Plan describes expected results in the header in terms of “changes in children’s lives”.  Following from that, indicators of expected results include, for example, “% of children not in school who integrate into the formal education system” or “% annual decrease in the prevalence of global malnutrition”. Some capacity development objectives are detailed under some of the thematic priorities. For example, under the ‘Child Rights and Governance’ theme a planned objective is to “Strengthen the capacities of civil society and child and adolescent organizations to promote and demand fulfilment of their rights.” Capacity results and indicators are more prominent under the Management /Operational Objectives portion of the Results Table, e.g “100% of SC partners and rights guarantors have improved their technical and organizational capacity of M&E, reporting, systematizing, and publication with rights focus, as well as the follow-up, reporting and management of administrative-financial aspects of their projects.”

## Characteristics of institutions addressed:

The most recent progress report available states that SCN collaborated with 29 partners over the period 2010-2013. Of these, 73 percent are from civil society, 17 percent are from the government and 10 percent are from the private sector or universities.  The 2010-2014 SP characterizes relationships with these groups as follows:

- Civil Society organisations: The primary objective of working with Civil Society Organisations is to promote awareness and knowledge of children’s rights and to provide technical assistance and capacity building in relevant areas. In collaborating with civil society organisations SC Nicaragua works with groups that seek to establish alliances to promote and advocate for the fulfilment of children’s right at a local and national level.

- Government Institutions: SC Nicaragua sees the government as a key partner in promoting wider systematic change for the promotion of children’s rights. SC Nicaragua prepares reports for the Children’s Rights Committee and the Universal Periodic Review and seeks to ensure that government institutions fulfil their role as duty bearers on children’s rights, in areas such as education, health care and protection. SC Nicaragua also promotes children’s participation in the preparation of reports and in different consultations.  At the national level, SC has continuing relationships with the Ministry of the Family, Adolescents and Children (MIFAN) and with the Ministry of Education (MINED) for the implementation of the Child Rights Governance, Education and Protection Programmes. SC Nicaragua’s is also linked to the National Disaster Prevention, Mitigation and Relief System (SINAPRED) through its Disaster Risk Reduction programme.

- Children and Adolescent Organisations/Networks: SC Nicaragua plans include working with children and adolescent networks that demand fulfilment of their rights. They do this by building their capacities to promote and advocate for their rights. They support formation of groups at different levels.

- Private Institutions: SC Nicaragua also has ongoing relations with two private communications institutions (one company that produces radio programming and another that does the same for television). They also collaborate with a university to develop curriculum on children’s rights and to strengthen specialised capacities related to children’s rights.

## Characteristics of the intervention:

As noted above, capacity building is seen by SC Nicaragua as a “cross-cutting issue” and “building local and national capacities” as one of five “common principles” in the 2010-2014 Strategic Plan. The other principles are: accountability (to children and other stakeholders); bringing innovations to scale; sustainable results, and; advocating for “structural and lasting positive change for children”. And as one SC staff member said, “the way we do relationships is all about capacity building”. SC Nicaragua’s overall strategic focus for the 2010-2014 period was “portfolio growth and institutional strengthening”. SC Nicaragua outlined different priorities in the SP depending on the sector (education, health and nutrition, child rights governance, child protection, emergencies) but priorities included strengthening SC Nicaragua field offices in selected geographic areas, and enhancing capacity of local authorities, as well as civil society actors.

The Partnership section in the four year plan, which describes SC Nicaragua’s strategy for working with local and national level partners, includes a sub-section on capacity development. A stated intent of the four year strategy was to “improve and harmonize the quality and efficiency of the programs and operations of SC Nicaragua’s and implementing partners in Nicaragua”. Key aspects included the following:

- Streamlining child rights programming and child protection, as well as the participation of children in all programs and parts of the project cycles

- Incorporating advocacy to ensure sustainability of program activities and contribute to structural changes for the protection of children

- Strengthening M&E to ensure sustainable results and contribute to innovation and scaling up (nationally and regionally)

- Training of partners in administration, finance and human resources in order to enhance the operational capacity of partners

The four year plan outlined a progression of investments from 2010 to 2014 moving from, among other things, training on SC protection policies and strengthening organizational processes, including M&E, financial and operational management.  The middle years were to include follow up and training support to ensure new skills and systems were being put in place effectively. The last two years were to focus on “strengthening the organization and development process management with children´s participation in order to contribute to the appropriation and local sustainable management”.

A key expected result of the investments during this period was to be: “SC staff and partners would have strengthened their capacities in development of project proposals with a strong sense of children´s rights programming, child´s participation and advocacy strategies, as well as monitoring and evaluation of projects and revision of reports in order to improve impact documentation and accountability process.” The plan also emphasised sharing learning with new staff, community and school partners and “continuation of the capacity building process at all levels.”

The modalities for capacity development in the Nicaraguan program vary by sector or programming area, but the most prominent ones identified in the SC Nicaragua documents are listed below:

- Training is the primary strategy in the education sector in Nicaragua, e.g. training teachers and MINED staff on reading skills, active learning, psycho-social development, supporting children with special needs.

- Technical support is another modality which SC Nicaragua relies on, for example, in the area of livelihood development.

- Advocacy is also an important modality in SC Nicaragua programming, e.g. to influence government policies in areas affecting children and adolescents such as education quality, children’s rights and food security.

- Institutional strengthening support from SC Nicaragua includes working with health institutions to improve the quality of services, e.g. community case management/newborn strategy, as well as strengthening of inter-municipal mechanisms to promote best practices and common platforms relating to child rights, and integrating relevant issues effectively in planning and budgeting processes.

- Relationship building – this modality is apparent, for example, in the area of disaster risk reduction. SC Nicaragua also undertook in the 2010-14 plan to engage multiple actors, more broadly, in order to support “a new culture for the construction of relations in which the higher interests of children become visible”. The latter included strengthening “guarantor institutions” so that they would be prepared to act appropriately in the case of a disaster.

- Sharing of best practices and lessons - this approach has been used to share with relevant stakeholders about livelihood strategies and advocacy on child rights.

SC staff interviewed noted that decisions about modalities are made at the country level and that in the case of Nicaragua significant emphasis has been placed on peer-to-peer sharing and learning. And while some of  SC Nicaragua’s CD efforts have been directed to the local or national actors referred to above, others have, as noted, sought to strengthen SC Nicaragua’s own capacity, e.g. in areas such as emergency response or management.

## Implementation Arrangements, including Budgets:

SC Nicaragua relied on a “mixed implementation model” to implement the four year plan covering 2010-2014. This included: 1) collaboration with partners, 2) direct implementation, and 3) mixed implementation (a combination of the first two modalities).  The rationale was rooted in “the recognition that different strategies are required to build sustainable capacities within the state and civil society toward the fulfilment of children’s rights, along with the need to acquire experience in the application and validation of models and strategies to verify impacts among children.” According to the four year strategy, criteria were developed to determine the most appropriate implementation model for each project supported, although according to SC staff, the greatest emphasis has been on collaborating with partners.

In the 2010-14 period, SC Nicaragua focused mainly on rural territories with high rates of poverty and limited organizational support while ensuring ongoing coordination at the national level. The Capacity Building ‘project’ undertaken during this period was coordinated and supported by SC Nicaragua’s M&E unit in collaboration with financial and program staff. As well as strengthening accountability to children, the programme aimed to strengthen the role of children’s networks in defending and promoting their rights.

SC Nicaragua’s receives funding from various sources. In 2009, it received approximately USD 7.6M in donor funding with SC Norway offering the most at 68%. The Swiss Cooperation Office in Nicaragua (COSUDE) was the next largest contributor at 8% followed by SC Spain and SC USA, both at 7%. The budget in the four year plan was presented by theme or sector area so it is difficult to discern how much of the overall budget (and actual expenditures) was dedicated to ‘capacity development’ per se over this period, although apparently efforts were underway at the time of this review to enhance clarity with respect to such allocations. Norway’s total expenditure for the period of 2006-2013 was $USD 8 million.

# Relevance

SC Nicaragua provided technical and financial support between 2010 and 2014 to contribute to the fulfilment of children’s rights, to strengthen the capacities of local partners to deliver on key priorities, and to encourage the sharing and implementation of successful experiences in the promotion and fulfilment of children’s rights. This support is seen as highly relevant given the fact that children in Nicaragua face numerous challenges in attaining their basic rights. For example, Nicaragua has the lowest rate of educational development in Central America, and indigenous children (an area of focus for SC) have the lowest educational levels in the country. Infant mortality rates remain high while food insecurity, child malnutrition and violence again children persist. The investments supported by SC Nicaragua are also relevant in light of Nicaragua’s international obligations with respect to children’s rights.

The challenges faced in Nicaragua are a result of systematic underinvestment in children and the regulatory systems to protect children which are weak, especially given the abandonment of CONAPINA (the National Council for the Comprehensive Care and Protection of Children and Adolescents). SC Nicaragua’s strategy recognizes that both the government and the civil society need support and guidance to develop their capacities to make strides towards the fulfillment of children’s rights in Nicaragua. SC Nicaragua also concentrates its programmatic efforts in the most vulnerable municipalities of the departments of North Atlantic Autonomous Region (RAAN), Jinotega, Matagalpa, Nueva Segovia, Madriz, Lean and Managua. A key component of their SP is to strengthen accountability mechanisms in order to contribute to the fulfillment of children’s rights, by focusing on policy frameworks, service delivery and protection systems. SC Nicaragua’s investments are intended to be mutually reinforcing, e.g. in terms of their impact on overarching priorities such as poverty reduction.

Approximately 160 children participated in the situation analysis preceding development of the SP and offered feedback on the objectives and results of the strategic planning process. Children’s participation will be a cross cutting issue for the next strategic period and the Program Coordinator will seek to ensure that children´s interests and proposals are taken into account in SC Nicaragua´s and partner’s work. Other priorities will be to develop children´s participation in the project cycle from the initial needs assessment to the final evaluation of the programs. All of the preceding have helped to ensure the relevance of SC Nicaragua investments, current and future, to local beneficiaries and other stakeholders.

# Design and Implementation

## Responsiveness to context specific factors

The interventions supported by SC Nicaragua from 2010 to 2014 were clearly responsive to the needs of children in Nicaragua. The country strategy took into consideration the underinvestment and the wider systematic failures to deliver on the rights of children at the national and local level, which was compounded by limited capacity among local stakeholders to address these issues effectively and limited awareness regarding the rights of children. Furthermore, the strategy clearly prioritised resources focused on the most disadvantaged areas of Nicaragua, where SC Nicaragua targeted the most vulnerable children. In addition, as noted above, children actively participated in the formulation of the SC Nicaragua SP suggesting a responsiveness to their specific needs. The choice of partners also reflected a recognition of the need to work at multiple levels, e.g. national, local, with a range of actors while relying on a range of approaches.

While the overall strategic emphasis is clearly responsive to the needs of children in Nicaragua, it wasn’t apparent from the review of project documents how specific activities, including various CD initiatives, were prioritised under the thematic areas of the strategic plan. Further, there is no reference to formal needs assessments being undertaken to inform either the overall strategy or the annual plans which shape the funding agreements, although references are made to what appeared to be standalone assessments and consultations. SC staff did indicate, however, that assessments are normally done with partners in advance of program start-up, relying on detailed standard forms from SC headquarters which would presumably help to ensure that initiatives under consideration are informed by contextual realities.

# Experience and lessons learned elsewhere

The Final Report from the 2006-2009 period highlighted the following as examples of capacity-related lessons learned from elsewhere:

- The support provided to SC Dominican Republic was highly valued as it allowed the entity to engage in the regional SC Alliance, and gradually introduce a child rights approach while helping it to transform from a community development organization to a national development organization focused on children’s rights. Field visits and monitoring of national SC offices were seen as particularly important inputs in these processes.

- In SC Honduras, SC’s progress report noted the importance of “employ(ing) individuals with the capacity both to wield influence in national-level inter-institutional commissions and to encourage direct actions that promote children’s rights at the local level” as a strategy for strengthening domestic institutional leadership in children’s rights. An input that allowed this to happen was SC-Norway support for salaries of Child Unit personnel and administrative staff.

- Finally, the report underscored the importance of children gaining experience in communications projects and sharing their “acquired capacities and talents” with other children in the country or region.

While it’s not clear the extent to which these specific lessons were reflected in programming in Nicaragua in 2010-2014, their inclusion in the final report from the previous phase suggests a commitment to learning and sharing. In addition, the emphasis placed on monitoring and evaluation (M&E) in the phase under review also suggested a commitment to carefully documenting experiences and sharing lessons.  And as noted above, sharing of best practices and lessons was seen as an important strategy in the 2010-2014 period, e.g. in livelihoods but also in advocacy and awareness raising with local and national stakeholders and decision makers.

The 2010-2013 progress report also includes significant details on how SC Nicaragua “used learning from evaluations, reviews, assessments etc. conducted during the period”. Examples provided in the report included:

•	Review and improvement of the content and methodology of planning instruments and aligning them with the work strategy and prioritised indicators of SC Nicaragua.

•	Identification of weaknesses and needs for strengthening capacities of SC personnel and prioritized partner organizations leading to development of training plans and decisions regarding “technical accompaniment and monitoring”, and

•	An intermediate review of the 2010 – 2014 Strategic Plan which led to an improvement of SC Nicaragua’s monitoring and evaluation system as well as those of partners.

## 6.1 Theories of change /champions

There is no reference to a ‘theory of change’ in the project documents for SC funded initiatives in Nicaragua until the 2013 SC Nicaragua’s Programme Plan in which SC Nicaragua is asked to describe ‘how it will achieve its planned results using Save the Children’s Theory of Change’. The 2013 planning document outlines a ‘theory of change’ for each thematic area of engagement rather than an overall approach for SC in Nicaragua. In the education sector, for example, it suggests that the ToC is “centred on working with partners including civil society, government institutions at local and national level, and on children and adolescents to raise the quality of education.” Other aspects included advocating for implementation of the national special education programme, promoting adoption of a teaching tool to help build a culture of peace and good treatment, supporting children’s participation and organisation in school and in the community, enhancing community organisations as actors in support of school attendance, innovation etc. In addition, relevant education initiatives were integrated into the national teacher training programme as a way of “generating results at a large scale”.

Similarly, the Health Program, including the HIV/AIDS component, centred on working with civil society partners and the Nicaraguan Ministry of Health. Beyond that, SC Nicaragua sponsored advocacy efforts relating to HIV prevention relying on “peer to peer” methods as well as school programs and broadcasting of messages. Specific references to capacity building in the ToC section of the health component of the plan spoke of “opportunities for exchanging lessons learned”, enhancing the capacity of partner organizations working in HIV and helping the Ministry of Health to systematize HIV prevention experiences in a “community-focused institutional strategy for HIV prevention.”

In sum, while there was no apparent explicit ToC informing SC Nicaragua programming, programing strategies in priority areas drew on similar approaches with SC Nicaragua: 1) playing a ‘convening’ role in bringing diverse actors together (e.g. government, NGOs); 2) supporting advocacy efforts to strengthen the capacity of various actors to demand and hold governments accountable for ongoing reforms and protection; 3) promoting the voice of children and adolescents; 4) training staff of partners to ensure they have the capacity to respond to designated priorities and to enhance the scale and sustainability of impacts, and; 5) exchange of experiences to systematize ‘good practices’.  In essence, these elements arguably represent an implicit ToC outlining conditions and activities required to affect the kind of change being promoted by SC Nicaragua.  Within this implicit TOC, SC Nicaragua was cognizant of the importance of government support, or lack thereof, to change and the need to shift its approach, as necessary, while seeking to ensure that government was at least minimally engaged on priority issues affecting children.

## Capacity needs assessment

The four year plan for SC Nicaragua (2010-14) indicated that a “diagnostic” was implemented in 2009 year that identified priority areas and opportunities for 2010, but the details of the diagnostic were not outlined in the SP.  “Performance evaluations” of partners were also referred to in the project documentation but the process and design of these were not detailed. There was also a reference to ‘assessment consultations’ in the results framework for the 2012 annual plan, but, again, specific details were not included in the planning documents made available. The 2010-2013 progress report does refer to a baseline study that was undertaken in 2012 to better understand why some schools and children had lower scores while others had higher scores. This information was used to design a course to improve schoolteachers reading and writing teaching abilities. Overall though, there did not appear to be a uniform or systematic approach to assessing capacity needs of partners and using that as a basis for determining CD investments by SC Nicaragua in the 2010-2014 period. Having said that, the SC Nicaragua staff suggested that they give priority to ‘mutual assessments’ of partners relying on consultative processes. It was further suggested that these assessments will help to shape the next multi-year strategic plan.

# Donor fit (Norwegian comparative strengths and historical relationships)

Norway is the biggest donor for SC Nicaragua funding approximately 70% (2009) of their operations. Prior to the unification of SC in 2009, the SC website reports that SC Norway was one of the first of the SC units to begin implementing programmes in Nicaragua over 25 years ago.  The magnitude and the history of Norway’s involvement in children’s issues in Nicaragua suggests a good ’fit’ which presumably provided a sound basis for relationships with Nicaraguan partner institutions.

## Continuous learning and adaptation

SC Nicaragua prepared a written response to an evaluation of cooperation with partners conducted by Save the Children International. The document is important because it demonstrates how SC Nicaragua systematically reviewed issues highlighted through the evaluation process. The recommendations from the evaluation included the following:

- A training plan based on needs assessment to identify the strengths and weaknesses of the partners should be developed prior to the commencement of a partnership agreement.

- There should be specific funds allocated to capacity building in a similar vein to specific budgets being allocated to monitoring and evaluation. It specifically states that SC should not need to rely on centralised SC Nicaragua funds.

- The topics for capacity building and methodologies should be determined by SC in collaboration with the partner organisation, and the partner organization ensuring the funding in its own budget.

- The partners need further and more periodic support in the areas of finance and procurement.  More support in following up on recommendations and support for systems development and improved internal control is vital.

According to SC Nicaragua’s written response to the evaluation, no formal assessments were undertaken at the beginning of the phase under review due to the transition to a unified Save the Children and the lack of funds earmarked for a needs assessment. Nevertheless, this will form part of their next strategic plan which is currently under development. The response does not further detail any adaptation or immediate response during the strategic phase under review. This highlights two important factors concerning SC Nicaragua’s ability to adapt and learn. Firstly, it suggests that the organisation has (or at least had during the previous period) limited scope to adjust or take on recommendations while in the midst of implementing an agreed strategic plan. Secondly, it highlights the issue of earmarking funds for capacity building. This is interesting because the support provided by Norway is specifically to build capacity, therefore, it would be assumed that some financial resources would be allocated to preparatory activities specifically to identify capacity building priorities.

# Results

## Results (Outcomes and sustainability of Outcomes)

The reporting of results in the 2010-2013 progress report focuses on results under the various thematic areas. The results reported are a mix of output and outcome level results even though the table at the bottom of the report is described as a “Results/Outcome analysis matrix” (underline added). Specific capacity development results are reflected in some sections of the report, but less so in others. One consequence is that there is not a clear sense across the board of changes in capacity of key partners arising from the SC Nicaragua investments. The thematic areas also show a slight variation in terms of what was articulated in the SP. Nevertheless, the following is a summary of key capacity development results distilled from the 2010-2013 progress report:

Children’s Rights Governance

- Thirty-six new municipal policies to ensure children rights were developed, for a total of 41 at the national level plus another 17 that are in process of being approved, for a total of 58 (38% of the municipalities in the country).

- 81 % of local governments (124) strengthened their capacities for planning with a children’s right perspective

- SC Nicaragua supported the Children’s Rights Observatory of CODENI and the Office of the Ombudsperson for Human Rights to monitor respect for children’s rights by public institutions

- 17,961 children were trained and now have knowledge regarding their rights and acquires skills to promote and demand their rights.

- Organised children and adolescents have mobilised and have made demands for fulfilment of their rights. They have expressed their interests and developed municipal agendas for the fulfilment of their and all children’s rights.

- 9,622 adults are better prepared to promote and ensure that children’s rights are met

- Community leaders have strengthened their capacities to promote and defend children’s rights, with special emphasis on the right to an education, protection, participation, and sexual and reproductive health.

- All of SC partners were trained in child participation standards.

- Children and adolescent community promoters strengthened their knowledge and skills in children’s rights and have replicated and shared their knowledge and skills with their peers.  They have also developed and facilitated activities according to their interests.

Protection

- SC trained 3,770 individuals from government institutions and civil society on identifying cases of violence, mechanisms for self-protection and steps for alerting authorities, of which 33% were children

Education

- SC Nicaragua has supported two Master’s Degrees programs in Political Science and Children’s Rights as well as three certification courses regarding Communications and Children’s Rights

- Staff from Partners and technical staff from MINED in the municipalities completed a course on how to teach children how to read well.

- 100% of primary school teachers were trained, and the teachers apparently showed improvement in terms of the methodologies for teaching reading and writing

Disaster Preparedness and Risk Reduction

- 178 communities and 426 schools (638 teachers) in 12 municipalities are better prepared and more resilient to respond to a disaster after having their response plans, risk maps, response committees strengthened, with the active participation of 39,256 children who are also engaged in DRR and disaster preparedness in their communities and schools.

HIV

- SC Nicaragua developed an HIV program in partnership with the Nicaraguan Ministry of Health (MINSA) with three Local Integrated Health Care Systems in León, Jinotega and Matagalpa. From 2011 to 2013, activities continued to be carried out with MINSA and in 2012 two additional partners – local NGOs: Si Mujer (Comprehensive Services for Women) and Health Without Limits – were included in the program. The objective was to strengthen the prevention component of the project by using a peer–to-peer education methodology (Teen-to-Teen) in District VI of Managua and in Siuna in the North Atlantic Autonomous Region (RAAN).

The results outlined above were clearly articulated in the results framework in the 2010 – 2013. What the report does not indicate though is which partner is responsible for what specific activity and what role SC Nicaragua played in the realization of the results. As a result, it’s difficult to assess which modalities have been most effective, and how much responsibility SC Nicaragua can take for the results achieved.

## Likely sustainability

There is some consideration in the 4 Year Plan (2010-2014) of exit strategies. The approach advanced is that each project within the broader SC Nicaragua ‘program’ should have its own exit strategy defined in the proposal. It further suggests that the sustainability of projects is based on the inclusion of all relevant stakeholders from the beginning, including children, with the objectives of the project being clear and achievable.  At the same time, the 4 Year Plan notes that most SC projects in Nicaragua “have been ongoing without any exit strategies”.

An example of an exit strategy is articulated in the initiative supporting the Nicaraguan Communal Movement (MCN). It determined that SC Nicaragua would support the movement for two years, until certain conditions were met for the sustainability of the movement. The exit strategy included: an identification of gaps in implementation; the consolidation of the results achieved to that point (expected or unexpected); the documentation of the major intervention strategies; and finally the strengthening of the stakeholders to ensure continuity and sustainability of the support provided.

Despite the evident reliance on exit strategies in some projects it can be argued that the sustainability of initiatives supported under the 2010-2014 SP was more likely to be a consequence of the willingness and ability of the Government of Nicaragua, and other local partners, to implement policies and allocate resources to the fulfilment of children’s’ rights. Alarmingly, according to the 2010-14 plan, the Government of Nicaragua, as noted above, abandoned the National Council for the Comprehensive Care and Protection of Children and Adolescents (CONAPINA) as well as the National Action Plan 2002-11 which meant there was no national policy in place to protect and enhance the rights of the child. On one hand, this might suggest a need for increased resourcing for SC in Nicaragua to build the capacity of government and civil society actors to fill the void and to ensure proper monitoring of children’s rights. On the other hand though, it raises questions about the sustainability of externally-funded investments in a context of government cutbacks and diminished support for domestic institutions with responsibilities for children’s well-being.

# Factors promoting effective CD

Some insights into the importance partners placed on capacity development and the modalities through which SC Nicaragua delivered CD are provided in the 2010-2013 progress report. These insights may not necessarily reflect factors promoting effective capacity development, but they do underline some of the types and characteristics of CD support provided that were particularly valued. In that spirit, SC Nicaragua partners highlighted the following types of CD contributions from SC Nicaragua during the period from 2010 to 2013:

- Formal capacity development: The partner’s saw value in ‘formal’ capacity development efforts in areas such as strengthening personnel in monitoring and evaluation, advocacy and financial administration. This type of capacity building took place in formal settings such as official trainings, certified adult learning programmes and university master’s degree programs.

- Technical assistance: The partners appreciated technical assistance provided with SC Nicaragua support, in particular, the support for the formulation of institutional strategic plans, beyond the projects financed by SC Nicaragua.

- Children focused technical capacity building: Providing technical tools to promote children’s participation and educational quality, child protection and monitoring was valued.

- Facilitating exchanges: Through these exchanges partners have learned from other partners and in the process built closer working relationships.

- Longer term partnership agreements: Relying on long-term agreements ensured a process of “accompaniment and support” throughout the program which was well received.

According to SC staff interviewed, capacity development is, at least in part, about contributing to sustainability and ensuring impact at scale. A specific example of the effective use of resources to scale-up an intervention is provided in the 2010-2013 progress report. By working through government ministries the intervention was scaled up from four to thirty five municipal health services, quadrupling the coverage of beneficiaries (infants, adolescents and pregnant women). The intervention involved training in HIV guidelines and protocols resulting in strengthened capacities of MINSA (Ministerio de Salud) health unit teams, and improving the quality of interventions in traditionally marginalised communities that have difficulty accessing health care services. This is an example of the use of strategic partnerships to increase the breadth and consequently the impact of the intervention. What is not clear from the progress report is whether the impact/quality of the intervention was maintained or increased through the process of scaling-up.

Other factors that may have contributed to more effective CD include:

- The quality of local partners and the duration of engagement with them

- The commitment of local staff

- Recognition of the need to work at multiple levels, including the enabling environment (e.g. policies) and to leverage change through mutually reinforcing investments and through partnership arrangements (effective bundling or networking of capacity)

On the less positive side, as touched on above, the government’s financial challenges and uneven commitment to child rights issues has put the onus on SC Nicaragua and local partners to keep the focus on a range of issues of importance to Nicaragua’s children. The relative weaknesses of domestic institutions, and the uneven commitment, could thus be seen as factors that have limited efforts to build capacity, effectively utilize existing capacity or to potentially sustain capacity gains realized through programming interventions.

# Conclusions

SC Nicaragua’s Strategic Plan and associated programming in the period considered under this review was clearly responsive to the needs of children in Nicaragua, and a relevant response to the systematic underinvestment in children in Nicaragua as well as the limited awareness and technical capacity to ensure the fulfilment of children’s rights in the country. The SP took into consideration the wider context and developed an approach based on the need to influence key stakeholders at local and national level in order to achieve lasting change for children in Nicaragua. In addition, the SP prioritised activities in the most impoverished areas of Nicaragua reflecting a clear focus on marginalised communities and their associated capacity needs.

Despite the overall relevance of SC Nicaragua’s mandate, as outlined in the SP, it is difficult at times to discern an overarching strategy for strengthening the capacity of SC Nicaragua’s diverse partners. This is in part due to the diversity of partners and program approaches, but also the variety of modalities and approaches employed. It is also reflected in the lack of specificity in the reporting of ‘capacity results’.  The latter follows from the limited reliance on systematic capacity assessments and consequent absence of specific capacity strategies to inform CD programming.

As noted, SC Nicaragua defines capacity development as a cross cutting theme.  While this suggests that capacity development is integrated in all of SC Nicaragua’s activities, reporting provided does not always discern between capacity development results and wider thematic achievements.  Another challenge relating to the reporting of results is, as noted, the specific role SC Nicaragua plays and their contribution to the results reported, including capacity results. The attribution challenge is, of course, not unique to SC, but does mean that it’s difficult to be clear on capacity results, especially in the absence of clear baseline data and uneven reporting on CD issues.

Nevertheless, SC Nicaragua’s programming appears to be responsive to needs based on consultations with relevant stakeholders, even if it is not directly informed by an overarching programme logic or ‘theory of change’.  Ultimately this raises the question of the extent to which capacity development efforts, such as those undertaken by SC Nicaragua, need be informed by detailed capacity assessments leading to clearly articulated CD strategies and activities with reporting that reflects that level of specificity. This approach can clearly be challenging in contexts with weak or emerging institutional capacities, with large numbers of institutional partners and when ‘implementing’ partners, such as SC Nicaragua are themselves limited in terms of their capability to offer CD support effectively across the board given the breadth and reach of their programming and oversight responsibilities.

# Annexes

## References

Save the Children Norway (SCN) 2010 – 2013 Periodic Results Report Partner Reporting, Nicaragua, 7/03/2014

4 Year Plan 201-2014 Nicaragua Programme, Save the Children Nicaragua, 2009

Annual Plan 2010 Nicaragua, Save the Children Nicaragua, 2009

Annual Plan 2011 Nicaragua, Save the Children Nicaragua, 2010

Programme Plan 2012, Funding from Save the Children Norway, Save the Children Nicaragua, 2011

A limitation in this desk review was the lack of access to evaluation documents in English for the period 2010-2014. The team did have access to one progress report covering the period 2010-2013 as well as  several planning and progress reports for the period up to 2009.

Save the Children Norway (SCN) 2010 – 2013 Periodic Results Report Partner Reporting, Nicaragua, 7/03/2014

Save the Children Norway (SCN) 2010 – 2013 Periodic Results Report Partner Reporting, Nicaragua, 7/03/2014

Save the Children Norway (SCN) 2010 – 2013 Periodic Results Report Partner Reporting, Nicaragua, 7/03/2014

Save the Children Norway (SCN) 2010 – 2013 Periodic Results Report Partner Reporting, Nicaragua, 7/03/2014