National Integrated Pest Management (IPM) Programme in Nepal, Phases I and II

Project NPL-2945

A desk review in the evaluation of Norwegian support to capacity development

Final

February 2015

Greg Gleed

Joe Bolger

Table of Contents

1.	Introduction	1

2.	Limitations	1

3.	Overview of the Project	1

3.1.	Background	1

3.2.	Objectives and planned outcomes	2

3.3.	Characteristics of institutions addressed:	2

3.4.	Characteristics of the intervention:	3

3.5.	Implementation Arrangements, including Budgets:	4

Table 1.	4

3.6.	Relevance	4

4.	Design and Implementation	5

4.1.	Responsiveness to context specific factors	5

5.	Factors external to the targeted partner institution	6

5.1.	Experience and lessons learned elsewhere	6

5.2.	Theories of change	6

5.3.	Donor fit (Norwegian comparative strengths and historical relationships)	7

5.4.	Involvement of partner institutions	8

5.5.	Continuous learning and adaptation	8

6.	Results	9

6.1.	Results (Outcomes and sustainability of Outcomes)	9

6.2.	Likely sustainability	12

6.3.	Factors Promoting Effective CD	13

7.	Conclusions	14

8.	Annex	15

8.1.	Referencing	15

# Introduction

This desk review of Norwegian CD support for the National Integrated Pest Management (IPM) Programme was conducted by a two-person team comprising two international consultants. A review of available documentation and an interview with staff from the Norwegian embassy in Nepal were at the core of the desk review approach. The desk review study is a secondary data source for the wider evaluation of Norway’s support to capacity development.

# Limitations

This desk study is based primarily on a review of selected project documents associated with the National Integrated Pest Management Programme in Nepal, in particular two mid-term reviews of the project’s two phases (see Annex 1 for list of documents reviewed). As a desk review, this paper does not draw on data from site visits or direct observation of project activities.  As a result, it tells only part of the story of this project, without the benefit of more detailed review of project activities, and interviews with a broader range of stakeholders. Nevertheless, consistent with the broader evaluation it is part of, it seeks to highlight key lessons learned about Norway’s support to capacity development in the agricultural sector in Nepal.

# Overview of the Project

## Background

The UN’s Food and Agricultural Organization (FAO) initiated support for integrated pest management in Nepal in 1997. In that year, Nepal and Norway signed an MOU for technical cooperation. An Addendum to the MOU was signed in 2003, and once again in 2007 to support the government’s National Integrated Pest Management (IPM) Programme. The national programme sought to provide farmers with ecologically sound pest control methods in order to: reduce loss of food, eliminate pesticide poisoning of farmers and consumers, and prevent ecological disturbance of plants and animals.  Phase I of the programme was implemented from 2003 to 2007 (grant of USD 1.3 M from Government of Norway) followed by a second phase implemented between 2008 and 2013. Phase II had a budget of USD 5M with 1.6M dedicated to the “regular” IPM programme component included in Plant Protection Directorate (PPD), and USD 3.4M for the FAO-supported component.

The project was implemented in an environment of political instability, socio-economic inequality, corruption and poor accountability. Other important contextual factors included Nepal’s administrative structures which are relatively weak and highly centralized with local bodies, in particular, often lacking in transparency and accountability; significant challenges given the need for the project to strengthen key national government entities as well as local and regional authorities to deliver on IPM needs across the country.

Nevertheless, agricultural remains centrally important to Nepal (36% of GDP) and the government has various policies and plans in place to support the sector. The government and sector also had broad support from international partners, including the Norwegian government, during the implementation period.  Domestic and external support has been directed at, among other things, IPM, as a response to misuse and overuse of pesticides, but also as part of a broader strategy to enhance production, food safety, commercialization of farming activities and to lessen post-harvest losses.

## Objectives and planned outcomes

The IPM Programme had two main objectives:

(1) To contribute to institutionalise a sustainable national IPM programme by strengthening the capacity of the PPD and collaborating national, regional and district level training and extension institutions in the governmental and non-governmental sector to integrate IPM training and support programs for smallholder farmers.

(2) To empower farmers, including women, to increase production and productivity efficiently while protecting the environment, conserving the biodiversity and avoiding health hazards for betterment of their livelihoods.

Phase II retained the two main objectives of Phase I (as above) while adding “linking to markets” to Objective 2. The second phase also gave particular emphasis to: consolidation, up-scaling and institutionalisation of previous achievements, inclusion of women and disadvantaged groups, and improved planning and monitoring to ensure equitable access to the programme’s benefits.

The expected outputs, by programme component, for Phase II are noted below (with associated budgets).

| Government component (“regular”) Budget: USD 1,6 million | FAO component (“intensive”) Budget: USD 3,4 million |
| --- | --- |
| Output 1: The National IPM programme is well institutionalised and fully functional. Output 2: Existing IPM training capacities are maintained and enhanced in all districts. Output 3: Information on the use and impact of pesticides is available and reflected in policies. | Output 1: Institutional capacities to provide pre- and in-service training in IPM-Farmer Field Schools (FFSs) are enhanced. Output 2: IPM-FFS alumni groups trained and organized to promote community-based sustainable agriculture. Output 3: Support services for farmer groups resulting in optimised appropriate technologies, more efficient production and better access to markets. Output 4: An information and coordination system in place to monitor progress, support policy and ensure transparency and accountability. |

## Characteristics of institutions addressed:

As suggested in the objectives outlined above, the IPM programme sought to strengthen, in particular, the PPD in the Ministry of Agriculture and Cooperatives (MOAC), as well as “collaborating national, regional and district level training and extension institutions in the governmental and non-governmental sector”. While much of the overall emphasis was on the PPD, given its central coordinating role on IPM issues, there was an implicit recognition (more explicit in Phase II) that capacity development efforts would have to focus simultaneously on capacity needs of multiple institutional and ‘informal’ actors with responsibilities (existing or potential) for supporting IPM in the country. The latter included the District Agriculture Development Offices (DADO), trained technicians from the Agricultural Service Centres and programme-trained farmer facilitators. The institutions engaged could be described as relatively weak, particularly in the start-up period, as they lacked capacity to fully address IPM, and related issues, thus the agreement to support the various project interventions.

## Characteristics of the intervention:

In Phase I, the Government of Nepal signed an agreement with the FAO to provide management and technical assistance services.  In Phase II, another agreement was signed with FAO (USD 3.4 M) which allowed for continuation of management and TA services but with a significant commitment to developing modules and approaches for intensification and institutionalization of IPM in 12 selected districts.  Areas of emphasis in the FAO component of Phase II included:  development of trainer and follow-up capacities, strengthening of IPM-FFS alumni groups, back up research and marketing support.

Under the PPD component of Phase II, the USD 1.6 M allocated was used to set up management and institutional structures to support the national IPM programme as well as to enhance collaboration with research and education institutions, private sector actors, NGOs and to enhance training capacity in districts not covered by the FAO component.   More specifically, this component facilitated establishment of an IPM Unit in PPD with a view to transforming it into a national IPM program, supported by an IPM Coordinating Committee operating under the authority of MOAC.  These were seen as key interventions to ‘institutionalise’ an IPM programme across the country along with the efforts to enhance training capacity at the district level and information sharing on IPM.

The FAO component relied substantially on FFSs to train farmers and farmer facilitators as a way of sharing IPM knowledge and methodologies. This aspect was seen as being quite successful, in part because it was farmer-driven and practical in nature.  FAO’s role was to serve as a “cooperating agency” which entailed working with the national IPM programme to institutionalise IPM in the 12 districts selected. In fulfilling its role, the FAO providing technical support (international and national) through a Project Support Unit. FAO also played a project management role in relation to, planning, budgeting, and reporting.

The Government of Nepal (GON’s) National IPM Programme also collaborated through this endeavour with a range of government and non-governmental agencies involved in the agricultural sector with responsibilities for extension, marketing, post-harvest management, research and vocational training .

As the years unfolded, the project increasingly focused on relationships among relevant institutions of various types and at different levels, representing a shift from a relatively narrow focus on skills/knowledge of key individuals and the capacity of a key central agency to a broader systems approach involving multiple institutional actors.

Throughout, programme managers were cognizant of the need to support capacity development efforts that were responsive to real needs and with potential for enduring benefits. At times, this meant offering training to farmers on concerns other  than IPM as a way of engaging them, building trust and then moving on to IPM issues.

The Norwegian role involved responsibility for general oversight of the intervention, through the Ministry of Foreign Affairs (MFA). The PPD/IPM unit submitted reports bi-annually to the Norwegian Embassy, as MFA’s representative in country, although the limited amount of reporting beyond project activities was a recurring topic of discussion during the annual meetings which were convened with FAO, PPD, and the IPM unit. Those meetings were intended to review progress against planned results, discuss annual workplans and budgets, as well as any issues of particular concern in the project at that time.

The various interventions supported under the two phases could reasonably be described as ‘complex’ as they involved multiple actors, systems and mechanisms, most of which had serious capacity and /or resource shortcomings which affected their ability, at least initially,  to  respond effectively to IPM-related challenges.

## Implementation Arrangements, including Budgets:

As noted above, Norwegian support for IPM in Nepal was channelled through the FAO and the PPD. Total funding for the programme from 2003-2013 was $USD 5.8 million. The MOAC had overall responsibility for the programme, including bringing together other stakeholders (governmental and non-governmental). The PPD was the designated implementing agency within MOAC, under the leadership of the PPD’s Program Director.  The PPD’s responsibilities included supervising district level plant protection staff, overseeing regional laboratories and collaborating with coordinating and technical committees. Aside from its ‘project management’ role, FAO played a strong technical role as a ‘process consultant’ helping MoAC with planning, budgeting, and reporting as their capacity at the outset was limited.

The table below highlights the areas and amounts funded in Phase II (up until the end of 2011) by component (FAO and PPD).

### Table 1.

| Five areas of institutionalisation | FAO component | PPD component | Total |
| --- | --- | --- | --- |
|  | Aggregated up to 31/12/11 | Aggregated up to 31/12/11 | Aggregated up to 31/12/11 |
| Coordinating institutions | 63,000 | 111,000 | 174,000 |
| Research institutions | - | 97,000 | 97,000 |
| Education institutions | 82,000 | 84,000 | 166,000 |
| Support service inst. | 339,000 | 357,000 | 695,000 |
| Farmer groups and farmer institutions | 807,000 | 468,000 | 1,275,000 |
| Sum | 1,290,000 | 1,117,000 | 2,407,000 |

Table from Phase II mid-term review (figures in USD)

## Relevance

According to the Phase I and II mid-term reviews, the IPM programme’s objectives were well aligned with Government of Nepal’s priorities and the needs of various stakeholders involved, building on and with clear linkages to other regional and national IPM projects. Interest in IPM among stakeholders (e.g. farmers, government officials) was described as “high and increasing”. IPM was also seen as contributing to broader goals of poverty reduction, food security, increased food safety and protection of farmers’ health and the environment. It was further judged to be relevant in light of Nepal’s changing contexts. The programme operated in almost all districts, security permitting, and was conducted in close collaboration with primary beneficiaries, including small-holder farmers.

The Norwegian-funded programming responded to specific capacity constraints or shortcomings related to IPM facing Nepalese stakeholders at various levels – from policy to operational – although it is not clear from the documentation reviewed how decisions were made about priority capacity issues to address or the most appropriate modalities to address them. There was also insufficient data in the documents reviewed to ascertain whether the interventions were in line with either PPD’s or MOAC’s wider ministry institutional development strategies (assuming such strategies existed).  The project reviews also reflected concerns about the readiness or capacity of Nepalese stakeholders to sustain the changes promoted over the long term (addressed further in Sec 4.2), an understandable challenge to highlight given the relatively low capacity of the institutions involved, the ongoing conflict in the country and other serious contextual factors.

# Design and Implementation

## Responsiveness to context specific factors

.

As suggested in the preceding section, the project built on and was responsive to the policy priorities of the Government of Nepal and the interests of ultimate beneficiaries. However, documentation was not made available from the pre-design or preparatory phases to inform this review of the extent to which or how project designers or managers were responsive to context specific factors in Nepal at those stages, although some commentary was included in the mid-term reviews.

The most significant overall contextual factor at the time of project implementation was the conflict in Nepal. The general view from the mid-term reviews was that the project was not only sensitive to the dynamics of the conflict but played a positive role in empowering local communities and in the process enhancing accountability of governments at various levels. The project also seemingly built on the strong leadership provided by key stakeholders and the motivations of farmers to benefit not only from the technical inputs but the social and economic advancement associated with engagement in the project, e.g. strengthening farmers groups, enhancing market access.

Other contextual challenges outlined in the mid-term reports included lack of market access and difficulties obtaining local resources, which would suggest that the planning processes could have benefited from stronger analyses of such considerations, while recognizing that such variables can, of course, change over time. ‘Linking to Markets’ was in fact added to Objective 2 in Phase II which suggests that project stakeholders learned from experience  and adapted to contextual factors, even if beneficiaries continued to struggle in meeting market objectives.

The high levels of participation in farmer field schools during implementation suggests that this approach was responsive to the prevailing context, including the capacity challenges facing Nepalese farmers. That responsiveness of the FFSs can be attributed largely to the fact that the curriculum used in the schools was need-based and thus directly relevant to participants’ needs. The fact that the FFSs were able to continue with minimal disruption over the course of the project despite the conflict affecting many areas of the country also underlines how this approach was appropriately responsive to that aspect of the project context.

The Mid-term review pointed towards two contextual factors that may not have been considered adequately at the design phase and that may have diminished the responsiveness of the intervention to salient factors in the project context. The Phase I mid-term review, for example, recommended that a “culturally grounded /sensitive approach should be sought and adopted gradually” suggesting that training materials and approaches had fallen short of the mark in these respects during early implementation. In addition, the review noted that ‘institutionalizing’ objectives may have been undermined by lack of understanding of financial incentives and clear direction re the mandates for the district, regional and national level oversight committees with respect to IPM issues.

# Factors external to the targeted partner institution

The main drivers behind the establishment of this programme were the priority given by the Government of Nepal to the agriculture sector, including IPM issues, and the expertise and resources Norway was able to bring to the initiative. The interventions arising from these shared priorities contributed to mainstreaming of IPM policy during the second phase and efforts to institutionalise IPM amongst various linked stakeholders, including other directorates within the Department of Agriculture, educational institutions, INGOs, and local government agencies.

The documents reviewed didn’t reveal how other factors external to the target partner institutions, e.g. power relationships, inter-institutional links, were considered in the design phase or during implementation, or contributed to strategic thinking about how to address capacity issues in the project.

## Experience and lessons learned elsewhere

There are few indications in project documents of learning about approaches to ‘capacity development’ outside of the project itself. However, the FAO component did commit to various approaches or methods that would have allowed the team to draw on lessons or experiences from Nepal or elsewhere, including: enhancing pre- and in-service training capacity, e.g. curriculum development for training of farmers, training of IPM Facilitators and farmer trainers, international study tours/policy level observation tours, internship opportunities for students, opportunities for students to conduct IPM-FFS related research, assistance in development of curricula for technical and higher education institutions. The mid-term report ranks activities in these areas as “satisfactory” without offering any analysis of which methods were more or less effective and why.

## Theories of change

There is no reference in any of the project documents reviewed to a theory or theories of change in relation to the Norwegian-sponsored IPM programme. Having said that, it could be argued that there was an implicit ToC in the programme which evolved from the first to the second phase of the project. Some of that is reflected in the Phase II inception report which talks about a strategy to “implement and gradually up-scale participatory IPM using the Farmer Field School approach as a national programme covering 75 districts of Nepal … as well as strengthening of farmers’ groups/organizations together with activities to promote better marketing of safer commodities…..” The Inception Report also underlined the main themes of the second phase which were consolidation, intensification and institutionalization noting that “support is based on the realization that IPM is not just about pest control, but about a holistic and sustainable production management that can help achieve food security and alleviate poverty.”

However, the experience of the IPM programme suggests that a more fully elaborated ToC may have helped stakeholders to develop a clearer sense of the requirements for sustainably advancing project objectives. It could also have helped to better test underlying assumptions regarding conditions required for success, including capacities required, constraints to developing or effectively utilizing them, or incentives of farmers to enhance their own capacity for IPM in the absence of guaranteed markets. The project also seemingly wavered in its determination as to whether capacity development efforts should be relatively shallow but broad (with high potential for demonstration across a large number of districts), or more focused (fewer beneficiary farmers but with greater emphasis on ‘quality’) – the latter emerged as a preferred ‘capacity’ strategy, but not until later in the project. As the Phase II mid-term report noted: “Towards the end of Phase I, involved partners recognized a need to bring government agencies, research and teaching institutions, NGOs and farmer associations closer together in a concerted effort to develop and promote IPM.”

Phase II also focused more on two other dimensions, based on lessons learned in the implementation of Phase I. Those were: 1) a clearer commitment to research, including links with research institutes, “to support IPM now and in the future, particularly as new pest problems arise with climate change”, and; 2) a commitment to better support ‘market links’ for farmers relying on IPM methods.  Beyond that, as suggested, Phase II emphasized “consolidation, up-scaling and institutionalization” of previous achievements. While all of this didn’t constitute a fully elaborated ‘theory of change’, it clearly reflected adaptations in the design and implementation based on learning in the earlier phases of the programme.

An implicit theory of change related to these investments would also highlight the importance of In sum on this aspect of the review, there was broad ‘buy-in’ by stakeholders on the programme’s objectives, supported by key institutional leadership, and the existence of shared incentives to achieve planned capacity changes among farmers, government stakeholders and market actors.

There was less evidence that any implicit theory of change involved a detailed and systematic approach to assessment of relevant capacity issues, or development of clearly articulated CD strategies. Rather priority approaches to CD seemed to emerge during implementation, e.g. the strong emphasis on FFSs, as the benefits of such strategies became apparent.

And while there appeared to be broad agreement on objectives, as stated above, there appeared to be less consensus or clarity as to how the changes promoted would be sustained beyond donor involvement. This experience is clearly not unique to this project but reflects the challenge often faced in externally funded projects of sustaining change which is reliant on local institutions with limited capacity, including the financial wherewithal to support reforms once external support is withdrawn. Programme stakeholders did employ various strategies to address this, e.g. strengthening of PPD, training of Nepalese facilitators etc. but absent an end-of-programme evaluation or impact study, it’s not possible to assess how successful those strategies ultimately were.

## Donor fit (Norwegian comparative strengths and historical relationships)

The documents reviewed noted that Norway had prior experience in IPM, although it had been elsewhere in Asia, not in Nepal. Norwegian scientists who had been involved in IPM elsewhere in Asia were not involved in this programme, partly for budgetary reasons, although the Phase II report suggested that Nepal could have benefited from that expertise in forecasting pest outbreaks and food safety monitoring. Nevertheless, Norway has been involved in this area of work in Nepal since 1997 suggesting some depth of historical engagement and relevant institutional strength.

## Involvement of partner institutions

As noted in the Phase II mid-term review, there was a recognition near the end of Phase I of the need to improve collaboration of various institutional actors, e.g. Government agencies, research and teaching institutions, NGOs, farmer associations, in order to promote IPM more effectively in Nepal. Among other things, this required strengthening the PPD so that it could play a stronger coordination role on IPM issues which was central to Phase II. Phase II was thus clearly designed and implemented taking into account the complicated myriad of institutional actors involved, including government stakeholders at national and local level, working groups, INGOs, and local farmer associations. However, while the Phase II MTR noted that the GoN had made “some progress in institutionalisation in all areas of education, coordinating organisations, service providers and farmer groups in terms of bringing IPM high on the agenda ….. (l)ess has been achieved in terms of increased staff in IPM at the various agencies.”

The Phase I mid-term review had also noted the need to engage district and regional level coordinating committees more in areas such as monitoring and evaluation and follow up on FFS activities.  The Phase II MTR indicated that coordination committees had been set up at national, regional and district level “with defined roles and responsibilities”.  Input was also offered to regularize coordination committee meetings, although the report noted that that objective had not been fully been realized.

The Phase II MTR further noted that despite the intention to engage research institutions, and issuance of invitations to such institutions to take advantage of opportunities within the programme, research “has not been a major component of the programme”. This had already been flagged in the Phase I MTR which described the “low priority for research in the programme”. That review recommended specific collaborations but by the time of the Phase II MTR, only “a few minor research projects funded by the programme, had been carried out”.

## Continuous learning and adaptation

The documentation reviewed highlighted learning and adaption within the project as it moved from the first to second phase, including taking on a broader selection of Nepali partners and adding new foci such as promoting market linkages.  Adaptation also included developing more ‘culturally sensitive’ approaches to implementation based on a recognition that successful adoption of IPM depends on a range of personal and social factors including empowering farmers to express their needs and participate in groups with diverse individuals.

Another notable aspect with respect to learning and adaptation was the systematic building on recommendations from project reviews. The last MTR identified three documents that provided recommendations that the project actively drew on: (i) National Integrated Pest Management (IPM) Programme in Nepal; Midterm Re-view Report, 2006 (ii) National Integrated Pest Management (IPM) Programme in Nepal II; Appraisal of Project Proposal, 2007 (iii) National IPM Programme in Nepal: Consolidation, Up-scaling and Institutionalisation, Phase II; Inception Report, 2009. In total, responses to thirty recommendations were detailed in these reports ranging from technical reporting to modalities for working in partnership. Overall, the reporting affirms a high level of integration and adaption to the recommendations advanced.

# Results

## Results (Outcomes and sustainability of Outcomes)

The IPM programme took a ‘results-based approach’ to planning and implementation, although the Phase I mid-term review noted weaknesses in monitoring, evaluation and reporting at various levels, including the district level. This, along with the absence of a baseline study, made it difficult to measure progress against expected results. A later review also noted some inconsistencies in the articulation of results.

In terms of actual achievement of results, the Phase I mid-term review noted that the number and spread of activities was “impressive” and that the project team should be “commended”. At the same time, it noted that the activities were still “insignificant” in light of the scale and complexity of the challenges being faced. This led to various recommendations, including calls for “continued financial and technical support … for some time” reflecting a recognition of the complexity of the challenge being addressed and the time required to fully achieve some of the expected results.

The Phase II mid-term review documented results achieved as of 2012 in relation to the key expected outcome, as follows:

| Narrative Summary | Objectively Verifiable Indicators | Assessment by Midterm Evaluation Team |
| --- | --- | --- |
| PURPOSE: To build on the existing institutional and programme strengths acquired by Nepal, both in the governmental and non-governmental sectors To scale up IPM programme in commercialization of agriculture covering selected districts of Nepal OBJECTIVES: • To contribute to institutionalize a sustainable national IPM Programme in Nepal by strengthening the capacity of PPD, collaborating national, regional and district level training and extension institutions in the government and non-government sectors to integrate IPM training and support programme for small holder farmers. • To empower rural farmers including women to increase production and productivity efficiently, while protecting the environment, conserving the bio-diversity and avoiding health hazards for betterment of their livelihood and linking with markets OUTCOME: National IPM Programme institutionalized and supporting community-based sustainable agriculture | 1. Separate IPM unit with full-time personnel established within PPD 2. FFS training and follow-up capacity exists within DADOs and other institutions 3. IPM-FFS activities coordinated on national, regional and district levels 4. Graduates from educational institutions able to implement IPM-FFS without further training 5. IPM-FFS integrated in the technology development of research institutions 6. Self-reliant smallholders and farmers’ groups/ associations/cooperatives have access to market information and technical support 7. Scaling up of programme is in pace with available capacity and maintains quality of farmer education | 1. IPM unit established, but three staff members on loan from other directorates. 2. Satisfactory 3. Satisfactory 4. Satisfactory 5. Satisfactory for IAAS, CTEVT and HICAST, but not for NARC 6. Satisfactory progress, but much remains to make a substantial impact nationally 7. Satisfactory progress, but scaling up needs continued attention |

As the table above suggests, the Phase II mid-term review characterized progress against most result indicators as “satisfactory”, with several qualifiers and some concerns regarding scaling up, the extent of access to market information and technical services by farmer groups, and sustainability of results. The key terms in the Outcome level result statement relating to the National IPM Programme are “institutionalized” and “supporting community-based sustainable agriculture”. The Phase II MTR looked at a number of factors relating to progress on “institutionalization”, a key to sustainability of intended capacity results. The report noted that with the government’s anticipated new IPM Policy, IPM issues were more likely to be factored into relevant plans, e.g. the Agricultural Perspective Plan and Sector Development Priority. At the same time, it noted that various institutional capacity issues, if not properly addressed, could limit potential gains associated with the passage of the new policy. The report also recognized that sustainable improvements in performance in relation to IPM in Nepal would require sustainable change in the broader ‘capacity system’ (not just the individual components) supported by Norway and other external actors, as well as Nepalese stakeholders. Specific comments on institutionalization of changes were offered in the following areas:

- Strengthening of PPD (including its coordination function):  The transfer of responsibility from FAO to PPD was seen as being “on track” in 2012 with PPD leading the IPM programme and being responsible for monitoring and evaluation, and FAO focused on module development and technical backstopping. With support, PPD had increased its professional capacity (e.g. core staff grew from three in Phase I to five in Phase II). However, three staff were seconded to the Directorate leaving open the question of permanent capacity to take on PPD’s important coordinating role. The latter was seen as particularly important given PPD’s role in overseeing IPM work at the decentralized level. The conclusion was that the capacity on hand, even with the seconded staff, was insufficient to assume that role effectively. PPD established a separate IPM unit in 2008 with 11 new staff. The PPD staff were to provide technical backstopping to the 12 “intensive districts” where FAO was operating as well as support to the “regular districts”. Those positions were financed by FAO. The technical backstopping included development of curriculum and training modules, designing post-FFS activities and follow up programmes for FFS groups and on marketing issues. According to PPD reports, these responsibilities were shared at the district level (est 60/40 between PPD and FAO) with PPD playing a strong role in coordination and FAO playing a technical backstopping role while providing links to the global scientific community.

- Enhancing links with research and educational institutions: The Phase I midterm review (2006) referred to the “low priority for research” in the IPM programme and recommended enhanced collaboration with the Nepal Agriculture Research Council (NARC) and various universities. According to the Phase II review, and as highlighted earlier, this had not materialized beyond “a few minor research projects”.  While budgets have understandably been an issue, the limited engagement of research institutions and associated dearth of applied research was seen as a constraining factor that could limit improvements more broadly in IPM, e.g. responding more effectively to newer challenges associated, for example, with climate change. In terms of educational institutions, the Phase II review noted strong efforts by various institutes to include IPM and FFS in their curriculum, often with the support of IPM programme staff, with courses involving field schools for participating students. Graduates have also been posted to the districts and sub-district agricultural offices to serve as junior technicians or junior technician assistants (JT/JTA), thus responding to the need for capacity at that level.

- Building capacity and links with District level offices: In Phase I, the District Agricultural Development Officers (DADO) undertook IPM activities, but they weren’t linked to the IPM programme. During Phase II, direct links were made with the IPM programme with a view to ensuring that domestic support would be in place beyond donor funding. As of 2012, the IPM programme was extended to 55 districts in addition to the 17 “intensive districts”. District agricultural staff, e.g. Plant Protection Officers, Agricultural Development Officers, have been included in the IPM training, and in turn trained farmer facilitators and farmers as per the ‘institutionalisation’ strategy. District Development Committees are now obligated to spend 15% of their budget on agricultural development, but engaging district and village level committees has been a challenge, according to the Phase II review, due to the absence of elected local officials.

- Strengthening farmer groups: This is the aspect of ‘institutionalization’ which received the biggest commitment, budget-wise, in Phase II and which realized the most progress. The Phase II report described the organizing of farmers in field schools, producer associations, and marketing groups as “remarkably successful even during the period of unrest”. Among other things, the programme helped farmers establish registered groups, with the intent that they would eventually become cooperatives.

The use of the farmer field schools had shown that even in a situation of violent conflict, such community, need-based agricultural development activities could be implemented with minimal disturbance. The amount of activities and geographical spread of the programme was impressive compared to the minimal staff associated with the programme at the central level.

Overall, the Phase II review noted that implementation was “going well and progress is satisfactory”. At the same time it noted that the number of farmers reached directly was relatively low (10,000), although the programme had had a “broader impact through assisting the work of other government projects, NGOs and farmer-to-farmer communication”.

The fact that there was no baseline conducted for Phase I and no final report or end-of-project evaluation available made it difficult for this Desk Review to clearly ascertain to what degree the delivery of activities and outputs against planned activities was achieved. Nevertheless, the documentation reviewed suggested that the project led to broader changes in terms of the thinking and practices of key stakeholders regarding IPM.

## Likely sustainability

The Phase I mid-term review raised various concerns regarding sustainability of initiatives supported through the programme noting that more attention need be paid to institutionalizing the programme within the government’s national development agenda, including more commitment to research, inclusion of IPM issues in extension work and development of an exit strategy.  These elements were addressed in the Phase II program document, with the exception of a specific exit strategy.

The Phase II mid-term report noted that the process of “institutionalization” was moving forward “according to the logframe”, although there was no certainty that it would be completed by the end of the project, key considerations being: an increase in the number of ‘permanent’ staff in PPD and an enhanced coordination role for the Department of Agriculture to ensure a broader impact on line agencies. The latter was also seen as important in strengthening the role of interested research and educational institutes. The review also highlighted a number of challenges that it saw as potentially affecting realization of expected results and sustainability. These included the following: “(i) lack of a market for IPM products, (ii) lack of area-wide pest control (e.g. insects fly from one field to an IPM field), (iii) lack of coordination of District Agriculture Development Office (DADO) with the District Coordination Committee, (iv) insufficient number of trained manpower at DADO, (v) difficulty in obtaining some of the indigenous materials used in IPM, such as wood ash, biobotanicals, etc., (vi) abundance of synthetic pesticides and lack of biopesticides, (vii) insufficient expansion of production and of farmer training for market regularity of produce – only 1 to 2 Farmer Field School per year, (viii) need for diversification, regularity and quantity of products, (ix) lack of IPM policy, (x) need for establishment of an IPM value chain, (xi) need for development of a condensed version of the IPM for other farmers who are interested.”(Phase II MTR, p. 22)

Another constraint which could affect the sustainability of gains realized through the project was the issue of the numbers of staff available to the IPM programme and their retention beyond the project end. The Phase II MTR described the level of staffing supported by FAO as sufficient while noting that PPD staff was insufficient and often engaged in other regular programs of the unit. The report further noted that MOAC had not deputed additional staff for the IPM program due to what it described as “rigid government regulations”.

An important observation to underline in this section is the seeming absence of any systematic reflection on potential scenarios or actions which could be taken to ensure the sustainability of project activities other than the continued involvement of a donor into a third phase. In retrospect, this can be considered a serious oversight as the intervention did not continue into a third phase. While there were discussions on potential alternative donors, there was no contingency plan put in place for a future scenario with no donor support.

## Factors Promoting Effective CD

According to the two mid-term reviews, the IPM programme experienced real success, despite the backdrop of conflict and political uncertainty in the country, among other challenges. This was attributed to a number of factors, including inclusion in the project design of objectives that all stakeholders could buy into, even during a time of conflict, e.g. increased access to meaningful economic opportunities. In the process, the programme directly affected approximately 10,000 farmers while stimulating changes in thinking about pest management, more broadly, among key actors at various levels.

While the programme documentation did not focus extensively on capacity development strategies or methods, the two mid-term reviews, in particular, highlighted a number of issues that influenced the effectiveness of CD initiatives in the IPM programme over its two phases and in the process yielded lessons about approaches to CD. These include the following:

- Depth vs breadth in capacity investments – As noted in the Phase II review, a choice had to be made in the programme whether to invest significantly in a relatively small number of farmers or to touch a larger number of farmers and other actors more superficially. A decision was made in favour of the former approach. Doing so clearly benefited those farmers who were able to incorporate IPM effectively into their farming operations. On the other hand, investing in the capacity of a more limited number of farmers left the prospect of potentially diluting the impact nationally. The team dealt with this dilemma by making strategic investments in key capacities that were seen as central to demonstrating the value of IPM, while seeking to contribute to conditions that would allow further spread of IPM practices beyond the term of the project.

- Taking a ‘systems’ approach to capacity challenges - Towards the end of Phase I, there was a recognition that if the programme was to succeed that partners key stakeholders with responsibilities for IPM would have to collaborate more effectively, e.g. government agencies, research and teaching institutions, NGOs, farmer associations. Among other things, this meant enhancing the capacity of PPD to coordinate these various actors. The Phase II review further noted that institutionalizing IPM among farmers “requires that a whole set of factors beyond pest control are addressed”. Among the factors they identified were: marketing, storage facilities, certification of IPM products, manufacturing of biopesticides, information service, savings and loan schemes, etc. While recognizing that taking a broader, systems approach appropriately reflected the complexity of the farmers’ situation and needs, the Phase II review also noted how it also could be much more costly and time consuming than focusing simply on the knowledge and skills of a small groups of farmers as well as the capability of one or several units such as PPD. Striking a balance between simplicity/manageability and complexity has thus been a challenge the project has faced. This reflects the inherent tensions in addressing a complex development challenge, with multiple systems dimensions, in a projectized format. Part of the response to this challenge was collaborating with other projects focusing on similar issues while trying to be strategic about key elements that would enhance prospects for sustainability of IPM advances.

- Mix of hard and soft capacities – Hard capacities refer to individual skills or competencies, e.g. financial planning, environmental management, or the capabilities of organizations or mechanisms, e.g. the capability of a coordinating unit such as PPD to exercise its mandate. Soft capacities refer to factors such as legitimacy, trust, motivations, shared values, commitment and leadership that are often critical to success. The latter can also include capability to network, collaborate, network or adapt to complex or quickly changing circumstances. In the case of the IPM programme, the log frame reflects the emphasis on hard capacities, e.g. farmers skills, capacity of PPD, district level officers etc. While there was no apparent explicit emphasis on soft capacities, the Phase II review noted how “successful adoption of IPM depend(ed) on a range of personal and social factors, such as self-confidence by farmers to step forward and express their needs, courage to get involved in groups with diverse individuals, marketing skills to sell IPM products, organisational skills, bookkeeping skills, etc. The IPM programme has, therefore, expanded its scope to assist farmers with all these issues.” This shows an openness to learning and adaptation by the programme team, including a responsiveness to the importance of soft capacity issues which were not part of the programme’s log frame.

# Conclusions

This intervention was clearly relevant to the priorities of the GoN and responded to capacity constraints and shortcomings relating to IPM in Nepal. Despite a context of conflict and political uncertainty, this complex intervention achieved real successes. The intervention was sensitive to contextual dynamics but also managed to empower ultimate beneficiaries and in the process enhance capacity and accountability at various levels of government. In addition, the intervention displayed the ability to respond to recommendations and evolve throughout the lifespan of the project. The midterm review of Phase II showed a high level of responsiveness to recommendations from previous reviews. In that spirit, Phase II built on the objectives of Phase I while focusing more clearly on up-scaling and institutionalisation of previous achievements, inclusion of women and disadvantaged groups, and improved planning and monitoring to ensure equitable access to the programme’s benefits. The project also added ‘linking to markets’ as a priority, once again suggesting an ability to learn throughout the phases of the intervention.

The Phase I mid-term review noted weaknesses in the results based management approach at various levels, as noted previously. Coupled with the absence of a baseline study, it was thus problematic to measure progress against expected results. Despite this, the intervention was seen as being well managed. One of the factors that promoted a conducive management environment was a clear set of project objectives that everyone could buy into. The strategic approach to investing resources, taking a systems approach, and focusing on a mixture of soft and hard skills all contributed to the success of this intervention. Furthermore, the modality of the partnership was also seen as having played a positive role in the success of the intervention.

Norway’s experience, more broadly, with capacity development in Nepal has been within a context of working with various collaborating ministries and agencies with weak to limited capacity. In the case of this intervention, part of the ‘success’ was attributed to FAO providing technical assistance support on basic project management, including the development of implementation plans, budgeting, reporting, and the day to day management of the intervention.   This was seen to be a central contributing factor to the successful implementation of the project.

Finally, as touched on above, some project stakeholders saw a need for a third phase, focused on, among other things, bolstering local markets and creating better linkages to them. And while much of the project documentation pointed towards a potential third phase, it wasn’t apparent that detailed consideration was given to exit strategies during Phase I or II. The Norwegian government ceased to support the intervention despite the advances realized in the two phases and what various stakeholders saw as a need for further investments to enhance prospects for institutionalizing planned results. From a capacity perspective,  this suggests that the project could have benefited from a clearer analysis of capacities required to sustain project results, followed by adoption of appropriate CD strategies with agreed time frames and realistic exit strategies. Absent that, the project has still contributed to impressive gains in IPM in a complex and challenging environment. Arguably though, those gains might have been more substantial and enduring with appropriate analyses and strategies to inform programming and exit strategies, possibly leading to a third and final phase.

# Annex

## Referencing

- Noragric Report No. 31 National Integrated Pest Management (IPM) Programme in Nepal (NPL 2945) - A Mid-term review (2006)

- Addendum No. 1 to Agreement between The Kingdom of Norway and His Majesty's Government of Nepal regarding the Provision of Financial Assistance of a National Integrated Pest Management Programme (IPM) in Nepal (2006)

- National IPM programme document (2008)

- Agreement between The Government of Nepal and The Norwegian Ministry of Foreign Affairs Regarding Development Cooperation Concerning the Programme Integrated Pest Management Phase II (2008)

- Appropriation Document, National Integrated Pest Management II, (2008)

- Midterm Review of the National Integrated Pest Management Programme in Nepal, Phase II (2012)

Ministry of Agriculture and Cooperatives (MOAC) figure for 2012.

Figures sourced from the Phase II Appropriation Document. Page 3

Arrangements described relate mainly to Phase II.

It should be noted that capacity development is being used specifically in reference to building the capacity of farmers in the sentence