Capacity Development for Statistics in Malawi

A case study in the evaluation of Norwegian support to capacity development

Final

September 2015

Joe Bolger

Chiku Malunga

Table of contents

1 INTRODUCTION	5

2 LIMITATIONS	5

3 OVERVIEW OF THE PROJECT	5

3.1 PHASE I - Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistics Office and Statistics Norway (2004-2006)	5

3.2 PHASE II - Capacity Building for Statistics and Planning (2007-09)	6

3.3 PHASE III - Developing The National Statistical System (2013-2016) and MEPD Macro Model For The Malawi Growth And Development Strategy (2012-2014) 	7

4 RELEVANCE	8

4.1 Country Needs	8

4.2 Norwegian Priorities	9

4.3 National Priority and Demand	9

5 STRATEGY AND DESIGN	10

5.1 Internal Context of the Institution	10

5.2 Planning Process and Capacity Needs Assessment	11

5.3 Evidence Base	14

5.4 Theory of Change	14

5.5 National Ownership	15

5.6 Donor Fit	15

6 IMPLEMENTATION AND MANAGEMENT	16

6.1 Implementation Arrangements	16

6.2 Results Verification and Measurement	18

6.3 Efficiency	19

6.4 Adaptation and Adjustment	20

7 RESULTS…..…………………………………………………………………………………………………………..……………………20

7.1 Short- and Medium Term Results	20

7.2 Sustainability	24

8 CONCLUSIONS AND LESSONS LEARNED	25

8.1 Overall Conclusions	25

8.2 Lessons and Success Factors	25

Annex 3 Scorecard	36

# Acronyms

ACBF				African Capacity Building Foundation

AES				Annual Economic Survey

CD				capacity development

CRESS				Country Report on Statistics for Malawi

DFID				Department for International Development

DNHA				Department of Nutrition, HIV, and AIDS

EAD				Economic Affairs Division

EU				European Union

GoM				Government of Malawi

IHS				Integrated Household Survey

LMIS 				Labour Market Information System

MAPS				Marrakech Action Plan for Statistics

MASEDA			Malawi Socio-Economic Database

MDG				Millennium Development Goals

MDPC (formerly MEPD) 		Ministry of Development Planning and Cooperatives

MEPD 				Ministry of Economic Planning and Development

MGDS				Malawi Growth and Development Strategy

MOF				Ministry of Finance

MOU				Memorandum of Understanding

MPRSP				Malawi’s Poverty Reduction Strategy Paper

MTR				Mid-Term Review

NA				National Accounts

NKO				Norwegian kroner

NSO				National Statistical Office

NSS				National Statistical System

PARIS21			Partnership in Statistics for Development in the 21st Century

QAF				Quality Assurance Framework

RBM				Reserve Bank of Malawi

SADC				Southern African Development Community

SCS				Statistical Common Service

SN				Statistics Norway

SNA				System of National Accounts

SUT				Supply and Use Table

TFSCB 				Trust Fund for Statistical Capacity Building (World Bank)

ToC				Theory of Change

WMS				Welfare Monitoring Survey

# INTRODUCTION

This case study of Norwegian capacity development (CD) support to the statistical system in Malawi was conducted by a two-person team comprising one international and one national consultant. A country visit to Malawi and a series of stakeholder interviews were at the core of the case study approach. Furthermore, a large number of programme documents and additional literature was consulted.

The results of this case study have been synthesised alongside a number of other case studies from Malawi in a country report. Both this case study and the Malawian country report are key data sources for the wider Itad-led evaluation of Norway’s support to capacity development.

# LIMITATIONS

- The interviewees met during the review process were all based in Malawi. Only one Statistics Norway (SN) staff member, on long-term assignment in Malawi, was interviewed. However, a draft of this document was provided to SN staff in Oslo resulting in feedback from them which was factored into the final report.

- Several key donor staff involved in statistics were not available for interviews during the evaluation mission.

- A draft report was shared with the National Statistical Office (NSO) but feedback was not received from the agency so input from that source on the draft could not be included in the final report, although key staff from the agency were interviewed during the evaluation process.

# OVERVIEW OF THE PROJECT

The Norwegian Government has funded a number initiatives since 2004 to strengthen the national statistical system in Malawi. A two phased approach to the project was proposed in the original plan but was later extended to three phases of support with different components eventually concentrating on different aspects of or needs in the statistical system in Malawi. This review draws on a selection of the interventions funded by Norway since 2004 rather than trying to cover every component in detail. The sections immediately below offer a brief overview of three parts funded by Norway, including key objectives outlined in project documents.

## PHASE I - Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistics Office and Statistics Norway (2004-2006)

The first phase of Norwegian support was designed to serve the needs for information to support Malawi’s Poverty Reduction Strategy Paper (MPRSP), including information required by implementing government agencies, national and international data users, as well as members of the Malawian public. It also sought to introduce modelling and to develop associated capacity. The Overall Goal and Objectives were as outlined below:

Goal:

- to contribute to poverty reduction and increased welfare of the population of Malawi by efficient fact-based policy planning in order to implement the Malawi Poverty Reduction Strategy Paper.

Objectives:

- to strengthen the National Statistical System (NSS) through strengthening the capacity of the National Statistical Office (NSO) for production of statistics, and

- to strengthen the economic and social policy planning capacity through strengthening the capacity of the Ministry of Finance (MOF) and the Ministry of Economic Planning and Development (MEPD) for mid and long term social and economic fact-based policy planning.

At the time initial support was provided to Malawi through Statistics Norway (SN), other donors were already involved in the ‘sector’. The support from Norway was intended, in part, to complement other donor investments.

## PHASE II - Capacity Building for Statistics and Planning (2007-09)

This phase was organized as two parallel projects with the NSO (Statistics Component) and MEPD (Planning Component).

Overall Goal:

- Contribute to improved policy making for poverty reduction and economic development.

Overall Purposes:

- Develop efficient and effective national statistical systems that compile and disseminate data according to international standards, and

- Production of data linked to monitoring of Malawi Growth and Development Strategy (MGDS) and Millennium Development Goal (MDG) targets, budget processes, impact evaluation, and the management needs of line ministries.

The Statistical Component, with NSO, had four components, with a three year budget of NOK 18,357,000 (USD $3.6 M), covering:

- Basic Economic Statistics

- National Accounts

- Poverty Statistics - Welfare Monitoring Survey, and

- Institutional Development of NSO

The Planning component, with a budget of NOK 7,725,000 (USD $1.5M), addressed:

- Macro-Economic Modelling and Analysis

- Gender Issues and Poverty Trends, and

- Institutional Development with MEPD/MOF

The overall budget, including reviews and annual meetings, was NOK 26,700,000 (USD $5.1M).

This phase sought to provide the information needed to implement the MGDS, which replaced Malawi’s PRSP in 2006, while strengthening national statistical systems. This phase of the project relied on technical cooperation between the Ministry of Development Planning and Cooperatives (MDPC, formerly MEPD), NSO, MOF, Economic Affairs Division (MOF/EAD) and Statistics Norway (SN) with a view to providing a basis for evidence-based policy decision making, to support maintenance of the system and to assist users to gain confidence using it.

## PHASE III - Developing The National Statistical System (2013-2016) and MEPD Macro Model For The Malawi Growth And Development Strategy (2012-2014)

The overall objective of this phase of support was to institutionalize the systems put in place in earlier phases and to ensure that they could provide input for national policy analysis. It was also intended to further experience with the systems established, enhance understanding of relevant systems, and provide appropriate training and simple guidelines.

This phase actually entailed two projects named below with their corresponding goal statements and expected results.

- Developing the National Statistical System (2013-2016)

This phase of the project started in March 2013 and will end in February 2016. During this period, Statistics Norway has provided a resident long-term advisor who is based in Malawi’s capital, Lilongwe, but spends a portion of his time in Zomba at NSO HQ. SN has also provided a visiting senior advisor on a 20% basis.  In addition, the project has provided funding for an NSS Secretariat based in the NSO which is responsible for implementing approved project activities.

Goals:

- to improve the ability of the NSS of Malawi to deliver high quality statistics, and

- to increase the use of statistics produced within the NSS in policy processes in Malawi..

Expected Outcomes were outlined in the project agreement as follows:

- Strengthening the NSS: a) Legal framework improved, b) operational framework improved

- Information Management Systems improved for statistical use

- Capacity Building – NSS staff (NSO and Statistical Common Service - SCS) sufficiently capacitated to manage the production of statistics for major sectors

- Advocacy – Increased knowledge and use of statistics by key users

- Sustainable funding mechanism ensured

- MEPD Macro Model for the Malawi Growth and Development Strategy (2012-2014):

Overall Goal:

- Strengthen the capacity in evidence based planning and timely production of policy analysis for policy makers.

Expected Outcomes:

- Government of Malawi (GoM) capacity in macroeconomic modelling strengthened

- Holistic and coordinated GoM approach to economic forecasting and analysis, and

- Enable GoM to meet with international institutions such as IMF, World Bank and other Malawi development partners on more equal terms.

# RELEVANCE

## Country Needs

Good statistics are important to any developing country to support planning processes and to contribute to accountability. The investments under the various phases of this project have been highly relevant to Malawi as they have contributed to more of an evidence-based approach to policy development, monitoring & evaluation and decision making, while building up capacity for the production and use of statistical information.  These objectives are mentioned prominently in the GoM’s ‘National Statistical System Strategic Plan, 2013-2017’.  Malawi is also a signatory to the 2004 ‘Marrakech Action Plan for Statistics’ (MAPS) which called for mainstreaming of strategic planning processes of statistical systems, with National Statistical Offices as the lead agencies.  Furthermore, support provided under the project is in line with the ‘Partnership in Statistics for Development in the 21st Century’ (PARIS21), and is complementary to support from the World Bank´s ‘Trust Fund for Statistical Capacity Building’ (TFSCB), among other donor initiatives.

As noted above, the first phase was designed, in part, to enhance the capacity of Malawi’s NSO to produce statistics for mid and long-term monitoring of the MDGs. The Phase III mid-term review noted that the capacity of statisticians in the NSO to produce statistics for the MDGs was “very good” and thus contributed to Malawi’s MDGs, including reducing poverty.  In Phase II, as noted above, project activities supported implementation of the MGDS, the government’s overarching planning document, while Phase III sought to reinforce or further institutionalize systems introduced in the first two phases and to advance national planning and accountability.

Support from Norway has been seen as particularly valuable and relevant, in part since it has helped address capacity constraints in areas that donors haven’t traditionally supported in Malawi, such as economic statistics.  Norwegian support has also focused more than other donor support on strengthening Malawian systems as opposed to funding specific survey work of interest to donor agencies.

The Phase I Final Report also commented on the issue of relevance as follows: “The project has maintained the relevance as defined by needs and concerns as expressed by the project objectives. Capacity, both in terms of trained staff and ability to deliver information relevant for, and demanded by users of statistics, has been strongly increased. It should be noted that an important element of “capacity” is also that users trust the statistical agency’s ability to deliver high-quality and relevant data in a timely manner. Phase 1 of the project has greatly contributed to enhance the reputation of NSO among its peers in the Malawi government sector.”

## Norwegian Priorities

Malawi became a Norwegian priority country for its development co-operation programming in 1997. The first Malawi-Norway MoU focused on education, health, agriculture and democratic institutions.  In 2000, when renewal of the first agreement was under consideration, Statistics Norway met with Malawi’s NSO which led to the original idea for the first project based on Malawi’s needs related to its Poverty Reduction Strategy Paper.

In recent years (2008-13), Norway’s bilateral assistance to Malawi amounted to NOK 2,568.0 million (USD $ 340M) (631.1 million kroner (USD $84M) in 2013 alone).  Priority areas of investment presently include: Agriculture and Food Security, Cultural, Environment, Climate and Natural Resource Management, Gender & Equality, Education and Health.  Norway has also spent over NOK 60 million (USD 8 million) on enhancing the capacity of Malawi’s statistical systems since 2004.

The recent Cashgate scandal unearthed significant irregularities in Malawi's state payment system. A special audit report revealed that between April and September 2013 approximately USD 15 million had been stolen. Following that, Norway and other donor countries froze disbursements of budget support and imposed strict conditions on development cooperation funds.  This has had a huge impact on the GoM as approximately 40 per cent of its budget has been donor-funded in recent years. Malawian authorities have developed an action plan to recover the funds and to restore the confidence of Malawians and donors alike.  However, the percentage of funds recovered as of the time this report was being written was modest and government ministries and agencies continue to struggle with reduced allocations arising from this scandal.

## National Priority and Demand

Enhancing Malawi’s statistical capacity is officially a priority of the Government of Malawi.  The National Statistical System Strategic Plan, 2013-17, for example, notes how the passage of the new Statistics Act by the Malawi Parliament in May, 2013 would, among other things “build sustainable capacity for the production and use of statistical information in Malawi” (emphasis added).  The Strategic Plan also indicates that it will “further strengthen the statistical capacity and enhance use of management information available in line ministries and departments for statistical purposes” while acknowledging that this will require “support from and collaboration with a variety of stakeholders in the Malawian context”. The following additional points from the Strategic Plan further reinforce the declared importance of building capacity within the national statistical system:

- “The plan has a twofold focus. On one hand, the plan focuses on the production and dissemination of official statistics. On the other hand, it focuses on strategies and actions that will improve statistical capacity in Malawi. (emphases added)

- The Malawi NSS, like other statistical systems in developing countries, has limited capacity to produce and disseminate official statistics that meet user needs. This is due to factors such as inadequate coordinating mechanisms, supporting infrastructure, and statistical staff, and limited financial resources. With the ever increasing demand for statistics, it is imperative to enhance the organization and capacity of the NSS to make efficient use of resources; improve productivity and management of data; increase the availability of quality data and raise the profile of statistics.” (emphases added)

As discussed later in this report, the GoM’s stated commitment to enhancing domestic statistical capacity hasn’t always been matched by financial commitments from the government. Nevertheless, the policy and legislative commitments remain.

# STRATEGY AND DESIGN

## Internal Context of the Institution

Support from Norway in Malawi has focused on the National Statistical Office (NSO) and the National Statistical System (NSS). The NSO is the main government department responsible for collection and dissemination of official statistics in Malawi. The NSO was established under an Act of Parliament which mandates it to “collect, produce, analyze and disseminate official statistics (data) for concerned institutions or bodies to make sound evidenced-based decisions.” Its activities are guided by a Strategic Plan (current version is its second) and among its major activities are the Population and Housing Census, Demographic and Health Surveys, annual surveys to update social indicators used to report on the MGDS and MDGs, Integrated Household Surveys conducted every five years, economic statistics and National Accounts. The NSO is also responsible for coordinating the NSS.

The NSO is headed up by a Commissioner who reports to the Minister of Finance.  The Commissioner is empowered to endorse statistical information from line ministries as official upon certification of its quality. The NSO itself has approximately 300 staff, about 40 of whom constitute its professional cadre. NSO is headquartered in Zomba, the colonial capital which is a 5 hour drive from the political capital of Lilongwe. NSO has five main Divisions at its headquarters: Economics, Agriculture and Natural Resources, Demographic and Social, Publications and Finance and Administration. It also has three regional offices in major urban centres around the country: Lilongwe, Mzuzu and Blantyre.

NSO is heavily reliant on external funding with 70% of its activities being funded by donors. Much of that funding is directed towards specific surveys which means there is a risk that activities are guided as much by the wants of external actors as those of the agency itself.  NSO gained somewhat greater autonomy with the passage of the Statistics Act in 2013, but efforts since 2007 to achieve semi-autonomous status, consistent with other such entities in region, have not succeeded. Achieving such status could mean, for example, that NSO would report to a Board or Council (rather than the Ministry of Finance - MOF), set its own salaries, and undertake studies to garner revenue for the agency.

The 2013 Statistics Act established the NSS and, according to the NSS Strategic Plan 2013-2017 empowers it to “raise public awareness about the  importance and role of statistical information; collect, process, analyze and  disseminate quality statistical data and information in a coordinated and timely  manner; promote the use of best practices and international standards in statistical  production, management and dissemination; promote the use of statistical  information, particularly for evidence-based policy design, monitoring and evaluation and decision making; and build sustainable capacity for the production and use of  statistical information in Malawi.” The statistical units in line Ministries which are part of the NSS are normally situated in their Planning Department and are run by Statistical Officers from NSO assigned to the Ministry under the NSS framework.

## Planning Process and Capacity Needs Assessment

During the planning stage for Phase I of this project, Malawi had, as noted, just begun work on its poverty reduction strategy. This meant that the government had a need for quality statistics to support relevant planning and monitoring processes. Around the same time, Malawi, along with other members of the international community, had committed to the Millennium Development Goals which further reinforced the need for better integration of statistics and planning.  These imperatives drove the process which led to the design of the first phase of this project, led by the Ministry of Development Planning and Cooperation and NSO, each of which also saw the project as an opportunity to enhance their own capacity. Statistics Norway assisted in the design of the project bringing strengths in, among other areas, national accounts and macroeconomic modelling.

Before project start up, Malawi’s Ministry of Finance and the Reserve Bank of Malawi (RBM) had already laid some of the foundations for work on the national accounts estimation process.  However, there had been less institutional collaboration on statistics and planning in Malawi’s social sector and in relation to poverty reduction. This led to a greater focus early in the project on statistical and planning capacity, although it was recognized that support would be needed as well eventually to enhance institutional collaboration.  Project proponents anticipated that strengthening institutional collaboration would be a longer term process, thus the early calls for a multi-phase project. At the same time, other donors were offering support in the area of statistics so there was also a recognition that Norwegian support would have to be mindful of and complementary to these other initiatives.

As alluded to above, when the renewal of the first three-year agreement on development cooperation between Malawi and Norway became imminent, the head of the International Office of Statistics Norway met representatives from NSO at a conference in Lusaka. Records of subsequent contacts underlined how the project ideas which emerged from the meeting were linked to the PRSP. SN advised that this would fit well with the key points of the new Norway-Malawi MoU, which was focussing at that point in time on good governance, HIV/AIDS, general health sector support and macroeconomic stabilization.

After the initial meetings between SN and NSO, a fact-finding mission to Malawi was undertaken by SN late in 2001. This led to the first outlines of the project proposal. Subsequent steps included a visit by six Malawian representatives to Norway to work with SN colleagues on the details of the project plan and to garner input from a Norwegian consultant.  These two undertakings led to greater familiarization amongst the various institutional actors involved and refinement of the project idea.

SN undertook a second mission to Malawi in 2002 to further fine tune the project proposal with NSO. The TORs for the mission called for consideration of the inclusion of more Norwegian institutions in the project in order to strengthen it in specific substantive areas, e.g. public financial management, agriculture, health.  Malawi’s Department of Economic Affairs (EA) in the Ministry of Finance was also brought into the process. The Phase I mid-term review (MTR) described the proposal that followed as “a very thorough document”. Nevertheless, Norwegian authorities subsequently called for significant cuts in the proposed budget which included dropping certain provisions such as funding for the proposed, partial re-location of NSO’s HQ from Zomba to Lilongwe, and cutting back on the data bank and dissemination activities.

After further reviews and exchanges with the GoM, and other donors, an Appropriation Document was approved by Norad in April, 2003 and a project agreement was signed in July, 2003.  The significant delays experienced in the initial planning process were attributed to various factors, including extended internal reviews (including deliberations on the budget cuts), as well as external consultations. The Phase I MTR further commented on “allegations that the in-house interest of the SN pushed some sophisticated policy research components of the project much further than warranted, but we find that this appears unsubstantiated”. They further concluded that the proposal “bears the imprint of a good operational plan which is clear in its objectives and where the activities follow logically from the analysis of weaknesses”.  One weaknesses that was noted though was the absence of any evaluation throughout the process on the issues of sustainability and risk.

Further regarding the planning process, the Phase I MTR commented rather critically on the “basic asymmetry between the Partner (the Malawian institutions) and the Norwegian cooperation institution (SN)”.  The authors noted: “it is fairly clear that SN has been on the offensive in conceptualising planning and preparing the programme document, although the latter is supposed to be “the Partner’s strategy”.  The major input from the Malawian side has been a paper seemingly prepared at great haste right at the beginning of the process. Although SN loyally tried to follow the ideas from the Malawian side, it is plain that the overwhelming capacity and experience of SN has tended to level alternative ideas that the Malawian partner may have had.”  Similar sentiments were offered in the appraisal document prepared by Norad in 2007 for the second phase of the project. The authors of that report indicated that “Malawian ownership of the project should be made more specific (with) a stronger focus on the Malawian context.”  Following from that assessment they recommended that further need be done in terms of “assessing the national users’ capacity in terms of human and financial resources.”

As far as the review team was able to determine, there was no formal capacity assessment in advance of Phase I of the project. In fact, the Phase I final progress reported “staff assessment and training plans have been postponed to Phase II of the project.” The Phase II proposal appraisal also noted the lack of “an institutional plan and human capacity development plan” for NSO as well as MEPD, suggesting no capacity assessment was undertaken in advance of that proposal being finalized. However, in 2006 a situation analysis was undertaken with the intent of assessing the capacity of the NSS to “produce and use statistics and the enabling environment for production and dissemination of statistics,” although it wasn’t clear to the team how that analysis was used to inform capacity development strategies or interventions.

There have been other specific initiatives to review capacity needs of relevant actors, including recent training needs assessments by NSO, the Functional Review of the NSO and NSS in 2010, however, the focus has tended to be on the training needs of individuals or specific new positions required, with less attention to broader organizational issues or systematic reviews of the National Statistical System as a whole. It also wasn’t apparent that any of the assessments have explicitly taken into account enabling environment issues of potential influence, e.g. the impact of low public service salaries on post-training staff retention. One respondent did contend though that the process of developing the Strategic Plans did provide opportunities to address capacity issues, although they were not addressed to any significant depth in the actual documents.

The 2013- 2016 phase of the Development of National Statistical Systems project did initiate work on a Quality Assurance Framework.  There were some delays in the start-up but early steps included conducting a Quality Self-Assessment based on the National Quality Assurance Framework (QAF) checklist developed by the UN Statistical Division. This was done with support from Statistics Norway with the intent of prioritizing interventions to improve quality in NSO and eventually having a QAF for statistics in the country.

In terms of Norway’s role in addressing capacity issues, the review team was told that Norad conducts appraisals of project proposals and reviews all agreements. The appraisal of Phase II, for example, offered specific comments on the need for better capacity assessments and plans. However, Norad doesn’t have any field presence to follow up on such issues and no longer has the Institutional Capacity Building Advisor position it used to have at headquarters to offer ongoing advice on such matters.  And beyond the comments referred to above, the review team was told that advice from Norad tends to be technical or sector-based advice more than on crosscutting issues such as capacity building.

## Evidence Base

The review team was made aware of previous and concurrent efforts to address capacity issues in the statistics sector in Malawi which would have informed interventions funded by Norway.  A project with the African Capacity Building Foundation (ACBF) in the late 2000s, for example, was supposed to identify capacity gaps in the NSS and ways to resolve them, in part, by enhancing coordination of all stakeholders. However, the review team was not able to access the document and 10 years later, coordination remains a challenge, including with and among donors. However, many of the issues highlighted in the 2009 Paris21 Peer Review of NSO have been acted upon.

The most recent NSS Strategic Plan calls for a mid-term evaluation to “assess progress, lessons learnt and to make necessary adjustments for the second half of the plan”. It also calls for a needs assessment of the NSO’s proposed Statistical School in 2013 and a training needs assessment for the NSS in the same year leading to new curriculum and skill development for “all NSS staff” and improved infrastructure to support the NSS.  While the preceding suggests a fairly intensive approach to assessing capacity needs in the Malawian context and garnering evidence for programming decisions, feedback from interviews gave a sense that CD interventions were often driven more by advocacy for specific training or workshops or were in response to opportunities provided by external funders rather than being driven by systematic assessments of needs.

Having said that, SN, through its Division for Development Cooperation, came to this project in Malawi with years of experience in other developing countries (e.g. Angola, Eritrea, Uganda, Pakistan, Botswana, South Africa and China) which would, presumably, have provided a base of experience or evidence to inform programming decision and approaches in Malawi.

## Theory of Change

The project support offered by Norway was not based on an explicit Theory of Change (ToC) but did rely on results frameworks, with risk assessments. If a ToC existed though, it might have been expressed (in brief) as follows:

- Strengthening capacity of individuals, and enhancing systems and selected organizations in Malawi, while improving the enabling environment for statistics (e.g. 2013 Statistics Act) will improve the quality and consistency of statistics produced and used by the GoM which will, in turn, enhance evidence based planning which will, in turn contribute to the realization of higher level development objectives, such as poverty alleviation.

However, an implicit  ToC, such as this, would have been based on assumptions about the strengths or potential of certain institutions, political support for/recognition of the importance of statistics, and assumptions about ongoing financial support for the statistical system in Malawi. Several of these assumptions have not proven to be sound which has meant that Malawians and Norwegians have been challenged to ensure long-term sustainability of results arising from current (and past) investments.

## National Ownership

Malawian stakeholders involved in statistics, including the current leadership at NSO, have had a high level of commitment to the project support offered by Norway. Over the various phases, project activities have, by and large, been supported actively by Malawian partners, based on an interest in enhancing statistical capacity and performance of the NSO, the NSS, and the government more broadly. However, capacity constraints and weaknesses in government have sometimes limited Malawians from taking stronger ownership of statistical reforms. And as discussed elsewhere in this report, significant dependency on donors in this area has also risked undermining effective national ownership.

The 2006 Phase I MTR acknowledged the potential impact of weak government capacity on national ownership, commenting somewhat critically as follows: “The problem is …. that an attempt at externally resourced capacity building in the areas of statistics and macro modelling that is per se well directed and needed is made difficult by the general decay in the Malawian administration and the presently adopted donor “ideology” that aid programmes will be run within and by the Partner country administration.  Since all indications are that it will be a long time before the Malawian system works with reasonable efficiency, one may ask whether there is not a case for the donor to consider temporary solutions that may not be totally in line with the present “ideology”.”

The same MTR highlighted some of the problems of sustaining a sense of ownership in what they described as an ‘asymmetric’ partnership.  As the review noted: “Statistics Norway is an organisation where the research department alone has 100 staff, whereas the entire NSO has a staff of some 350. A better appreciation by aid authorities of the different strengths of the two parties and an attempt to beware of biases that this could lead to would have been desirable.” Norway has tried to be mindful of that potential for asymmetry, while striking a balance between offering timely operational support and advice, but not losing sight of the longer-term objective of ensuring reforms are led and sustained by national authorities with the capability and commitment to do so.

Over the course of the project, mechanisms have been put in place, e.g. the NSS Steering Committee, new legislation has been passed (Statistics Act, 2013) and a new Development Cooperation Strategy has been agreed to which increase prospects for effective ownership, but the challenges remain in a context of continuing administrative fragility and under financing of statistical activities by the government.

## Donor Fit

The ‘donor fit’ in this project has been seen as a good one in various respects.  Several aspects of Norwegian support that have been particularly valued include the focus on longer-term needs of NSO/NSS (vs just supporting specific surveys), provision of support in substantive areas not usually attractive to donors, and Norway’s valued role in donor coordination.  Norway has also been attentive to practical needs in Malawi’s statistics sector, e.g. procurement of IT equipment (“state of the art”) which has made a notable difference in terms of the efficiency of statistical systems. In addition, Norway was described by some respondents as more flexible than other donors.  The latter is valued particularly as Malawian actors struggle for continued support in the aftermath of Cashgate.

The ‘downsides’ in term of the fit relate mainly to the appropriateness of some of inputs from the Norwegian partners.  In several cases, Malawian respondents suggested that greater care could have been taken up front in ensuring the appropriateness of systems or approaches being advocated by the Norwegian partners. This ‘technology transfer approach’, seemingly without systematic consideration of its appropriateness in the Malawian, resulted in several cases of short-term adoption of approaches that either had to be dropped or modified. Norway also paid for expensive software licences without getting assurances that the GoM would be prepared to cover the annual costs after completion of the project.

On balance though, the support from Statistics Norway has been highly valued by Malawian partners and the overall donor fit has been viewed in positive terms.

# IMPLEMENTATION AND MANAGEMENT

## Implementation Arrangements

The implementing institutions in Phase I of the Institutional Cooperation Project were the Ministry of Economic Planning and Development, the Economic Affairs Division of the Ministry of Finance and the NSO. The NSO was responsible for the statistical part, while MEPD and EAD were responsible for the planning part. As per the agreement between the two governments, MoF represented the interests of Malawi and had overall responsibility for ensuring successful implementation, while project activities took place mainly within NSO and MEPD.  Further under the agreement, Malawi entered into contracts with the NSO and MEPD.

Administrative responsibility for the project ‘on the ground’ in Malawi rested with GoM. The MoF had a Project Coordinator, but a formal Project Management Unit was not established within the Ministry, possibly since most of the activities were undertaken in NSO and MEPD. The Phase I mid-term review flagged four areas where it suggested administratively the project was falling short: the failure by the NSO to reflect the grant in the annual budget for the first programme year; failure to apply the granted duty free status to some imported goods at an early stage; the budgets were not well linked to the declared objectives and outputs, and; the accounts weren’t structured along the lines of the budgets, objectives or outputs. Finally, the MTR questioned whether Malawi had provided sufficient local personnel to work on the project, e.g. on the National Accounts and modelling components in particular.

Annual meetings during this early phase were held with representatives of Norway and Malawi to: review progress, discuss possible revisions to plans and budgets, possible (in Project Agreements)extensions or new components/activities, approve work-plans and budgets, and discuss issues of special concern. Malawi had responsibility for preparing work-plans, with budgets etc. for consideration at the Annual meetings.  The Phase I MTR noted that “documents prepared for the meetings have not conformed completely to the format set out in … the Agreement” and minutes have been delayed.

Under the Developing the National Statistical System component (2013-16), NSO has been the designated implementing agency with responsibility for planning, implementation, reporting and monitoring. As per the project agreement, they were also expected to enter into a cooperation contract with Statistics Norway regarding technical advice, including a Long Term Advisor, to support development of the National Statistics System.  Regular Annual Meetings under this component are chaired by Malawi.  Under the project agreement, Norway was also given responsibility to act as the lead donor on behalf of DFID as a partner to the agreement. Funding under this component was provided for one part-time NSS Coordinator, one full-time Assistant NSS Coordinator as well as a full-time Secretary. Plans were set in motion to hire an additional Assistant Coordinator but that had not been completed before the end of the last reporting period.

In terms of government systems supported through the project, regular NSS Steering Committee Meetings have been organised in recent years focusing on priorities such as the draft NSS Strategic Plan 2013-2017, progress on statistical activities across the NSS, and the implications of the new Statistics Act for the work in the line ministries. Over time, increasing emphasis has been placed on ensuring the participation of Directors of Planning from the line ministries on the committee.

Regular Donor Coordination Meetings have also been organised, e.g. to consult on the draft NSS Strategic Plan and to discuss resource mobilization for undertakings such as the Welfare Monitoring Survey (WMS). Other more informal meetings have been held to ensure development partners are aware of developments in the statistical field and to solicit their feedback, as appropriate.  In addition, ad hoc Technical Working Committees have been established and organised to address technical issues, e.g. poverty measurement and the design of the WMS 2014 questionnaire.

Donor coordination has been an important issue in the context of support for the statistics ‘sector’ in Malawi.  Many donors are presently or have previously been engaged with either NSO or NSS.  The European Union, for example, has offered support in the area of trade statistics, while also supporting installation of software and advanced training (MA level) through Chancellor College. UNDP doesn’t currently have a statistics project in Malawi but has supported NSO on the 2014 MDG survey, as well as the Integrated Household Survey (IHS) and Demographic Survey.  Ireland has been providing scholarships for Master’s level students to study in Ireland and has worked with the Department of Nutrition, HIV, and AIDS (DNHA) on a micro-nutrient survey. DFID’s biggest investments have been on the IHSs and strengthening of NSS.

The challenge, in brief, is that donors are supporting lots of good ‘activities’, but it is not well coordinated. The NSS Strategic Plans had called for the establishment of a donor coordination committee which was done in 2009. However, for some donors, their interest is in supporting specific survey work reflecting their particular priorities.  As one interviewee commented: “Lots of donors are doing one off surveys”, i.e. ad hoc surveys with limited long-term support to NSOs. Another respondent said “despite efforts to bring donors together, everybody is taking a bite out of NSO”.  As a result, support is dispersed and while there are rhetorical commitments to improve coordination, a variety of issues, from different funding cycles to varying substantive priorities have so far limited coordination, despite the efforts of Norway which is currently the lead in Malawi on donor coordination in the area of statistics.

Another challenge is ensuring Malawian leadership in coordination which has proven to be difficult so far, partly because of its own capacity challenges but also because of the unwillingness of donors to ‘be coordinated’.  The Cashgate scandal has further limited donor willingness to support a ‘single program’, even if they could agree on what that would entail. Linked to the latter is a wavering confidence among donors arising from some of their investments in this area, including concerns with what has been described as a ’DSA culture’, budgets for proposed initiatives which were described to the review team as “loose” and financial claims which are frequently questioned, or eventually deemed ineligible.

In the mix of donor support, Norway has done more than others to focus efforts beyond individual surveys in order to support longer-term capacity development. However, they, as well, have had their challenges in coordinating donors and in some of their own investments, e.g. having to put a pause on specific initiatives due to “irregularities”.

A promising development though on the donor coordination and harmonization front has been the recently produced Development Cooperation Strategy for Malawi 2014-2018. This is the second such document in Malawi arising from the international Aid Effectiveness dialogue, building on the same key principles, e.g. enhancing ownership and effectiveness.  Flowing from this, the GoM is trying to engage donors more on the government’s agenda, although as one government official noted, it’s not always easy as the donors “always want us to do things a certain way”. Donor coordination support also tends to be focused more on technical rather than systemic support. Nevertheless, it was suggested that the new cooperation strategy document should be helpful as it provides space for more dialogue at the national level, including through sector Working Groups.  Working Groups have existed before, but reportedly lacked capacity, with the result that donors have tended to driven the agenda.

## Results Verification and Measurement

The review team did not have access to all progress reports or project agreements so it is difficult to offer definitive views on the issue of results verification and measurement.  However, the Final Report for Phase I does attest to the fact that that phase had a clearly articulated Goal, several Objectives and a series of expected Outputs which were to be measured by specific indicators, e.g. regular release of improved economic statistics reports, documentation reports published, reports published, annual reports published, model based economic policy reports published, databank established etc.. The expected results were presented in an annex to the report, in tabular form (Summarised Output Based Project Report for Phase 1) which included Indicators and Achievements. However, the table and the description in the narrative portion of the report focused largely on activities carried out or outputs achieved rather than the extent of progress against expected higher level results.

The Final Report for Phase II (Statistics Component) did report on Outputs and Outcomes. The Outputs reported on though were not always consistent with the Outputs in the Agreed Programme Summary in the project agreement signed by the project proponents. And the Agreed Programme Summary didn’t actually include expected results at the Outcome level so it wasn’t abundantly clear what expected Outcomes the Final Report was reporting against.

The 2012 proposal for the Developing the National Statistical System component (2013-16) did include a logframe, with indicators, but with results, once again, declared only at the Output and Goal level. The baseline for that component was established in 2014 which obviously precluded effective measurement of results from the beginning, although it should, in theory at least provide a basis for measuring change onward somewhat more systematically. However, the 2013-14 progress report indicated that “the outcome indicators will only be evaluated at the end of the project phase” without specifying why progress towards those expected results couldn’t be reported on earlier than that. Nevertheless, consistent with that assertion, the 2013-14 report focused on activities carried out during the reporting period by Activity Area. In light of DFID’s withdrawal of financial support for this component, the Norwegian Embassy requested quarterly reports be provided (financial and activity) which at least should provide more opportunities to verify results achieved at the output level.  The Annual Meetings also provide an opportunity to further assess and verify results, either achieved or in progress.

In sum, the project appears to have made serious efforts to account for results at the activity/output level. However, the apparent absence of logic models with clearly articulated intermediate or higher level results (below Goal level) has limited the ability to systematically verify progress towards those higher level results. Since Outcome level results should be reporting on changes in ‘behaviour or practice’ (as opposed to completion of activities) the reports were thus not as strong as they could have been on aspects such as capacity results being achieved at the institutional level, or even changes in behaviour or practices arising from training efforts, for example.

## Efficiency

According to the 2008 Phase I Final Report for the Institutional Cooperation Project, there were delays at the onset of the project due to unforeseen administrative problems, e.g. signing of the project agreement, opening up project accounts. The sub-component focusing on improved economic statistics and national accounts also experienced delays due to a shortage of qualified staff to carry out required tasks for the National Accounts work, and unavailability of relevant economic data from sources for the Annual Economic Surveys and Government Accounts. The staff shortage was reportedly addressed in the reporting period, although there were still concerns that staff could be drawn off for other responsibilities. The sub-component focusing on NSO’s capacity (individual and systems) as well as dissemination and improvements in the databank experienced delays in staff assessments and planned training, although plans for dissemination of data were expanded.

During Phase I, of the NOK 13,269,000 (USD $1.8m) funded for the three year period, all funds were spent by 2006 and an additional NOK 2,135,000 (USD $280,000) was provided to NSO as bridge funding to cover activities pending finalization of the Phase II agreement as there was a 7 month wait for finalization of the project document for Phase II.

A final concern raised with respect to efficiency, or value-for-money more specifically, had to do with the cost of Long Term Advisors in the project. It was widely recognized that a significant portion of the budgets have been allocated to cover the costs of these Advisors. And while there was a generally positive view of the role they played, questions nevertheless arose as to whether that was the most cost-effective use of funds to support the needs of the NSO and NSS.

## Adaptation and Adjustment

A number of respondents characterized Norwegian support as flexible and adaptive. In the work on the macro model for the MGDS, for example, the annual updating of the Supply and Use tables was deemed to be too ambitious in light of NSO’s limited capacity.  It was thus agreed that the tables would be prepared every five years and information for the intermediary years would be by interpolation.  It was further agreed with MEPD that SN would provide technical support to adapt the input from the National Accounts to the model.

The Decision Document for NSO – Developing the National Statistical System - Phase II noted how exchanges with NSO on challenges and progress are “good and open” based on their history of engagement with the Norwegian embassy and SN. The document further noted how SN had been flexible in accommodating NSO’s needs, including on matters such as foreign exchange shortages.

The Final report for Phase I of the Institutional Cooperation Project noted how the last 6 months of the project had initially been planned as part of Phase II, but was eventually considered an extension of Phase 1 which “due to great flexibility from the Lilongwe Embassy” allowed for smooth transition from the first to second phase.

In some instances, Malawian stakeholders contended that Norwegian partners had been too insistent on a particular approach or methodology, and while that may have resulted in some delays, Malawian concerns were usually accommodated eventually. In at least one case, that entailed abandoning the approach initially advanced.

# RESULTS

## Short- and Medium Term Results

This sub-section of the report highlights a selection of short and medium term results from various phases of the project.  In so doing, it offers some sense of the achievements realized with Norway’s support since 2004, albeit mainly at the output level reflecting much of the reporting, as noted above.

- Institutional Cooperation Project (Phase I, 2003-2007)

The Final Report for this portion of the project (dated April, 2008) referred to the following results for its various components:

National Accounts (NA)

- New national accounts figures were compiled with integrated annual Supply and Use Tables (SUT) in current and previous year’s prices for 2002, 2003, 2004 which were released to MEPD for the macro-economic model.

- Preliminary National Accounts figures for 2005 and 2006 were compiled and released.

Annual Economic Surveys (AES)

- The project supported the AES for 2003, 2004 and 2005 with the data being used in the SUT.

MPRSP Poverty & Social Development Statistics

- The project supported the annual Welfare Monitoring Surveys 2005 and 2006.  SN support was required onward in calculating poverty estimates.

- The results for WMS were disseminated at a workshop and were also made available on CD-ROM

- Support for the annual WMS enhanced capacity of NSO in social statistics.

NSO Activities

- Support from Statistics Norway focused on complementing cooperation by UNICEF and UNDP on a social statistics database (MASEDA) by providing a mapping module

- The latest version of MASEDA was launched and training conducted targeting Monitoring and Evaluation officers in the districts, sector ministries (these activities were funded by UNICEF and UNFPA).

- Institutional Cooperation Project (Phase II, Statistics Component, 2007-11)

The end of phase report for this part of the project highlighted the following ‘Outcome level’ results, among others, in the components below:

Basic Economic Statistic

- New Business Information Register set-up which will be capable of receiving data from other registers

- Annual Economic Survey data much more reliable than previously leading to improved NAs, and better data for the Economic Statistics division

- On-the-job training and short term missions built capacity and confidence of Economic Division staff

National Accounts

- NA figures more reliable than before and provide better basis for the economic policy

- GoM has better basis for engaging the IMF in bi-annual meetings

- Higher quality NA improves public confidence in NSO

- NA provides more reliable input-output tables for MDPC macro model

Poverty Statistics

- WMS planned with good quality; minimal SN support.

- WMS results widely used by GoM and international organizations.

- Annual WMS based NSO poverty estimates used in national planning and public discourse

- WMS related on-the-job training has built capacity and confidence among NSO staff

Institutional Development of NSO

- Improved management at NSO

- Increased NSO awareness of the need for in-house training, as well as formal academic training and foreign Technical Assistance

- Better understanding within NSO re importance of modern IT tools and how it can contribute to strategic planning

- NSO willing to take more responsibility for cooperation with other members of the NSS

- Developing the National Statistical System (2013-2016)

Below are some of the key results (Output level) reported in the latest available progress report (March 2013 to 31 May 2014), by component.

Strengthening the legal and operational framework of the NSS

- Information was provided to Cabinet and Parliament for approving the Statistics Act (activity mostly carried out in previous phase).

- NSS Strategic Plan 2013-2017 prepared and approved pursuant to a consultative process which generated plans reflecting the needs of different sectors.

- Work started on Quality Assurance Framework with a focus on self-assessment and tailoring to Malawi’s specific challenges

Improvement of Management Information Systems

- One sector review was carried out. Ministry of Labour asked the NSS Secretariat to carry out a review of its plans for setting up a Labour Market Information System (LMIS).

- Ministry of Agriculture and Food Security finalized a new Strategic Plan for their sector statistics, with support from NSO/NSS.

- Expansion of Management Information Systems to other sectors initiated.

Training and strengthened capacity for the NSS system

- Program for statistical certification and qualification for degree work at Chancellor’s College commenced, based on on-line material from Royal Statistical Society.

- Discussions held with Chancellor’s College re development of long-term training in statistics which would be open to NSS staff.

- One course conducted on survey design.

- Ongoing supervision and advice to statistical units on data collection, processing and dissemination procedures

- Ongoing participation in forums requiring statistical advice, e.g. dissemination workshop with UN Women and Oxfam on gender statistics.

Advocacy for statistics - Better knowledge of the potential use of statistics

- Advocacy materials produced and disseminated (ongoing), e.g. leaflet on the Statistics Act 2013 and two bulletins on statistics disseminated at the NSS SP 2013-2017 launch.

- One user-producer workshop involving users of statistics from Government ministries, departments, the private sector and development partners.

Ensuring sustainable funding mechanisms for the NSS

- Activities halted due to budget revisions associated with the withdrawal of DFID funds stemming from the Cashgate scandal.

In summary, the project has been reasonably successful in terms of contributing to meaningful results for NSO and NSS.  The Phase I MTR, for example, noted that despite ambitious objectives, the project has “fared remarkably well”. The Phase MTR II indicated that “progress was on track” in terms of new and higher quality statistics and capacity. And the Phase III MTR asserted that the results of long-term support are “clearly visible”.  Some of these improvements have been despite limited staff and/or competing duties or time commitments. Through the various phases, Norway has also been able to contribute to improved systems, e.g. for National Accounts, coordination of statistical production, improved training, producing indicators to monitor the MDGs and MGDS, although various sources indicated that the training offered wasn’t enough to respond to the shortcomings in the system. Various reviews and interviewees also noted ongoing concerns about timeliness, quality of data, and the challenges in retaining staff.

Specifically in terms of improvements in the institutional capacity of NSO and NSS, since there is no baseline for either, it is difficult to systematically assess changes in their capacity arising from project investments.  Nevertheless, reports, anecdotal evidence and interviews conducted suggest the following:

- Norwegian (and other donor support) has contributed to enhanced capacity in NSO and the NSS

- Capacity improvements are evident in various areas: improved skills and knowledge of statistical staff (e.g. in statistical methods, use of statistics for forecasting and planning), improvement of systems, and better infrastructure

On the other hand:

- NSO and NSS partners have lost staff who have benefited from training as they have become more employable in better paying positions (often outside of the public service). As one respondent stated on the latter point, “It’s hard for NSO/NSS to compete”.

- Links between NSO and line Ministries still need strengthening despite efforts to enhance cooperation and collaboration

NSS members, such as MEPD, have also benefited from Norwegian support, including the support to NSO to improve data for use in MEPD forecasting. NSO developed input-output data (data from enterprises, SUT etc.) which was provided to MEPD for forecasting and economic modelling.  However, concerns were raised with the review team regarding the macro-economic model advanced with Norwegian support.  According to some respondents, not all of the economic modelling was working as planned, due, in part, to data gaps or delays in receiving data. Some Malawian partners expressed concern that the model was too complicated and the process for adopting it was not ideal. According to Norwegian partners, Malawian counterparts were involved in the development of the model with an initial focus on a more aggregated model before a joint decision was made to develop a more disaggregated model. Associated concerns raised had to do with the turnover of technical staff at MEPD which made it difficult to orient new staff or get them up to speed, and the cost of the software licence (and how it would be covered after the end of the project).

In terms of negative effects of donor interventions, this report has already highlighted some of the potentially distortive influences of donor-funded activities (not necessarily Norway specifically). The latter have included funding specific activities, e.g. surveys, that have deflected attention away from NSO/NSS longer-term institutional development priorities, the ‘perverse incentives’ that fuel the existing ‘DSA culture’, and the ongoing risks of dependency associated with the high levels of donor funding for NSO/NSS activities.

## Sustainability

The plans for the various phases and components of the statistics projects in Malawi funded by Norway have not always been clear on the issue of sustainability, including capacities and enabling conditions required to ensure sustainability of project results.  They have also not been clear on exit strategies. The Phase I final progress report (2008) suggested that “Transfer of competence and consolidation of sustainable capacity requires a horizon of at least 8-10 years”. Seven years later, NSO has just submitted a proposal to Norway for a Phase IV, which presumably will be advocating support up to 2018 which would mean, if approved, Norway’s investments would stretch over a period of 15 years.

Further on the issue of sustainability, the Phase I MTR commented: “A fairly remarkable feature of the whole project conception and planning process – including preparation of project proposal, appraisal, appropriation document and agreement - is the absence of evaluation of sustainability and risks.” (emphasis added) The same report noted the importance of being mindful of several issues:  “the professional strength of project personnel and the organisational framework in which they work.” The Phase II MTR picked up on this theme highlighting the need to strengthen the “organizational aspects” in support of sustainability and to focus more on long-term development rather than “short-term fixing”. Related aspects touched on in a Phase III progress report included NSO’s capacity to train its own staff leading to a view of the Statistical School as a “crucial catalyst for project sustainability, as a way of maintaining and upgrading NSO competence”.

During the second phase, discussion about exit strategies seemed to dwell more on the issue of time frames, i.e. when to exit, and when it was apparent that the project would extend beyond the originally planned two phases, the talk shifted to “a flexible exit strategy”.  Functionally for project managers, thinking increasingly about ‘exits’ led to declarations of less emphasis on technical support, e.g.  for standardized household surveys, and more emphasis on human resource development, the Statistics School and the program at Chancellor College.

Finally, it should be noted that SN did endeavour to support elements that would increase system sustainability. For example, they encouraged use of administrative data already complied by Malawian authorities that could be used for production of statistics. The intent was to limit reliance on donor-sponsored, and often cost intensive, large scale surveys. One example was relying on a simpler, less resource demanding approach to National Accounts. SN acknowledged that his has taken longer than originally planned while also suggesting that further progress would require support from other parts of the GoM.

# CONCLUSIONS AND LESSONS LEARNED

## Overall Conclusions

As suggested in the preceding sections, the Norwegian-supported statistics projects reviewed have been highly valued by Malawian stakeholders and have contributed to the overall goal of strengthening capacity for more of an evidence-based approach to policy development, monitoring and evaluation and decision making in Malawi. They have also contributed to Malawi’s capacity for the production and use of statistical information.

Respondents were positive about Norway’s leadership role in donor coordination and CD, including offering support in areas that other donors don’t and committing resources to long-term capacity issues while others focus more on specific survey work.

Key factors that have contributed to the successes realized through these initiatives include the commitment/ownership of key stakeholders, the quality of inputs offered by Norway and the duration of the engagement, although Malawi remains challenged to sustain some of the capacity and performance gains realized through the investments for a number of reasons.

## Lessons and Success Factors

The Influence of Contextual Factors in Capacity Development (CD) Processes

The context in Malawi offers a mixed picture in terms of its impact on CD processes relating to statistics.  On the positive side, as mentioned earlier, there is a generally high level of commitment to the reforms supported by Norway. This includes from the highest levels of officials responsible for statistics in the country. The project work has also contributed to the strengthening of mechanisms which should put Malawian authorities more ‘in the driver’s seat’ on reforms in this area.

At the same time, there are a number of contextual factors which will continue to challenge the implementing or sustaining of CD efforts in country. These include:

- the low level of support to NSO/NSS from the GoM (70% of NSO activities currently funded by donors) and associated risks, including continued dependency by the government on donor funds to pay for key statistical services and capacity building efforts.

- The lack of government funds for the sector also raises questions about the sustainability of current and prospective efforts to strengthen institutional capacity, e.g. the Statistics School or programs at Chancellor College which potentially have key roles to play in ensuring a continuing flow of new and upgraded skills into the sector.

- NSO’s status in the broader government system (relatively low) which may limit its ability to secure additional government funds or attain semi-autonomous status

- Low salaries in the Malawi public service which continue to encourage rent seeking behaviour while limiting the capacity of government bureaus to retain qualified staff, particularly after they have been trained to higher levels.

- Engagement of multiple donors in the area of statistics which has brought benefits but also risks pulling sector actors in various directions and diluting efforts to address longer-term capacity concerns.

A further overarching factor is the lack of confidence or trust which has arisen pursuant to the Cashgate scandal which has led donors to shift away from budgetary support and diminished their interest in common programs.

CD Strategies and Modalities

CD support offered by Norway has relied on various modalities:  Long/Short-term Advisors (although reliance on LTAs reduced as the projects unfolded), on-the-job training, software and infrastructure support, as well as attachments and study visits (to Norway and elsewhere). While a large focus has been on enhancing skills and knowledge of individuals, the inputs from SN did seek to strengthen repetitive production processes (e.g. AES, WMS and System of National Accounts - SNA) which yielded institutional benefits. Also as noted, SN offered advice on the establishment of NSO’s Statistics School, although by Phase III NSO was responsible for arranging courses and lectures on its own. In addition, Norway has supported development of a Diploma program at Chancellor College. The projects also included some ‘higher level’ CD investments aimed at influencing policies or legal frameworks, e.g. support for development of Strategic Plans, updating of the Statistics Act.

All of the preceding were seen as valuable in contributing to enhanced skills and/or performance. The most valued CD inputs were those that were seen as ‘practical’ and directly relevant to the needs of beneficiaries. This included knowledge and skill development (e.g. through higher level training), support for surveys and associated ‘learning by doing’, e.g. on AES, WMS, as well as infrastructure support, e.g. tablets which significantly increased the efficiency of data collection. CD inputs that were less valued were those that hadn’t been tailored sufficiently for the Malawian context, e.g. ‘technology transfer’ efforts that, as previously suggested, were advanced without sufficient regard to local needs/capacity.

Training opportunities were highly valued for various reasons, although it was widely recognized that it often increased prospects for staff moving on with the risk that there would be a net negative impact for the capacity of the institution involved. The NSO, for example, reported that it has lost approximately 10 professional staff in the last 5 years (“the cream of the crop”, as one senior NSO official said). Ironically, many of these moved on to donor agencies e.g. UNFPA, WFP, Paris21, and as they were highly skilled they were difficult for NSO to replace. Combined with slow recruitment processes, this has meant vacancies for long periods of time in key positions. Some modalities such as short-term training, or exposure visits, were also seen as important not only for the learning benefits but for how they motivated staff.  However, one Malawian respondent suggested that there is a need to go beyond training, e.g. to address organizational processes, while others expressed the need to deal with the “culture” of the public service.

Respondents were asked what different orientation they would recommend, if any, in terms of CD support, if the project was to be done over again.  Various responses were offered. Some recommended more focus on long-term training, e.g. university-based, early on to strengthen the HR base in relation to statistics, while other suggested more emphasis on south-south exchanges (without foregoing the option of Norway-based training or exposure visits to support specialized needs).  At the end of the day though, a majority favoured a mix of approaches/modalities, although it wasn’t apparent that assessments of the relative merits of different modalities, including ‘value for money’, were undertaken when considering the various options over the course of the project.

Institutional Collaboration

Institutional collaboration was the main mechanism for provision of capacity building support under the project. As noted above, it entailed provision of long-term advisors, expert visits, study tours, etc. Among the benefits flowing from this arrangement, according to respondents, were: the focus on trying to build capacity rather than “just doing surveys”, as well as the sharing of expertise (e.g. in technical areas and on how to run a statistical agency, such as the NSO).

However, several concerns were raised about the institutional collaboration arrangements, including: the high percentage of project funds earmarked for foreign advisors, which some suggested could have been used differently (at least a portion) to support Malawian needs; questions regarding the efficacy of certain advisors (e.g. individuals who were highly qualified technically, but not necessarily “best suited” in terms of training or skills transfer), and; the fact that Advisors did not come with significant funds, e.g. for workshops, which are valued by local partners.  Further regarding Long Term Advisors, it was noted that some didn’t have prior international experience and cross-cultural training was reportedly not part of their preparation. With those provisos though, most Malawians valued the idea of institutional collaboration with Norwegian partners, with one senior official suggesting that while the approach was “working fine, there was simply a need to improve the model”. Specific suggestions for modified approaches included more short-term vs long-term advisors, more openness to south-south exchanges, and better assessments up front when considering ‘technology transfer’ options.

Long and Short-term Advisors

The Advisors provided through the project have offered different types of support, as noted above, from technical advice on modelling to advisory support on the development of strategic plans and training programs, helping NSO to take more of a leading role on statistics within government, as well as coordination of Norwegian inputs in the sector. Short-term advisors have often been used for more specialized inputs, or in some cases follow-up on support offered while on long-term assignment in Malawi. (Note: several of the Long-Term Advisors had to cut short their assignments for health or family reasons.) The overall quality of inputs offered by Advisors though was generally seen as very good.

Respondents had varying views on the comparative advantages of long vs short-term advisors. Some preferred long-term advisors (3-5 years) with a clear view that Malawians would take over responsibilities after completion of the assignment. Others preferred short-term advisors highlighting that while long-term advisors may have specialized capacity or skills in one or two areas, reliance on short-term advisors opened up the possibility of relying on a wider range of skills/experience from a longer list of prospective advisors. With short-term advisors from SN there was also the possibility of accessing them electronically for long distance advice following their assignments. Yet others felt that it was important to keep open to a mix of short and long-term advisors to maximize responsiveness to evolving needs.

Slightly different perspectives were offered by different stakeholders on the role of Malawians in shaping the terms of the assignment and actual selection of the Advisors.  Most indicated that national partners were involved in the development or agreement on TORs, but the majority of Malawian respondents indicated that they had a limited role in the selection of Advisors, with most chosen from within Statistics Norway, although some stated that they had offered recommendations based on reviews of CVs. As one respondent suggested though, Long Term Advisors provided through the Norwegian partner institutions were usually based on recommendations from them (“not much back and forth”).

Strengthening Institutions

Two targets of ‘institutional strengthening’ support from the project, beyond NSO and NSS members, are worthy of mention. One is the Statistics School, which is, as noted, actually part of NSO. The ‘school’ is housed in a room at NSO HQ which is used for short-term training for staff from the various NSO Divisions. The Training Officer in charge determines training needs based on consultations with staff and organizes course accordingly. The review team was told that over 50 short courses were conducted over the past year. All training is presently done in Zomba but with an intent to extend to the other regional offices eventually.  The school has received some support from Norway, the idea being to draw on Norway’s model with staff teaching different courses. However, this has proven to be difficult given that prospective trainers from within NSO staff are already committed to other responsibilities which limits their ability to take on teaching duties. Attracting trainees at the designated times has also been a challenge, in part, according to some respondents, because staff prefer to conduct field work rather than attend training since the former allows them to secure allowances.  Questions were also raised about the sustainability of the Statistics School and NSO’s capacity to keep it going, although it appears that is what NSO wants.

Norway has also worked with Chancellor College in Zomba on development and delivery of statistical training. The College is presently in the process of introducing a Diploma in Statistics. Most of the ground work has been done and the intent is to start up either later in 2015 or early 2016. Previous attempts have been made to start up a program at Chancellor but did not succeed due to the demands on faculty time.  Nevertheless, there is a sentiment that the current attempt will succeed, in part due to what is seen as a growing demand for statistical skills, within NSS as well as the broader labour market in Malawi.  Presently, Chancellor College is providing Certificate courses through the Royal Statistical Society. The qualifications that the College can provide are seen as offering an extra incentive for prospective students as they would increase remuneration levels in their jobs. Public servants attending the Certificate program will also receive a small allowance, e.g. for books. The courses provided will build on an initiative with the University of Redding which developed courses for the Southern African Development Community (SADC) for universities in the region to adapt.

Malawian Perspectives on Capacity Development

It is evident from a review of key Government of Malawi documents that CD is often referred to, mainly as an objective of one investment or another, but strategies are rarely if at all clearly articulated. The MGDS, for example, is based on six main themes: Sustainable Economic Growth; Social Development; Social Support and Disaster Risk Management; Infrastructure Development; and Governance, with “Gender and Capacity Development” listed as an “additional theme”. The MGDS sub-section on capacity development reads as follows:

- Government recognizes the need to develop capacity at all levels for successful implementation of its development programmes. Government will, therefore, reorient and expand existing investment in infrastructure and equipment. It will also provide a conducive environment for the development of skills and knowledge to respond to the needs of the economy (italics added for emphasis). The key strategies include developing and strengthening human and institutional capacities, mainstreaming capacity development in all sectors and promoting effective performance management systems. (italics added)

The strategic elements highlighted in italics in this statement are quite appropriate, but once again, there is no road map or strategy for how those priorities will be addressed.

Similarly, the Strategic Plans for NSO and NSS both reference the need for ‘capacity development’, but as with the MGDS, without any significant guiding details.  Both of the SPs focus more on what each entity “wants to do” vs what they “want to be”, and what capacities and processes would be required to allow them to be what they “want to be”, e.g. in the case of NSO - a ‘semi-autonomous’ entity that is able to attract and retain highly qualified Statisticians to respond to the needs of government and others prepared to pay for statistical services.

CD is also identified as a priority in the NSS Strategic Plan, but as with the other documents referenced, it doesn’t contain an explicit overall CD strategy. Rather it primarily documents priority areas of activities. Furthermore, it does not appear to be informed by a shared or systematic analysis of capacity needs, constraints and opportunities at various levels – individual, organizational and systems.

Finally, the new Development Cooperation Strategy (2014-18) offers some ‘hopeful’ directions regarding development cooperation generally and capacity development more specifically. It posits as one of its 6 main objectives:  Ensure capacity building for effective and accountable institutions. It also underscores the importance of country leadership and ownership of development priorities, including capacity building efforts, and then jointly commits the Malawian government and donor partners to: a) collaborate in building critical capacities to ensure effective institutions and policies for sustainable development; b) ensure that Technical Assistance is demand driven and responsive to institutional and human resources capacity needs of Malawi, and; c) collaborate to improve capacities for domestic resource mobilisation. It also calls for “increased capacity building support” and “minimization of TA” which should “respond to capacity needs in institutions.”  In addition it urges scaled up support to improve national M&E and statistics capacities. The challenge, as with the commitments in the other declaratory documents will be for donors and the GoM alike to deliver, and to do so in a context of diminished trust and sometimes conflicting substantive priorities.

Roles and Competencies of Donors and Partners (National and International) in Supporting Capacity Development Processes

As highlighted above, NSO has a Statistics School headed up by a Training Officer who is a trained Statistician. The Training Officer’s role includes conducting training needs assessments, developing curriculum and conducting short-term training courses. Specialist Officers from NSO are called upon, as available, for delivery of training programmes.  NSO also works with other institutional partners to enhance their capacity to effectively utilize statistics or in the case of Chancellor College, to deliver accredited training programs.  However, based on interviews in country, it appeared that important Malawian partners, especially NSO, are highly stretched and thus limited in terms of their ability to effectively respond to existing capacity constraints. They are able to capably identify short to medium terms priorities, notably training needs, but they arguably lack a longer term institutional capacity vision.  Nevertheless, with donor support, NSO is contributing to specific initiatives which could pay dividends for the broader NSS over the medium-longer term, e.g. the Diploma program at Chancellor College, if they are ably supported, financially and otherwise. There may also be need to enhance strategic thinking among the leaders.

Norway’s support, like that of other donors, has been highly valued by Malawian partners.  As one NSO respondent indicated, “if we didn’t have donor support, we wouldn’t have NSO as it is today”.  Norway, and other donors, have generously funded a range of activities, many of which have already been noted in this report. However, Norwegian embassy staff in Malawi is overextended as their country program has grown significantly in recent years without any increase in staff.  And the staff professional responsible for the statistics ‘file’, including leading on donor coordination in this area, has multiple other responsibilities which preclude him from taking a more active role beyond ‘normal’ oversight and participation in activities such as the annual project meetings. Furthermore, the embassy doesn’t have specialized skills in statistics, or capacity development, so relies substantially on the Norwegian partners to fill that role. And the review team was told that Norad has capacity development guidelines, which are “good”, but they are not always known to staff or used widely.

Statistics Norway has a long history of engagement in international cooperation and has brought a high level of skills to the projects in Malawi. Many of the interventions they have supported have yielded positive results for Malawi, as described in earlier sections of this report.  If there is one ‘critique’ though of the approach, it is that it tends to be ‘technical’ in nature, and linked to that, occasionally supply-led, i.e. based on Norwegian ways of doing things. The suggestion arising from several sources was that it could be more ‘developmental’ in nature, including being more sensitive to the needs and limitations inherent in the Malawian context.

Specifically on the question of SN’s ‘competency to support capacity development processes’, several respondents, as noted above, questioned the ‘capacity development skills’ of some of the Advisors (as distinct from their technical skills and knowledge) which raises questions about the selection and preparatory processes for Advisors. The broader issue though is whether SN supported interventions are sufficiently informed by joint analyses with local partners of capacity opportunities and constraints in the ‘sector’  leading to strategies aimed at supporting not just ‘what works now’(potentially, or in fact) but ‘what can be sustained’ over the longer-term.  SN’s contributions to development of the Strategic Plans, for example, have been responsive to the latter dimension, but many incentives may favour a focus on short to medium term results, and the Norwegian government doesn’t seem to have pushed them to take a more rigorous approach to systematically addressing long-term needs, although Norway has been relatively more attentive to such matters than other donors.

Lessons Arising

A number of lessons have arisen from the experience with the projects discussed in this report covering the past 11 years.  Those lessons include the following, paraphrased from Final Reports of the two phases of the Institutional Cooperation Project:

Phase I:

- Demonstrating the ability to deliver policy relevant information to institutions, such as the Ministry of Finance, increased the demand for its output while also triggering national ownership and domestic funding.

- Combined training activities involving users and producers of statistics was valuable and mutually beneficial

- Institutional cooperation in the first phase started with provision of technical cooperation to  build  trust and confidence between partners, gradually moving towards other issues such as planning and management

Phase II:

- Annual repetition of standardized exercises, e.g. AES, WMS is effective for capacity building purposes and has helped to lay the foundations for NSO to take over without compromising quality.

- Adequate training is dependent on the presence of a Long Term Advisor to provide daily on-the-job support and to advise on specific issues. General courses are insufficient by themselves.

- Increased user demand can fuel development of new products, but also leads to the need for additional staff and/or training

- Under the “Institutional Development of NSO” component, there was a deemed need for a steady focus on the implementation of, and support to the central functions at NSO, in part due to donor funding being directed towards specific surveys and the fact that the focus on on-the-job training limited prospects for inter-divisional transfer of competence and establishing common practices.

- Reliance on donor support for specific surveys, leaves NSO vulnerable to reduced or limited funding from GoM.

- The small number of trained statisticians available for NSOs production of statistics is a current risk factor and a severe threat to long term sustainability.

- While NSO should be able to provide statistical support to other NSS institutions, it then faces the risk of spreading its specialized knowledge too thinly between the various parts of the system.

Final Comments

As one respondent suggested with respect to statistics in Malawi, “the ambition is high, but there are still gaps in capacity”.   Another external stakeholder indicated that it is difficult to have discussions on capacity issues in Malawi as priorities and interests vary amongst key stakeholders, and it takes time to build up trust. It is for that reason, he continued, that much of the focus has been on ‘activities’ that are directly responsive to pressing Malawian needs, rather than ‘bigger picture’ issues on which it may be difficult to gain consensus.

In terms of moving forward, several themes were prominent in the feedback from stakeholders in Malawi. First is a sense that NSO needs to take more of a leadership role on these issues. That includes bringing donors together, something that is recognized as not being easy. It also requires capacity, and NSO is, as noted previously, already thinly stretched to deliver effectively on its mandate.  Secondly, NSO needs to lay out a vision that donors can buy into – an organizational vision, not just a ‘work vision’ – one that is strategically clear, but practical as well, e.g. how to deal with key issues such as staff retention. NSO also needs to do a better job of analysing its own capacity needs and those of others in the NSS. Thirdly, in terms of approaches, it needs to look beyond training of individuals, with more of a focus on the outcomes of training but also the needs of organizations.

Donors also have to reflect on how they can most effectively support Malawi’s efforts to increase is statistical capacity and deliver more effectively on its requirements. At present, most would agree that the donor community investments in this area are disparate, often self-interested, put pressure on a system already under stress and are not likely to contribute in a meaningful way, as currently organized,    to sustained improvement in GOM’s statistical service.

Finally, while Malawi has made progress as a result of donor support, including from Norway, ranking now among the top placed countries in SADC with respect to statistics, other African countries, such as Rwanda, are making quicker progress in this area, and their experience should be examined to see if there are useful lessons that can be draw upon.  Whatever approach is decided upon (beyond what is already in the relevant Strategic Plans), goals should be realistic, well-defined and based on a clear understanding of the capacity constraints and opportunities in the Malawian context.

Annex 1: References

- Final Report, Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistical Office and Statistics Norway, 2003 – 2007, April 2008

- Mid-term Review of the NSO/MEPD/MoF Malawi-Statistics Norway Project, Final Draft 25.04.06

- Decision Document,  NSO – Developing the National Statistical System - phase 2

- National Statistical Office, Final Report,  Phase 2,  Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistical Office and Statistics Norway, July 1st 2007 – July 1st 2011, including Bridge Funding between Phase 2 and Phase 3, STATISTICS COMPONENT, March 2012

- Hallgrimur Snorrason, Patrick Chimutu, Mid-Term Review of the Cooperation Between Malawi and Norway in the Field of Statistics and Planning, 20 December, 2008

- Erlend Nordby, Thorn Oftedal, Norad, Economics and Public Administration Department, Appraisal of Statistics and Planning for Malawi Growth and Development Strategy – Malawi, January 2007-December, 2009

- Agreement between the Government of the Kingdom of Norway and the Government of the Republic of Malawi regarding development cooperation concerning Capacity Building for Statistics and Planning (Phase 2)

- Agreement between the Norwegian Ministry of Foreign Affairs and the Government of the Republic of Malawi regarding development cooperation concerning NSO Statistics for the Malawi Growth and Development Strategy - Phase 3

- Lars Lundgren, John Mataya, Barbara Wirth-Bauer (Norad), Mid-term Review, Statistics for the Malawi Growth and Development Strategy, Commissioned by the Royal Norwegian Embassy in Lilongwe, January, 2014

- National Statistical Office (with assistance from Statistics Norway,  Zomba and Oslo), Statistics for the Malaŵi Growth and Development Strategy - Phase 3, July 2011 to June 2014, November 9, 2011

- Agreement between the Norwegian Ministry of Foreign Affairs and the Government of the Republic of Malawi regarding development cooperation concerning MEPD Macro Model for

the Malawi Growth and Development Strategy - Phase 3, 2012

- Albert Caspers, Chinyamata Chipeta, Barbara Wirth-Bauer (Norad), Mid-term Review, Macro Model for the Malawi Growth and Development Strategy, Commissioned by the Royal Norwegian Embassy in Lilongwe, February, 2014

- Agreement between the Norwegian Ministry of Foreign Affairs and the Government of the Republic of Malawi regarding development cooperation concerning Developing the National Statistical System, June, 2013

- PROJECT PROPOSAL, Developing The NATIONAL STATISTICAL SYSTEM , 2013 – 2016, SUBMITTED TO THE NORWEGIAN EMBASSY AND THE DFID, October 2012

- Developing the National Statistical System, Progress Report for the period 1 March 2013 to 31 May 2014

- Ministry of Finance, Economic Development and Planning, DEVELOPMENT COOPERATION STRATEGY FOR MALAWI, 2014-2018, MAKING DEVELOPMENT COOPERATION WORK FOR RESULTS, Lilongwe, September 2014

- National Statistical Office (Government of Malawi), National Statistical Office Strategic Plan, 2012-2016, September, 2012

- Statistics for the Malaŵi Growth and Development Strategy - Phase 3, INSTITUTIONAL COOPERATION PROJECT PROGRESS REPORT, July 2013 to June 2014, National Statistical Office Components

- National Statistics Office, Government of Malawi, Country Report on Support to Statistics (CRESS), 2009-2014, April, 2012

- National Statistics Office, Integrated Household Panel Survey, 2010-2013, Household Socio-Economic Characteristics Report, November, 2014

- PARIS 21, Peer Review of Malawi National Statistical System, 26-30 January, 2009

- Ministry of Finance and Development Planning, Department of Development Planning, Malawi Growth and Development Strategy II, 2011-2016

- National Statistical System,  National Statistical System Strategic Plan, 2013-2017, November, 2013

- Ministry of Finance and Development Planning (Economic Planning Division & Economic Affairs Department) in consultation with RBM, Chancellor College and Statistics Norway, The Malawi Growth and Development Strategy II and beyond, A Project Proposal for an Institutional Technical Cooperation between the Ministry of Finance and Development Planning (Economic Planning Division & Economic Affairs Division), Reserve Bank of Malawi and Statistics Norway over a period from April 2012 to April 2014, Lilongwe, February 2012

Annex 3: scoring against questions established for the evaluation

| # Annex 2 Scorecard |  |  |  | National Statistical Office |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Score 1-4 where 1 is negligible or very low and 4 is high. If the question not applicable to project score n.a. | Score 1-4 for how important to success in achieving outcomes was presence or absence of factor (4 = essential; 1 = little or no significance) |
| Overarching Question | Detailed question | Scoring |  |  |  |
| 1) CD intervention Addresses a stated national priority in the recipient country (priority sector and/or the needs of a priority population) | Does the CD intervention address a genuine national priority? | Clearly stated and justified national priority scores 4. Is clearly not a priority scores 1 |  | 4 | 4 |
|  | Is this a politically Urgent priority | Scores 4 high-up the political agenda e.g. because of public pressure or fear of not dealing with it leading to political problem |  | 4 | 3 |
|  | Does the intervention address the needs of a particular priority population - How/why is this population a priority | Scores 4 if targeted towards a particular group with clear priority, e.g. the poor. Scores 1 if untargeted |  | 3 | 2 |
| 2) CD intervention Addresses a clearly identified capacity constraint that the country did not have the capacity to address itself and does not duplicate support being provided elsewhere | Capacity constraint identified and specified at national policy level - clearly a felt-need at national level | Scores 4 if a clear statement in a major national policy document. Scores 1 if only mentioned in catch all phrases |  | 2 | 3 |
|  | Sub-question on felt-need: Where did the original identification of the CD constraint come from? Was it first identified by national government, the institution itself or an external player? | Scores 4 if a clear statement in a major national government policy document. Scores 1 if only mentioned in catch all phrases or clearly donor inspired |  | 3 | 3 |
|  | Capacity constraint real and well specified but was not a felt need of the institution | Scores 4 if both the institution and the national government identified the constraint and considered it important. Scores 1 if was externally identified and then sold nationally |  | 3 | 3 |
|  | What are the largest capacity constraints in the sector Support does not duplicate work of others | Scores 4 if corresponds to the most important constraints with no duplication, scores 1 if constraint was not key and/or duplication of work of others |  | 3 | 3 |
| 3) CD intervention Addresses a priority for Norway | Addresses a priority for Norway | Scores 4 if a clear statement in a Norway policy document at time of project. Scores 1 if only mentioned in catch all phrases |  | 4 | 2 |
| 4) Competencies of donor and external implementing/TA partner (if any) | Was the subject matter area of the intervention one where the where the donor has strong competencies? | Scores 4 if high competency, 1 if no particular experience of area and no strong back-up from Norad or experienced partners |  | 2 | 2 |
|  | Does the donor know the country and institutional context well? | Scores 4 if knows well, 1 if little or no experience and knowledge |  | 4 | 4 |
|  | Does the donor know the target institution(s) well? | Scores 4 if knows well, 1 if little or no experience and knowledge |  | 4 | 3 |
|  | Does the external implementing partner know the target institution well | Scores 4 if knows well, 1 if little or no experience and knowledge |  | 3 | 4 |
| 5) Was the intervention designed with | Full involvement of national government | Scores 4 if high involvement. 1 if little or no involvement |  | 2 | 2 |
|  | Full involvement of target institutions | Scores 4 if high involvement. 1 if little or no involvement |  | 3 | 3 |
|  | Other local stakeholders | Scores 4 if there was wide consultation with non-core stakeholders and 1 if consultation was limited to the government and the institution. |  | 2 | 2 |
| 6) Was there a comprehensive capacity needs assessment for a) the sector/area of work and b) the institution. | Was there an initial comprehensive capacity needs assessment | Scores 4 if there was a comprehensive assessment. 1 if there was no assessment at all |  | 1 | 3 |
|  | Did later phases factor in capacity needs assessment type information. from earlier phases | Scores 4 if information was recorded and good account taken of that information |  | 3 | 3 |
|  | Was the assessment appropriate to the scale and nature of the intervention | Scores 4 if the resources committed to CD needs assessment were appropriate to the scale and complexity of the intervention. n.a. if there was no assessment |  | 1. | 1 |
|  | Were the findings of the assessment applied in the intervention | Scores 4 if there was good account taken of needs assessment data. n.a. if there was no assessment |  | 2 | 2 |
|  | Were national stakeholders appropriately involved in the capacity needs assessment | Scores 4 if there was appropriate involvement of all relevant stakeholders. Scores 1 if there was no involvement or no needs assessment |  | 1 | 3 |
| 8) Important context-specific factors for the CD intervention to contribute to its objectives identified and taken account of in design and implementation working with them rather than changing them if this is not the direct purpose of the CD or changing them if they are a direct impediment to CD achieving goals (e.g. trainees cannot do anything with their training) | National culture (e.g. hierarchical, male dominated, importance of tribal or party allegiances - much communication outside formal channels, importance or lack of importance of law and of formalised policies; Institutions have or do not have a lot of freedom) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis |  |
|  |  |  |  | 2 | 2 |
|  | Institutional culture (e.g. hierarchical/ command, consultative, consensus, units compartmentalised, networked, informal networks more important than structural relationships, bureaucratic (form filling), rule based) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis |  | 3 | 3 |
|  | HR systems and possibilities for advancement and reward | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis |  | 3 | 3 |
|  | Financial systems and budget allocation (e.g. budget not performance related, budget does not mean funds available, authority for expenditure) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis |  | 3 | 3 |
|  | Were the specific incentives and disincentives to achieving the planned CD identified? What was actually done to build on them in the case of incentives or offset them in the case of disincentives? | Scores 4 if identified and taken fully into account in design and implementation. Scores 1 if no analysis or no account taken of analysis |  | 1 | 2 |
| Was the full complexity for the CD in achieving outcomes recognised and addressed in design and implementation |  | Scores 4 if elements of complexity identified, mapped and taken fully into account in design and implementation. Scores 3 if implicitly recognised and addressed. Scores 1 if no analysis or no account taken of analysis |  | 2 | 3 |
| 7) Theory of Change (ToC) | Was there an explicit or implicit Theory of Change - How adequate was it | Scores 4 if the ToC was explicit and adequate, 3 if it was implicit and adequate. 1 if no ToC and implicit ToC weak |  | 1 | 2 |
|  | Quality of the ToC: -Realistic, making realistic assumptions (assessments of pre-conditions) along the lines of contribution including those related to the overall and the institutional context) -Unpacks link between institutional capacity and performance and performance and development effectiveness - Identifies milestones and key assumptions to be monitored | Scores 4 if satisfies all criteria, 1 if ToC did not exist implicitly and did not satisfy conditions |  | 1 | 2 |
| 13) The design and implementation strategies were informed by clear rationales to address the priority capacity issues identified |  | Scores 4 if a clear identification of issues and how to be addressed. Scores 1 if little evidence that there was any consciousness of issues |  | 3 | 3 |
| 14) Consideration of alternative potential CD approaches/modalities. responsive to recipients’ needs and informed by a clear understanding of the implementation context | Alternative modalities: Choice of modality, e.g. training, technical advice, exposure through work experience visits, etc. to alternatives, system design and transfer, conditional financial support - a complementary mix. What was the evidence that alternative modalities were examined and choices made | Scores 4 if alternative modalities for overcoming the constraint were evidently examined and acted on. Scores 1 if there was little consideration of modalities and modality not appropriate |  | 2 | 3 |
|  | Sub-question - cost implications were considered in modality choice | Scores 4 if costs were clearly considered and a factor in the choices made. Scores 1 if they were not considered and the modality was not cost -efficient |  | 2 | 3 |
| 17) The choice of partners were responsive to recipients’ needs and informed by a clear understanding of the implementation context | Alternative implementation partners with relevant experience. If the implementation partner was a twinning partner was there examination of consultant firms, TCDC or a national institution. | Scores 4 if there was evident consideration of the pros and cons of different partners and good choices. Scores 1 if a partner was chosen without any evidence of consideration and it was a poor partner |  | 2 | 3 |
|  | Technical twinning (not implementation) was there a net contribution of twinning over other modalities such as consultant firms, TCDC or a national institution. | Scores 4 if there was evident consideration of the pros and cons of different technical twinning partners and good choices. Scores 1 if a partner was chosen without any evidence of consideration and it was a poor partner |  | 3 | 3 |
| 18) Choice of time frame and sequencing: a concentrated support to change or a longer term and more evolutionary approach. What was the evidence that alternative modalities were examined and considered choices made |  | Scores 4 if there was evident consideration of the pros and cons and choice well based. Scores 1 if a choice made without any evidence of consideration and it was a poor choice |  | 3 | 3 |
| 15) The design drew on experience elsewhere | Identification of specific relevant experiences/evidence that informed the design | Scores 4 if there was evident consideration of experience elsewhere and it was acted on. Scores 1 if there was no account of evidence from elsewhere and this led to major deficiencies |  | No information | No information |
| 16) Implementation strategy drew on experience elsewhere | Choice of consultants with relevant experience | Scores 4 if the expertise brought in had relevant experience. Scores 1 if clearly did not have relevant experience |  | 3 | 4 |
| Key factors for financial accountability were: a) identified and considered in the design and b) addressed in the implementation, while maintaining focus and not becoming excessive? | Were well identified in the design | Scores 4 if well identified in design. Scores 1 if little or no specification |  | 2 | 2 |
|  | As implemented were suitable to government accountability mechanisms | Scores 4 if as implemented well suited to government systems. Scores 1 if unrelated to government systems |  | 2 | 2 |
|  | Met Norway's requirements | Scores 4 if as implemented fully met Norway's requirements. Scores 1 if completely failed to meet requirements |  | 2 | 2 |
|  | Covered all essential aspects | Scores 4 if provided good accountability on use of money by purpose as well as category of expenditure and against budget. Scores 1 if failed to provide coverage of key aspects |  | 3 | 3 |
| 19) M&E framework appropriate and applied | Was there an M&E framework well designed/appropriate - Not excessively heavy well linked to milestones on immediate outcomes not just delivery of outputs such as persons trained. | Scores 4 if well designed M&E framework in place. Scores 4 if in place, appropriate and applied. Scores 1 if non existent |  | 2 | 2 |
|  | Were the findings of M&E applied, to make management decisions and adjustments in budgets, activities and timeframes by Norway? | Scores 4 if well considered and applied. Scores 1 if little M&E and/or not applied |  | 2 | 3 |
|  | Were the findings of M&E applied for accountability of implementers | Scores 4 if performance on M&E reported results was used vigorously e.g. withholding payment. Scores 1 if little or no direct use |  | 2 | 2 |
|  | Were the findings of M&E applied, to make management decisions and adjustments in budgets, activities and timeframes by the implementers? | Scores 4 if well considered and applied. Scores 1 if little M&E and/or not applied |  | 2 | 2 |
|  | Were the findings of M&E applied, to make management decisions and adjustments in budgets, activities and timeframes by the implementers? | Scores 4 if well considered and applied. Scores 1 if little M&E and/or not applied |  | 2 | 2 |
|  | Were the findings of M&E applied for wider learning | Scores 4 if evidently disseminated and used. Scores 2 if nothing disseminated for wider learning from M&E. Scores 1 if other information disseminated ignoring M&E findings |  | 2 | 2 |
| 21) Adaptive management: Were there any significant changes in the intervention during implementation based on evidence, especially to better achieve outcomes or make outcomes more relevant? |  | Scores 4 if major changes made on the basis of evidence or no evidence there was need for changes that were not made. Scores 2 if no changes on the basis of evidence. Scores 1 if evidence ignored |  | 3 | 3 |
| 23) Buy-in to the objectives and modalities of the intervention Target institutions and local stakeholders sense of ownership of the intervention | Was the intervention implemented with the national authorities in the driving seat? | Scores 4 if all major decisions taken by national authorities. Scores 1 if national authorities had little or no voice in the CD |  | 2 | 2 |
|  | Buy-in to the objectives and modalities of the intervention - Political level. Does the national government feel it owns the intervention? | Scores 4 for very evident support in decisions, actions and time given not just words. 1 if no evidence of support 2 if support but do not understand or fully agree on what is to be achieved |  | 4 | 4 |
|  | Buy-in to the objectives and modalities of the intervention - Institutional leadership level | Scores 4 if very enthusiastic and committed, clearly understanding what is to be achieved. 1 if cynical and uncommitted |  | 4 | 4 |
|  | Buy-in to the objectives and modalities of the intervention -Direct Counterparts | Scores 4 if very enthusiastic and committed, clearly understanding what is to be achieved. 1 if cynical and uncommitted |  | 4 | 4 |
|  | Do the direct beneficiaries feel they own the intervention (for these projects direct beneficiaries are the trainees) | Scores 4 clear commitment to the intervention and its follow-through by all and they think of it as their project. Scores 1 if regarded as something entirely external even if useful in some respects |  | 3 | 3 |
| 24) Internal and external champions for the CD identified and real | External senior national bureaucratic and political | Scores 4 if they are able to influence strongly at the right level and clearly committed. 1 if do not exist in any real way |  | 3 | 2 |
|  | Internal senior management | Scores 4 if clearly identifiable who in senior management taking a real lead and they are able to and do provide good leadership. 1 if do not exist in any real way |  | 4 | 4 |
| 25) Support and guidance for a) selection; b) design and c) implementation of CD interventions - (Embassy and other government staff) | Have staff received adequate support and guidance (comments, guidelines, training, contact point for advice) for CD as distinct from technical elements | Scores 4 if support levels high and accessible. Scores 1 if little or no support |  | 2 | 3 |
|  | Did the staff look for support on CD | Scores 4 if staff actively looked for support. Scores 1 if staff did not seek CD support |  | 2 | 1 |
|  | Did Norway have sufficiently flexible procedures to respond to adaptive project design and management needs of CD | Scores 4 if procedures flexible to respond to needs of CD with major change if needed. Scores 1 if no flexibility at all |  | 3 | 3 |
|  | Did Norway welcome or tend to respond negatively to suggestions for change during implementation | Scores 4 if fully open to suggestions. Scores 1 if a closed mind to changes |  | 3 | 3 |
| 26) National Government procedures and attitudes | Does the government have sufficiently flexible procedures to respond to adaptive management needs of CD. | Scores 4 if fully flexible and procedures and facilitates change. Scores 1 if will not accept change |  | 2 | 2 |
|  | Does the government welcome or tend to respond negatively to suggestions for change during implementation | Scores 4 if facilitates change in response to well justified requests. Scores 1 if will not accept change |  | 4 | 2 |
| 27) ) Support and guidance for a) selection; b) design and c) implementation of CD interventions - Norwegian Twinning partners | Have staff received adequate support and guidance (comments, guidelines, training, contact point for advice) for CD as distinct from technical elements | Scores 4 if support levels high and accessible. Scores 1 if little or no support |  | 2 | 3 |
|  | Did the staff look for support on CD | Scores 4 if staff actively looked for support. Scores 1 if staff did not seek CD support |  | 2 | 2 |

| Results and Their Sustainability |  | Score 1-4 where 1 is negligible or very low and 4 is high. If the question not applicable to project score n.a. | National Statistical Office |
| --- | --- | --- | --- |
| 29) Capacity of the target institution(s) | Evidence that the Capacity of the Partner Institution (s) has a) improved and b) improvement was in line with targets and c) commensurate with the resources deployed. d) Was the improvement sufficient to deliver on the intended or essential prerequisite for enhanced delivery of results by the institution? | Scores 4 if satisfies criteria a, b, c, and d. 1 if satisfies none of the 4 criteria | 3 |
|  | Evidence that the assisted institution has achieved progress on its intended outcomes as a result of its improved capacity | Scores 4 Improvement was entirely due to capacity. Scores 2 if no improvement and Scores 1 if there was a deterioration | 3 |
|  | Evidence of the interventions contribution to the outcomes for capacity and delivery by the institution (both capacity and delivery could improve or deteriorate for reasons little linked to the intervention) | Scores 4 Improvement was entirely due to CD. Scores 2 if no contribution and Scores 1 if there was a deterioration due to e.g. resources being diverted by the CD away from delivery by the CD | 3 |
| 30) Evidence of specific CD outcomes having continued or are likely to be continued | Extent to which internal conditions exist to support continuation of CD outcomes: e.g. -Stability of staffing (e.g. has the change relied on just a few individuals; and if they go, how will that affect sustainability of outcomes?) -Internal incentives/motivation to maintain and build on the change? | Scores 4 if there are no significant internal barriers to continuation of outcomes and a clear internal commitment. Scores 1 if there is little interest in continuation | 2 |
|  | Extent to which national external conditions exist for the outcomes to continue, e.g.: - Budget allocation (have costs of the institution gone up and can this be sustained)? - Continuation of a positive external environment, e.g. supportive policies and ongoing support from key stakeholders? | Scores 4 if there will very evidently be budget and necessary changes by government, etc. etc. If this unlikely or there are clearly other priorities, scores 1 | 2 |
|  | For twinning: evidence that the twinning relationship will continue beyond the end of donor funding | If no twinning N.A. If both the twinning institution and the national institution very clearly committed to working together in the absence of supplementary financing scores 4. Scores 3 if committed and some medium-term finance has been located. Scores 1 if no connection likely (e.g. if TA all consultants and no real interchange with twinning partner) | 2 |
| 31) Unintended effects of the CD) positive and negative | Positive effects, if any, can include such things as wider pool of policy trained people for civil service | Scores 4 if very extensive and 1 if none | 3 |
|  | Negative effects, if any, (can include such factors as diverting resources from areas of greater priority - making systems more elaborate without being more effective or being parallel systems) | Scores 4 if none and 1 if very extensive | 2 |

The ‘Country Report on Support to Statistics (CRESS), 2009-2014’, prepared by the NSO in April, 2012, offers more details on support received by NSO, by donor, from 2009 to 2014.

PARIS21 is a consortium of donors, country governments, decision makers and practitioners that seeks to improve dialogue between producers and users of data.  It is considered a development partner of the GoM.

Final Report, Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistical Office and Statistics Norway, 2003 – 2007, April 2008, p.8

Support to Malawi has increased significantly over the past three years – from 374.7 million kroner in 2011 to 403.8 M in 2012 and 532 M in 2014 - albeit with the same numbers of embassy staff in Lilongwe.

National Statistical System, National Statistical System Strategic Plan, 2013-2017, November, 2013, Executive Summary.

Ibid, p.1

Ibid, p.1

Mid-term Review of the NSO/MEPD/MoF Malawi-Statistics Norway Project, Final Draft 25.04.06, p.12

Ibid, p.12

Ibid, p.12-13

Erlend Nordby, Thorn Oftedal, Norad, Economics and Public Administration Department, Appraisal of Statistics and Planning for Malawi Growth and Development Strategy – Malawi, January 2007-December, 2009, p.1

Ibid, p.1

Final Report, Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistical Office and Statistics Norway, 2003 – 2007, April 2008, p.8

See PARIS 21, Peer Review of Malawi National Statistical System, 26-30 January, 2009.

National Statistical System, National Statistical System Strategic Plan, 2013-2017, November, 2013, p.15.

Mid-term Review of the NSO/MEPD/MoF Malawi-Statistics Norway Project, Final Draft 25.04.06, p.22.

Ibid, p. ii

The software is considered an integral part of Norway’s support, but in the absence of an exit strategy, there are no assurances what the GoM is planning to carry on in the future.

The Country Report on Statistics (CRESS) for Malawi for the period 2009 –2014 identifies the sources and levels of funding to the NSS. Among other things, it indicated that financial commitments to statistical development from 2009 to 2014 (for NSO and line Ministries) amounted to approximately US$29.8 million. This figure included ongoing activities. Norway was reported as having the third highest commitment level among donors (after DFID and EU), but the highest disbursement rate. Norway was also considered the “major donor to the NSO due to the long term commitments and arrangements”.

Mid-term Review of the NSO/MEPD/MoF Malawi-Statistics Norway Project, Final Draft 25.04.06, p.24.

Although Statistics Norway did provide the review team with end reports for the first two phases, as requested.

While a formal baseline wasn’t prepared at the start of the project, initial fact finding missions included what SN described as “extensive reports” that provided a basis for early programming.

Developing the National Statistical System, Progress Report for the period 1 March 2013 to 31 May 2014, p. 14.

Final Report, Institutional Co-operation between the Ministry of Finance, the Ministry of Economic Planning and Development, the National Statistical Office and Statistics Norway, 2003 – 2007, April 2008, p.7.

Mid-term Review of the NSO/MEPD/MoF Malawi-Statistics Norway Project, Final Draft 25.04.06, p.12.

Ibid, p. 21.

National Statistical Office (with assistance from Statistics Norway,  Zomba and Oslo), Statistics for the Malaŵi Growth and Development Strategy - Phase 3, July 2011 to June 2014, November 9, 2011, p.17.

It’s not clear why these two themes are combined as they are under the MGDS.

Ministry of Finance and Development Planning, Department of Development Planning, Malawi Growth and Development Strategy II, 2011-2016 p. xxi