Capacity Building and Technology Transfer for Mitigation of Geo-hazards in Vietnam in the Context of Climate Change

A case study in the evaluation of Norwegian support to capacity development

Final

September 2015

Joe Bolger

Dang Ngoc Dung

Table of contents

ACRONYMS ……………………………………………………………………………………………………………………………………3

1	Introduction	4

2	Limitations	4

3	Overview of the Project	4

4	Relevance	7

4.1	Country needs	7

4.2	Norwegian priorities	9

4.3	National priority and demand	9

5	Strategy and Design	9

5.1	Internal context of the institution	11

5.2	Planning process and capacity needs assessment	11

5.3	Evidence base	12

5.4	Theory of change	13

5.5	National ownership	13

5.6	Donor fit	13

6	Implementation and Management	14

6.1	Implementation arrangements	14

6.2	Results verification and measurement	14

6.3	Efficiency	15

6.4	Adaptation and adjustment	16

7	Results	16

7.1	Short- and medium term results	16

7.2	Sustainability	19

8	Conclusions and Lessons Learned	19

9	Annexes	25

9.1	References	25

9.2	Scorecard	26

Scoring against Questions established for the evaluation	26

Acronyms

ADB		Asian Development Bank

CD		Capacity development

COE		Centre of Excellence (for Geohazard Mitigation)

GPR		Ground Penetrating Radar

HUMG		Hanoi Univeristy of Mining and Geology

IMRG		Institute of Mineral Resources and Geology

MDG		Millennium Development Goal

MFA		Ministry of Foreign Affairs

NDRMPP 	Natural Disaster Risk Management Program Project (World Bank)

NGI		Norwegian Geotechnical Institute

NOK		Norwegian kroner

NTP		National Target Program (NTP) to Respond to Climate Change.

NVE		Norwegian Water Resources and Energy Directorate

PECC I 		Power Engineering Consulting Company 1

PMU		Project Management Unit

SEDP		Socio-Economic Development Plan

ToC		Theory of Change

UiO		University of Oslo

USD		US Dollars

VNU		Vietnam National University, Hanoi

# Introduction

This case study of Norwegian capacity development (CD) support to enhance capacity and transfer technology for mitigation of geohazards in Vietnam was conducted by a two-person team comprising one international and one national consultant. A country visit to Vietnam and a series of stakeholder interviews were at the core of the case study approach. Furthermore, a large number of programme documents and additional literature was consulted.

The results of this case study have been synthesised alongside a number of other case studies from Vietnam in a country report. Both this case study and the Vietnamese country report are key data sources for the wider Itad-led evaluation of Norway’s support to capacity development.

# Limitations

The evaluation team was well supported by the Norwegian embassy in Hanoi and local partners, notably VNU. Both of these entities graciously and effectively organized meetings and interviews for the evaluation team and made themselves available for interviews as well. There were some gaps in availability of Vietnamese personnel the team intended to meet, but this didn’t materially affect the evaluation process or results. Norwegian partners commented on the draft report, although efforts to organize interviews with them were not successful.

# Overview of the Project

Vietnam faces a number of challenges relating to the potential impact of geo-disasters triggered by climate change, earthquakes, typhoons, landslides or subsidence. However, the country has had insufficient capacity (e.g. knowledge, skills, capable institutions) to deal with such challenges effectively.  In response to this, Vietnam National University (VNU) prepared a project proposal seeking support from the Government of Norway to improve its capacity, and that of selected partners, in geo-disaster mitigation and in the process assist the country to deal with potential geo-disasters.

Norway responded positively to the proposal and the result was a two phase project which commenced in 2008 and was still ongoing at the time this report was written. VNU is the lead implementing agency for the project and the sub-sections immediately below offer a brief description of the two phases of the project, with a particular focus on expected results.

Phase I (2008-2012)

Phase I of the project was named Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam.

The Goal articulated for Phase I was as follows:

- To contribute to increasing the country’s capacities for geo-disaster mitigation

The Purpose/Objectives were to:

- Build capacity for Vietnamese experts in the areas of geo-disaster adaptation and mitigation

- Increase capacity in tackling geo-disasters, and

- Help establish scientific procedure for research implementation and assessment of geo-disasters at the sites of hydropower plants, cities and coastal zones in the typical natural and socio-economic condition of Vietnam with a focus on global climate change

Phase I had three components which are listed below with associated budgets (USD) and Expected Impacts.

Table 1: Phase I Components and Expected Results

| Component | Expected Impacts | Budget (USD) |
| --- | --- | --- |
| - Capacity Building (training and support to formal education) | Self-confidence in analyzing, managing and finding solutions to geo-disaster problems in Vietnam. | $278,543 |
| - Three case studies (pilot field project on various subjects to gain hands‐on experience) 2a) Pilot study Cua Dat hydropower plant 2b) Pilot study on coastal zone of the Red River 2c) Land subsidence in Hanoi | Enhanced competence and capabilities to perform geo-disaster investigations at other sites. Ability to solve similar problems in other critical areas resulting in better land use planning and techniques for forecasting shoreline changes. Trained local personnel will contribute in chalking out long-term solutions in urbanised areas which include proper land use planning in the affected areas. | $1,265,538 |
| - Disseminate information (dissemination of data and results) | Awareness and preparedness on dealing with natural disasters which is a fundamental basis for effective disaster risk management approach | $333,170 |

With an independent audit and project staff/management costs, the total budget (Norwegian contribution) for Phase I was USD $2.2M. The in-kind contribution from the Norwegian Geotechnical Institute (NGI) and VNU was equivalent to USD $50,000 each.

Phase II (2012-2014)

The name of the project changed in Phase II to Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change. As suggested in the Phase I End Review, the project title in Phase I didn’t accurately reflect the development issue being addressed. The review also suggested that given the areas already being addressed in Phase I (weather and climate change induced geo-hazards and geological conditions), the references to “Environment” and “Energy Development” in the original title were not appropriate.

The budget for Phase II was 20 million NOK (USD 3.6 M) with a counterpart budget of 2,000 million VND (USD 100,000) meaning the total budget for both phases was USD $5.8M.

The Phase II proposal included a Logical Framework matrix, in part reflecting encouragement from the Phase I End Review to take more of a results-oriented approach in Phase II.  The Phase II proposal also indicated that doing so “will help in keeping track of the various activities linked with the results and outputs of the programme”:

Table 2: Phase II - Logical Framework Matrix

| Objectives | Indicators of Expected Results |
| --- | --- |
| Development Objective: To reduce the impact of Geohazards in Vietnam in the context of changing climate | Reduced risks at pilot programme study sites thanks to increased geohazard awareness and preparation |
| Specific Objectives: Capacity building for VNU in areas of geohazard adaptation and mitigation | Trained teaching and research staff and students at VNU and other organizations such as the Power Engineering Consulting Company 1 (PECC 1) & Hanoi University of Mining and Geology (HUMG) |
| Short term Objectives: a) Establishment and formalization of graduate program on Environmental Geology and Geohazard of Oslo University’s standard b) Perform pilot programme studies c) Propose geohazard mitigation measures Increase in the number of students studying Environmental Geology and Geohazards Involvement of local organizations | Increase the number of students studying Environmental Geology and Geohazards Involvement of local communities Geohazard mitigation methods suggested in critical areas |
| Output Results: - Capacity build up through on-the-job training - Improvement and effectively running of International Research Centre on Disaster and Environmental Change (including procurement, transfer and training on modern equipment and relevant software) - 2 PhD and 10 Master students trained 4) Knowledge Disseminated | Capacity and skills enhanced of at least 10 teaching staff and 50 students Number of trained staff Modern equipment and software supplied A number of Vietnamese organizations participating in the improvement and running of the Centre Number of experts from Norway (NGI, University of Oslo - UiO,…) participated in activities of the center Number of MSc, PhD trained with the assistance of the center Number of guidelines published papers based on the research of the center Enrolment of students in VNU and UiO Organization of seminars and workshops with participation from stakeholders |

The expected Impacts weren’t included in the Logical Framework but were expressed in the Phase II proposal as follows:

- “The programme aims to improve the living conditions in Vietnam by carrying out geohazard studies for mitigation and adaptation of Geohazards in the tropical conditions of Vietnam.”

This statement of expected impacts goes further than the Goal statement in Phase I which had somewhat vaguely called for the project to contribute to “increasing the country’s capacities for geo-disaster mitigation” without any specific reference to impacts, e.g. improved living conditions, at the community level.

The Phase II proposal further suggested that by recommending and implementing measures to mitigate against geohazards at infrastructure sites, e.g. hydropower plants that the project would “contribute in alleviating poverty for the residents living in the affected areas”.

# Relevance

## Country needs

The content of this two phased intervention has been well aligned with various aspects of the project context, e.g. political and policy context, physical and natural environment, as well as the needs of recipient institutions. Natural disaster risk reduction is a declared priority of the Vietnamese Government in Socio-Economic Development Plans (SEDPs) 2006-2010 & 2011-2015, the Governmental Action Plan Framework for Adaptation and Mitigation of Climate Change in the Agriculture and Rural Development Sector Period 2008 -2020 (Decision No: 2730/QD-BNN-KHCN, 5th September 2008) and the National Target Program (NTP) to Respond to Climate Change.

The World Bank has also ranked Vietnam first in terms of the potential impact of climate change on population, GDP, urbanization and wetland areas which further underlines this area of investment as a national priority. The Appropriation Document for the project highlighted a number of specific areas of vulnerability associated with climate change, including the following:

- “Extreme weather events induced by climate changes are happening more frequently and with higher intensities. Heavy rainfall and cloudbursts are leading to more floods and landslides. Local livelihoods experience set-backs. The events are counterproductive and are threatening the sustained economic development of Vietnam.

- Floods and flash floods, in addition to causing river bank erosions, are causing delays and problems for both existing and new hydroelectric projects and other infrastructure projects in the country.

- Drought incidences appear to be increasing in some provinces. These events have implication on water supplies and agricultural practices and have the potential to increase surface erosion and subsidence as more and more underground water resources are tapped.” (italics added)

The project was approved in response to these concerns and based on a perceived need to enhance scientific knowledge on geo-disasters in Vietnam and with a view to “develop methodologies and models to help reduce the vulnerability of the country with respect to natural disasters.” This led to the specific request in the project proposal for support to extend the knowledge base of VNU researchers, and to enhance the capacity of VNU, while conducting pilot studies and spreading awareness.

The relevance of the project was also underlined by the fact that at the time the proposal was submitted Vietnam was developing a National Target Programme on Climate Change Adaptation. Other donors were already supporting or gearing up programming in this area and the support from Norway was intended to complement those efforts.

From a global perspective, the project focus is consistent with global priorities as per the Millennium Development Goals (MDGs) (e.g. MDG 1 – poverty reduction and MDG 7- environmental sustainability) as well as various international initiatives and commitments relating to climate change.

In terms of the relevance of the project to participating institutions, the geo-disaster training and research activities funded by the project have not only benefited students, lecturers and researchers of the main implementing partners such as VNU (one of the biggest educational institutions in Vietnam), Hanoi University of Mining and Geology (HUMG) and Power Engineering Consulting Company 1 (PECC 1), but has also benefited others such as the Institute of Mineral Resources and Geology (IMRG), the Institute of Geology, University of Civil Engineering, University of Transportation and the Ho Chi Minh City University of Architecture. Indications from project reports and interviews are that the training and research opportunities afforded through the project have been relevant to the needs and interests of the students/researchers associated with these various institutions, especially with the emphasis on ‘learning by doing’ which was seen as an effective way to learn while contributing to personal/ institutional learning.

The project pilot activities also targeted relevant entities and issues in various regions of the country. For example, the project pilot activities in Phase I focused on: the Cua Dat hydropower plant; Hai Hau coastal erosion in Nam Dinh Provinces, and; Quoc Oai in Hanoi, with an emphasis on affected communities.  Phase II committed to focus on:  Tan Nam commune, Quang Binh District, Ha Giang Province; Nam Dan Commune, Xin Man District, Ha Giang Province; Song Tranh 2 Hydropower Plant in Quang Nam Province, and; Hai Hau coastal erosion in Nam Dinh Province.

## Norwegian priorities

Norwegian development cooperation with Vietnam dates back 40 years. Norway's current sector and thematic priorities in Vietnam are: climate, the environment and forest cooperation; renewable energy; technical cooperation; women and gender equality, and culture. Collaboration in higher research and education are also priority areas for Norway’s development cooperation as are institutional strengthening and capacity building.

The Norwegian government has recently increased its  development  budget  with  more  focus  on  climate  change  and  renewable  energy. Vietnam is also one of the three priority countries in Asia selected by the Government of Norway for collaboration on preventive measures for natural disaster risk reduction and one of four countries to concentrate on for climate change related programming.

## National priority and demand

The priorities addressed in the project are directly in line with Vietnam’s national priorities. For example, the project supports two of the main objectives of Vietnam’s National Socio-Economic Development Plan 2011-2015 which are:

- Clearly improve and enhance quality of education, training and human development, and

- Strengthen the protection of natural resources and environment, and actively respond to climate change impacts.

Furthermore, as indicated above, the priorities addressed in the project are consistent with the short and long term targets of institutional partners such as VNU and HUMG and reflect what are considered to be urgent priorities given the potential risks of geo-disasters to local communities in Vietnam.

# Strategy and Design

There was very little documentation available to the review team on the design process for this project. What is known, however, is that no formal capacity assessments were undertaken in advance of the project to determine the most appropriate approach to capacity development with key Vietnamese partners. As Vietnamese partners indicated, such needs were “determined when working with local partners” or by drawing on international reports on disaster mitigation to help identify specific types of constraints, and using that as a basis to determine priority interventions, e.g. strengthening of human resource needs relating to geo-disaster mitigation, including management.

The project ultimately worked at three levels: individual, institutional (university) and national (PECC1, HUMG, IMRG), although capacity development (CD) strategies were not clearly articulated either within or across these levels. An estimated 27% of project funding was provided for training, while 57% of project funding was for pilot studies which included “training for practitioners” with a primary focus on “technical knowledge and field practical experience”.  The remaining 16% in Phase I was for dissemination activities. Less attention was paid explicitly to institutional or policy issues. The reason for the latter, the review team was told, was that policy issues were being addressed through other projects, e.g. Asian Development Bank (ADB). Phase II did turn the focus somewhat more to  institutional issues, e.g. with the proposal to develop a Centre of Excellence, but planning documents have been vague on  details and strategies for setting it up, beyond an intent to use it to bring together specialists from diverse backgrounds - Geologists, Social Scientists, Psychologists - to address geo-disasters. Another important shift in the strategy in Phase II was the explicit emphasis on climate change which was reflected in the modified naming of the project.

The main modality or mechanism for capacity development was the institutional collaboration with select Norwegian institutions. According to stakeholders interviewed, VNU benefited substantially from training opportunities under this collaborative arrangement, as did other engaged entities such as the Geological Institute and PECC1. Within the institutional collaboration arrangement, a number of approaches were relied upon to support capacity development of Vietnamese partners:

- learning by doing (direct support for field and laboratory based work)

- sharing of experiences/materials by Norwegian partners

- training of Vietnamese students in Norway (at University of Oslo (UiO) or at the Norwegian Geotechnical Institute (NGI)), and

- sending individuals to international conferences to develop their capacity and/or to disseminate the results of the project.

In terms of the selection of Norwegian institutional partners, according to interviewees, they were proposed by Vietnamese partners and selected in Phase I by the Norwegian embassy after the Ministry of Foreign Affairs (MFA) consulted with Norad.  Phase II relied on competitive processes which led to the selection of UiO and dropping of the Norwegian Water Resources and Energy Directorate (NVE). The Vietnamese partners were not involved directly in the competitive selection process in Phase II, although they did reportedly indicate their preference for NGI’s continued involvement.

The partnerships with participating Norwegian institutions were described in positive terms by stakeholders interviewed based on the history of engagement in the case of NGI, the quality of the personal relationships, and the high standard of knowledge and experience of those involved. The general need for Advisors through the institutional collaborations was reportedly agreed to between the Norwegian and Vietnamese partners but VNU was not involved in developing the TORs or actual selection of individual advisors. However, after NGI was selected, they signed an Agreement in each phase which specified the mandate and detailed tasks and responsibilities of each party. Decisions regarding Vietnamese partners were made by VNU and were reflected in their proposal to the Norwegian government.

The project design included provisions for dissemination of “data and results” from the pilot studies but included only initial efforts to enhance capacity to demand, or strengthening the ‘voices’ of communities to hold authorities to account on geo-disaster issues, although Component 3 did include awareness raising. The latter incorporated, for example, raising awareness about risks among households around hydropower plants. The project also involved some media engagement (more as the project advanced). In addition, research results presented at a workshop were publicized by the media, and on the internet, leading to discussion in the National Assembly and a decision at that level requiring authorities to take appropriate actions.

As to whether the approach taken was the ‘best fit’, if the focus was to be on enhancing research and teaching capacity of a tertiary institution in Vietnam in the area of geo-disasters, one could say that it was a ‘good fit’. However, the Development Objective for Phase II was to “reduce the impact of Geohazards in Vietnam in the context of changing climate” and the associated Indicator of that expected result was “Reduced risks at pilot programme study sites thanks to increased geohazard awareness and preparation.” Risks were, in fact, reduced at some pilot sites by virtue of project interventions. However, the project would have to scale up if its objective was to, more broadly “reduce the impact of Geohazards in Vietnam in the context of changing climate”.

## Internal context of the institution

VNU advanced the original proposal for this project and positioned itself as the lead institution on the Vietnamese side, collaborating with a number of other Vietnamese institutions. However, as outlined further below, and as flagged in Norad’s 2008 Desk Appraisal of the proposal, not much was known about the capacity of VNU to manage a project of this nature at the outset. Nor was much known about their capacity strengths and shortcomings in relation to geo-disasters specifically and how they might be addressed in such a project.  Nevertheless, VNU was known to be a credible and important tertiary institution in Vietnam’s education sector.

## Planning process and capacity needs assessment

The Norwegian embassy in Hanoi met with VNU and NGI several times in 2007 regarding a possible project. The VNU (as the coordinator of the initiative) eventually submitted a project proposal to the embassy asking for 12.1 mill NOK for a ‘disaster mitigation and adaptation capacity building project’ which would be spread out over a three year period.  Norad’s Desk Appraisal of the initial project proposal noted the relevance of the proposal but was critical of various aspects of the approach and design. Key concerns raised included the following:

- The point of departure for the project was supposed to be the World Bank’s Natural Disaster Risk Management Program Project (NDRMPP).  The project proposed by VNU was expected to complement this WB project, but it wasn’t apparent from the proposal how that would be done as there was no analysis of how gaps in the NDRMPP would be addressed. Nor did it describe how it would complement other donor-supported initiatives (Care Denmark and the Government of the Netherlands).

- VNU described itself in the proposal as one of the “nodal points in Vietnam for geohazard studies” without being clear on its own capacities and shortcomings or those of other relevant stakeholders in Vietnam.

- The appraisal noted that the proposal was based mainly on a “technical (engineering) approach to geo-disaster mitigation management” with much of the research to be carried out by NGI and NVE engineers (and geologists). However, the proposal didn’t include provisions for how the project would deal with social and socioeconomic dimensions of geo-disaster mitigation and planning.

The proposal also didn’t outline how it was actually developed leaving questions about the extent of other stakeholder involvement in planning and analyses. It further lacked a detailed risk analysis, including institutional factors required to sustain the proposed investments.

Finally, the appraisal noted that the proposal didn’t outline the overall goal, outcome, outputs and associated activities in a Logical Framework format with indicators, making it difficult to get a clear sense of how the various activities were linked and would contribute to higher level results. The appraisal noted that with these shortcomings it would be difficult to monitor progress towards expected results.

A revised proposal submitted by VNU addressed some of the above-noted concerns but the revised design was still considered by Norad to be “weak”, e.g. the link between proposed activities and expected results and lack of clarity on how socio-economic aspects would be dealt with during implementation. Nevertheless, the revised proposal was approved by the Norwegian Embassy which subsequently signed a project agreement with VNU.

## Evidence base

As suggested in the preceding sections, the project proposal was based on clear priorities of both Vietnam and Norway. The priorities identified by Vietnam were, broadly speaking, backed by strong evidence, including the aforementioned World Bank report which noted the high level of risk in Vietnam in terms of potential geo-disasters. Research activities undertaken in the project also provided evidence for specific interventions at the community level while contributing to learning materials for the institutions involved. The evidence emanating from such research has also supported dissemination activities and engagement with policy makers on key issues relating to geo-disasters.

However, the project lacked formalized ‘evidence’ on the nature or scope of the capacity challenge to be addressed through the project, the methods by which those challenges would be addressed and the evidentiary basis for advocating a particular approach. For example, as far as the review team was able to determine, no formal assessment of capacity needs or shortcomings (for VNU, and/or other institutions) was undertaken at the outset to give more precision to the proposed interventions outlined in the project proposal. For its part, VNU noted during this review that they were not aware of, or informed about, any guidelines or requirements for capacity assessments or other analyses to underline their project proposal.

## Theory of change

The project had no Theory of Change (ToC). The project did, in principle, embrace a results based approach, but it was weakly applied.  An implicit ToC though would have been something like this:

- Development of knowledge and skills of individuals, relating to geo-disasters and climate change, in selected institutions will help those institutions to be more capable in carrying out relevant research, teaching students and working with ‘at risk’ communities to better understand those risks and to mitigate them.

This implicit ToC though was based on assumptions about the ability of participating institutions, such as VNU, to rely strictly on new knowledge and skills, developed through collaboration with foreign partners, and combined with awareness raising efforts to influence change at local and national levels. The implicit ToC also focused largely on ‘transactional’ changes at the level of individuals (e.g. support for training or research) with implicit assumptions that these investments would lead to ‘transformed’ institutions and to sustained institutional change beyond the term of the project, without being clear though on the required intermediary steps between the transactional changes sponsored through the project and the higher level expected transformations.

## National ownership

The Project has had a high level of national ownership. As previously noted, VNU submitted its own proposal to the Norwegian Embassy, established partnerships with Vietnamese and Norwegian partners, specified its own needs and those of local communities, and took leading roles in project design, planning, management and reporting. The program management unit (PMU) housed in VNU was also viewed positively in the Phase I End Review in terms of keeping track of overall progress and addressing issues such as pilot study sub‐contracts.

The fact that the project has been led by a well-regarded and well-connected national institution in Vietnam, VNU, that has broad political support, has also helped to reinforce national ownership of the project.  Arguably though, “ownership” may have been too focused on VNU, not extending sufficiently to other partner institutions or the community level, although relationships among the various stakeholders involved in implementation appeared to be open, cordial and collaborative. Under the project agreement, VNU was recognized as the project “owner”, with responsibility for management and financial arrangements, among other things. At the same time, the project proposal named many different implementing partners but their roles were not always as clear as they could have been, with some exceptions, e.g. the engagement of Hanoi People’s Committee and Nam Dinh People’s Committee in pilot activities. Greater clarity on the roles of the other partners may have broadened ownership and in the process extended the reach of benefits arising and prospects for sustainability.

## Donor fit

Norway has a long history of development cooperation programming in Vietnam. As noted earlier, Norway's current strategy for Vietnam is based on five priority areas: climate, the environment and forest cooperation; renewable energy; technical cooperation; women and gender equality, and; culture. With respect to the first priority area, Vietnam is described on Norad’s web sites as “as one of the country's most important partners in the area of climate and forests.” This stems, in part, from Vietnam’s commitment to reduce greenhouse gas emissions by 2020.

Also as noted earlier, Norway has recognized that Vietnam is one of the world’s most vulnerable countries to climate change due to rising sea levels which could have a significant impact on, among other things, the country’s food security. Norway’s commitment to climate change, environmental issues, and prevention of natural disasters follows from these realities. It also builds on historical relationships between VNU and NGI which were carried forward in this project.  The donor fit is thus seen as a positive one given Norway’s history of engagement in Vietnam, its current commitment to the areas addressed in this project and the institutional capacity and experience Norway has been able to share with Vietnam through the two phases of this project.

# Implementation and Management

## Implementation arrangements

VNU was the lead implementing agency in Phase I of the project, in partnership with HUMG, PECC 1, and the People’s Committees of Hanoi City and Nam Dinh Province. The Norwegian partners were NGI and NVE.  The Phase II documents identify the same organizations as implementing partners, with the exception of the two People’s Committees and NVE, the latter being replaced on the Norwegian side by UiO.

The project was managed on a day-to-day basis by a Project Management Unit. The PMU was established according to Decision No.5629/QD-KHCN dated 14/11/2008 for Phase I and Decision No.4534/QD-KHCN dated 26/12/2012 for Phase II. According to those decisions, the PMU in Phase I consisted of a Project Director, two Deputy Directors, an Administrative Secretary, a Scientific Secretary and an Accountant. Phase II added a person in charge of International Affairs and a Cashier. As stated in the Decisions, the PMU was responsible for providing consultancy and assistance to the Project Director in project deployment and implementation, appropriate to the signed Agreement and Government’s management regulations.

The Phase I review team indicated that it was “impressed by the initiatives, dedication and flexibility of program management in carrying out a whole range of activities”. In fact, it suggested that the approach encouraged by the PMU helped to bring in a wide range of project stakeholders in Vietnam.  The PMU was also credited with ably administering relevant contracts. However, several critical points were raised by the auditors including a need for improvements in accounting for project funds and financial reporting.

## Results verification and measurement

The 2011 End Review of Phase I, produced by Scanteam, highlighted shortcomings in reporting including the lack of a results-based approach to reporting in the first phase of the project. Some project results were measurable and reported on, e.g.  # of training participants and # of Masters students and PhD candidates graduated with project support, and # of pilot studies carried out by the project. However, the impacts of training and education on beneficiaries' performance (e.g. in teaching and researching), have not been documented systematically. Other changes, e.g. in institutional capacity, have not been measured or reported routinely.

Progress reports in Phase I were semi-annual and annual. In Phase II, the project shifted to quarterly reporting. However, the reports have lacked detail in terms of reporting specific results achieved against planned results, and deviation analyses. A number of performance indicators were identified at the design stage, but these have not been used systematically in monitoring and reporting. And it was not until the 2010 and 2011 Annual Reports that the project explicitly reported progress against expected results. Even at that stage, reporting was at the activity/output level (see 2011 Annual Report, Annex A - Comparison of Proposed and Completed Activities). The 2009 report had no reference to outputs, outcomes or impacts whatsoever.

The above comments on reporting are not meant to imply that project stakeholders didn’t focus on achieving real and meaningful change. They did, and project stakeholders worked hard towards those ends, e.g. organizing and participating in training and conducting the pilot studies. However, as suggested above, it’s not apparent from the reporting that the project managers took a systematic approach to verifying and measuring results (beyond the activity/output level). These shortcomings were noted in the Phase I End Review which remarked that while the project was “performing well in terms of ongoing activities”, indicators for outcomes and impacts were lacking and the project “wasn’t clearly structured to monitor the results chain”.

## Efficiency

While efficiency is difficult to assess in projects like this, one issue that did arise in this review was the cost of personnel from Norway. As the Phase I End Review noted: “The use of personnel from NGI and other Norwegian consultants is expensive, but decisions to use it are based on requirements rather than on cost‐efficiency criteria.” The review went on to say that Vietnamese stakeholders saw the value‐for‐money of Norwegian advisors as “high”, although selection didn’t appear to be based on any comparison of alternative approaches. Respondents from VNU though did describe the advisors as “highly competent”.

Further with respect to efficiency, the PMU did assess intermediate results of sub-contractors before committing to funding the remaining portion of contracts which was seen as one way of effectively addressing the cost efficiency issue. The team also sought out local contractors where possible as a way of managing costs.

## Adaptation and adjustment

The project has demonstrated flexibility over time, e.g. changing implementing partners and shifting the focus more explicitly to climate change in Phase II. In Phase II, the project also extended more support to community level beneficiaries after the experience in Phase I which saw the results of pilots not extend beyond local authorities.  Doing so allowed citizens potentially affected by geo-disasters to be more aware of risks and to increase their options for mitigating or avoiding the risks.

Phase II also followed up on 5/7 recommendations from the evaluation at the end of Phase I. These included recommendations on strengthening participatory approaches, improvements to the Logical Framework from Phase I, and relying more on a results-based orientation, although some of those changes could have gone farther than they did.

# Results

## Short- and medium term results

Overall, the project has been ‘successful’ in terms of delivering on planned activities. The End Review for Phase I which was undertaken 6 months before the end of the phase indicated that the planned outputs would be achieved by the end of 2011. In fact, some of the performance indicators ended up being higher than targeted. For example: one of the performance indicators for capacity building: "Number of experts trained through on job training in Vietnam" was targeted as "minimum 20", but achieved 103; and the indicator "number of experts trained in the field work of hydropower plant" had a target of 5 but achieved 12. Education on Environmental Geology and Geohazards for Masters and PhD students was also seen as having high prospects for sustainability and potentially expanding to broader impacts. On the downside, implementation in Phase I was reported as having been delayed to an extent.

VNU’s Final Report of Phase I (dated March 2012) highlighted the following key results, among others, from the three priority programming areas:

- Capacity Building (training and support to formal education)

- More than 100 participants in various trainings (approximately 25% female) on “practical aspects of mitigating geohazards”, e.g. training on use of Ground Penetrating Radar (GPR); visit of VNU researchers to Norway to learn about modern techniques of hazard and risk assessment for mitigation of natural disasters

- Seventeen participants received training in Norway, at NGI, at NVE and at UiO, resulting in a database, teaching materials and providing “the basics for serious academic research publications from various angles”.

- Procurement of a weather station and installation at VNU’s training campus at Ba Vi for training purposes

- Establishment of a joint Masters and PhD programme on “Environmental Geology and Geohazards” in Vietnam and enhancing the international center of excellence

- Case studies (pilot field project on various subjects to gain hands‐on experience)

- 24 contracts (including 4 from NGI) for pilot studies, investigated major geohazards such as flood, inundation, landslide, land subsidence

- Geohazard maps related to landslides and debris flow produced, with recommendations on mitigation. Various studies carried out in affected areas including on socio-economic impacts.

- Inundation and flood maps developed for downstream areas of Cua Dat hydropower plant and Hanoi city.

- Land subsidence and inundation maps developed for study areas, with recommendations on subsidence control and flood mitigation measures.

- The four scientific studies carried out by NGI staff allowed learning about new methods and technology. Also, Vietnamese participants were exposed to the use of NGI’s Q-System for rock mass characterization.

- Dissemination of information (dissemination of data and results)

- Technical reports from the pilot project studies were prepared in collaboration with NGI and distributed to stakeholders, e.g. on Seismic Microzonation, Surface Wave Experiments, GPR Tomography and Subsidence Estimation.

- Some results from pilot project studies were presented at Hanoi Geoengineering International Symposium (total of eleven intermediate reports available in 2012).

- Knowledge from the Masters and PhD studies was shared with local stakeholders e.g. infrastructure development authorities who are designing and constructing hydroelectric developmental projects.

Phase II in the project is still ongoing so there is no final tally of accumulated results. The most recent report available covers the period from June 2013 to May 2014.  Despite earlier stated concerns with reporting, the 2014 Annual Report still focused on Activities during the reporting period with no reference to cumulative results or progress towards Outcomes or the Overall Goal. A sampling of key activities during this period, by component, is offered below:

1)	Capacity Building, Educational Training and Scientific Exchange

- NGI and UiO prepared training materials and lectures for various courses, e.g. on landslide risk management, stability of soil slopes and structural mitigation measures, highly mobile landslides: risk assessment and mitigation, methods for mapping landslide hazards, flood risk analysis, flood zoning, flood forecasting systems, flood frequency analysis, early warning of landslides, geological hazards, and mitigation measures for landslides.

- Training courses in Hanoi were provided by experts from NGI and UiO: 12 lectures relating to landslides and floods (84 participants from different institutions) plus site training along highways in Hoa Binh province (35 participants)

- Training courses in Norway - Six VNU staff went to NGI and UiO to learn about human and financial management, project management, centres of excellence, laboratories, and an education programme on Geo-environment. Four staff went for one month joining lectures for the Masters programme on Environment Geology and Geohazards at UiO, collecting teaching materials from relevant courses and performing advanced testing on soil samples from West Hanoi city.

- In total, 8 experts were trained, 50 young staff were trained through “on-the-job training” or “learning-by-doing” in Vietnam, while 6 masters and 2 PhD were supported by the programme.

2)	Pilot Studies

- Song Tranh 2 hydropower plant - Field investigations were carried out at the Song Tranh 2 Dam by experts and young researchers to investigate geological conditions, geotechnical conditions, damages of houses triggered by earthquakes and vulnerability (psychology and properties).  This was described in the 2014 Annual Report as “the most multi-and interdisciplinary survey on impact of earthquake and flooding and resilience of community ….. conducted”.

- Son La hydropower plant and adjacent areas (including the national highways No. 6) -  Experts and students from VNU, NGI, UiO, and HUMG surveyed and collected information about the plant, assessing geological, geo-engineering conditions in the vicinity, geo-engineering characteristics along national highways, and loss due to landslides along the road. The results showed the vulnerability of humans and vehicles to landslides under different scenarios. This pilot and the Song Tranh pilot trained a total of 21 experts.

- Landslides in Xin Man district - An investigation by experts from NGI and VNU led to the installation of a rain gauge station (from Norway) to monitor rainfall so as to predict rainfall induced landslides. The data is recorded regularly and messages are forwarded to relevant people if rainfall exceeds threshold values.

3)	Dissemination

- 8 local workshops/seminars were organized in Ha Giang and Quang Nam provinces, as well as 2 national workshops with more than 200 participants coming from ten Vietnamese institutions.

- One paper was published in an in international journal and 8 national papers published articles in 2013.

- One guide book was drafted on early recognition and response to landslides and debris flows.

- In sum, dissemination activities engaged approximately 300 people from 11 relevant institutions.

In terms of overall effectiveness, the 2011 Phase I End Review indicated that while the project “suffered from initial delays” training activities weren’t negatively affected and performance exceeded quantitative targets. However, the authors of the report suggested that “the depth of gained knowledge from attended training is relatively modest”, mainly due to the short duration of the sessions organized. They further opined: “It is debatable if the term “training” may not give a wrong impression. Exposure to and orientation on new subjects may be more realistic terms, as the subject matter is in general complex, and deep understanding may elude the novice.”

With respect to the pilot projects, the project plan called for three study locations in Phase I but more than ten studies were undertaken in the first phase. And the project engaged 15 institutions in Vietnam compared to the 8 committed to in their plan.

The 2011 End Review also noted that it was difficult to discern “measurable impacts”, especially from   short term training, and partly due to the fact that expected outcome level results, and their connection to outputs achieved, were not clear. Nevertheless, the End Review team noted evidence of impact in one area - land subsidence in the greater Hanoi area.  In this case, VNU and NGI, through the pilot, relied on methods which were new to Vietnam to detect natural cavities in the sub‐surface and establish a link to land subsidence problems which had led to movement of buildings and cracks in their structures. The results were shared with local authorities as well as community members leading to the improvement of foundations in new construction.

## Sustainability

The capacity of participating faculty/students has been enhanced through project investments. The new knowledge and skills relating to geo-disasters attained through the project are likely to be sustained and to be of benefit to VNU, and other institutions, as long as staff/faculty remain. Some students who benefited from training or research opportunities will obviously graduate and move on but some of those will be positioned to contribute onward with other institutions. Yet others, of course, may take advantage of higher level study opportunities. However, as far as the evaluation team could tell, neither VNU nor the project team has tracking systems to determine when new knowledge or skills are used, and how; and which beneficiaries stay with their institution or move on. Either way though, there are reasonable prospects that benefits will be sustained at the individual level, especially given the increasing opportunities in Vietnam for gaining employment related to disaster management.

Concerns were raised though during the review process regarding sustainability of benefits at the institutional level.  VNU, for example, did not appear to have any kind of an exit strategy from the project or a sustainability strategy outlining how benefits would be sustained for them as an institution beyond the term of the project.  As noted above, the Phase II plan does call for the establishment of a Centre of Excellence, and an MoU has been signed between VNU and UiO in support of this. Beyond that, however, it’s not 100% clear in any of the documents seen what specifically its mandate would be, how it would be established and managed and ultimately how it would be sustained as an ongoing entity.

The review team was also concerned about sustainability of benefits at the community level. The project has supported useful and relevant work in various communities, e.g. establishment of early warning systems. In the sites visited, the initiatives seemed to have the support of the People’s Committees.  However, it wasn’t apparent that all of those committees or communities had the capacity to further enhance or even sustain local capacity for risk mitigation or management. Representatives of one community for example, were asked about capacity for data analysis, especially post-project. The response of a key respondent was “we will look to the Norwegians for support”. This suggests that the project may need to factor in more clearly in its implementation plans the means by which skills will be transferred to community level partners in order to sustain the benefits associated with the assistance provided.

# Conclusions and Lessons Learned

Overall Success and Capacity Benefits

As suggested in the preceding sections, the  project has generally been seen by project stakeholders as a ‘success’ , despite specific concerns, and project investments have clearly yielded a number of capacity benefits, including improvements in the capacity of individuals involved from participating institutions, such as VNU, through training, pilot studies, and exchanges with Norway. Respondents also highlighted improvements in research skills, use of technology (e.g. remote sensing and advanced field testing equipment e.g. GPR), improved mapping skills, among other improvements. Some participants were able to use research data collected through the project for theses or for lectures. VNU beneficiaries noted that for some of them it was the first time they were involved in “real research” which offered them a variety of benefits, e.g. learning about new methodologies, being exposed to field realities vs “just reading articles” (as before) or learning about technical issues from Norwegian partners. After Phase I, greater opportunities emerged for graduates, e.g. MAs going on to PhD programs, or undergraduates going out into the work force with new skills. However, when asked about ‘capacity benefits’ arising from the project, respondents tended to focus, as the comments above suggest, on research or training opportunities  for individuals vs institutional benefits. And changes in institutional capacity were not, as previously noted, routinely measured, so it is hard to be definitive about institutional benefits other than what has been written in progress reports which mainly describe activities undertaken rather than institutional results being pursued or realized.

However, in a session with HUMG stakeholders, they did indicate that before engaging in project activities they assessed potential institutional benefits to be realized, e.g. through training.  Specifically for HUMG, the initiatives supported needed to have: 1) a scientific result, 2) a training result, and 3) a publication arising.  HUMG’s Department of Geology also has its own short and long term objectives as a department, e.g. by 2020 they will need ‘x’ number of staff with at least an MA. According to interviewees, they linked those needs to contracts with VNU suggesting at least some level of institutional consideration in their engagement in capacity development activities.

At VNU, they have laid some foundations through the project for longer-term institutional change. This has been done, for example, through: 1) development of Masters and PhD courses of international standard on Environmental Geology and Geohazards which has the potential to create a new generation of qualified academics for VNU and other universities and technical colleges in Vietnam, and; 2) the beginnings of the establishment of a regional Centre of Excellence for Geohazards. The latter is expected to strengthen academic cooperation among relevant institutions in Vietnam, within the region and potentially with Norway, although, as noted, strategies for developing and sustaining the Centre are not clear.

Communities engaged through the project included ones that have been affected by, or are at risk of being affected by landslides, earthquakes, subsidence etc.. The consequences of such disasters can and have been felt in various areas from loss of life to diminished livelihoods, weakened or destroyed infrastructure and psychological impacts.  Communes involved in the project have established ‘Disaster Risk Management Committees’ but need more investment in skills and strengthening of systems to deal with geo-disasters, e.g. identifying risks more effectively. One community visited, which had been devastated earlier by flash floods had an early warning system installed with project support which monitored rainfall levels. VNU gets real time data and shares it with the commune if the system shows that it is at or over the risk threshold. However, VNU has not yet trained commune or community officials to deal with interpretation of data for the time beyond the end of the project when VNU will no longer be able to directly support the community.  Some sensors had also been stolen which further brought into question the sustainability of benefits without project support. Based on the few sites visited by team members on this review, it appeared that more could be done to enhance capacity at the community level to not only manage early warning systems but also to enhance capacities to prevent disasters, to mitigate risks and to respond to disasters when they do arise. However, this would require different types of inputs/ resources than were provided in the two phases of this project.

CD Approaches

Interviewees were asked as part of this review what were the ‘best approaches’ to capacity development or what approaches they would encourage if they had the opportunity to ‘re-do’ the project.  Respondents suggested, among other things: more support for young scientists to conduct research, write publishable articles, or to attend international conferences to link them with other scientists; more “real life exposure” to risk scenarios (“doing is better than training”) which would not only expose them to new realities but open up opportunities for them to better influence policies, and more study in the region, e.g. Thailand vs Norway, as a cheaper option with adequate quality, although collaboration with partners such as NGI was also seen as an important option to retain, e.g. for scholars honing specialized professional skills.

These comments suggest several things: 1) that the ‘best’ approach really depends on the need being addressed, e.g. longer-term study or exposure in Norway can be highly valuable for already skilled individuals seeking to enhance their level of expertise or familiarity with new methods only available overseas; 2) for many Vietnamese, ‘learning by doing’ in their own country can be hugely important as it provides opportunities to get real, ‘practical’ experience to help address basic needs (academic, or otherwise). What the responses also suggest though is that priorities are often identified by stakeholders at the level of individual needs.  Linked to that is the apparent lack of: 1) systematic processes to identify institutional capacity needs, and; 2) clear processes to identify the approach(es) (e.g. short/long-term training, study tour etc.) best suited to address the need identified.

Ownership and the Donor’s Role

Among the reasons for the ‘successes’ realized to date in the project are the fact that it has been responsive to national and institutional priorities regarding geo-disasters and climate change. The idea for the project, as indicated earlier, originated with VNU and had the support of the central government, the People’s Committees engaged through the initiative as well as community stakeholders. This is consistent with Norway’s ethos, and that of other donors, as reflected in the Paris Declaration on Aid Effectiveness, and its successors (Paris Declaration: “Developing countries set their own strategies for poverty reduction, improve their institutions and tackle corruption”).

Ownership though has many facets. In this case, the project idea originated, as indicated, with VNU which advanced the concept with the Norwegian Embassy in Hanoi. Embassy staff, as well as Norad colleagues, reviewed the proposal and offered comments.  Norad was expected to offer technical inputs and address any potential ‘developmental’ concerns. According to written exchanges between the Norwegian embassy and Norad staff in Oslo who reviewed the proposal, various concerns were raised by Norad staff.  As indicated earlier in this paper, they referred to, among other things, the proposal’s “weak design”, the “technical (engineering) approach to geo-disaster mitigation management”, the absence of a solid description of Vietnam’s current capacity to cope with and manage disaster situations and consequently how the project could most effectively address any shortcomings, as well as the uncertainty re VNU’s own capacity to carry out such a project.  The embassy described Norad’s recommendations as “well-founded and valid”, accepted some of the Norad suggestions, but indicated that others would not have to be addressed or included in the revised proposal, e.g. “socio and socio-economic aspects of disaster mitigation”.

The points above are highlighted for several reasons:  1) what they imply about the role of Norad in development programming (including capacity issues) in countries such as Vietnam, and; 2) what they suggest about actual ‘ownership’ in the context of Norwegian funded programming in Vietnam. On the first issue, members of the review team were told that in years past Norad had more influence in Norwegian embassies overseas and accordingly on development programming. Now, it appears that Norad offers inputs through long distance advice from staff based in Oslo. Most of this input is ‘technical’ in nature, e.g. education, health, climate change, seemingly with less attention to cross-cutting issues such as capacity development. The result, it would seem, is that programming decisions are made based substantially on Norwegian foreign policy priorities, with less attention to issues such as capacity development, and with embassies now less involved in substantive programmatic issues, including planning and implementation of projects - essentially keeping more of a ‘hands-off’ approach.

On the second issue, the experience reviewed for this paper also raises questions about the nature of ‘ownership’. In this case, VNU, a credible Vietnamese institution, submitted a proposal which made a reasonable request for technical support to enhance the skills and knowledge of its academics and students and to better place it to support communities at risk. The proposal was, as noted, eventually endorsed but as far as the review team could determine, the project proceeded absent any significant assessment of relevant capacity issues.  For the review team, this highlighted a potential risk arising from what may be described as a relatively ‘hands off’ approach, that is acceptance of proposals from local partners that may lack rigour or may not be backed by adequate analysis or evidence. However, that needn’t necessarily be the case as such proposals can, of course, provide a basis for critical, constructive dialogue that can ultimately enhance not only the quality of the intervention, but local ownership as well.  A further question which follows though is whether Norway actually has the capacity to ensure such ‘standards’ are met, i.e. does it have the systems, procedures or even human resources in embassies, or elsewhere, that have the time to raise such questions with partners when proposals are submitted.  Or is it seen as adequate to engage with partners and address such issues through current arrangements for pre-project assessments, regular (annual) meetings, mid-term reviews, and/or informal exchanges.

Institutional Collaboration

Another issue worthy of reflection in this case is Norway’s approach to institutional collaboration which has been the key mechanism for capacity development in this project.  As noted earlier in this paper, the Norwegian partners engaged through the project were well regarded and their contributions to VNU and other Vietnamese partners have been highly valued.  But was this the most effective mechanism for capacity development?  The simple answer is that we don’t know, in part because there is no basis for comparison against other Norwegian approaches in this ‘sector’ in Vietnam.  But certain questions do arise that merit consideration moving ahead, e.g.: Is there a risk that this approach risks being supply-led, or insufficiently informed by Vietnamese realities; does it lead to analysing and addressing ‘developmental’ problems through ‘technical’ lenses?; does it lead to acceptance of foreign TA as a (unquestioned) ‘free good’?; does it risk undermining local (or regional) capacity, especially if some incentives favour continued engagement of Norwegian partners (especially in roles that could potentially be taken on by local or regional actors)?; does it go against principles of untied aid? And is it the most effective (and cost-effective) option to address the issues at hand? Or is it simply what Norway wants, i.e. enhanced collaboration between Norwegian and Vietnamese institutions. If the latter, maybe it is a matter of expressing that more clearly and ensuring shared understanding of that priority. Finally on the question of roles, it is interesting to note that some of the partners involved in the institutional collaborations have essentially taken on Norad´s historical role between the embassy and local partners, leaving them with the technical/programmatic responsibility, without being bound by any specific guidelines on issues such as capacity development.

Many of the potential shortcomings of institutional collaboration noted immediately above have been overcome in this project through the development of strong personal and professional relationships. The ‘critique’ offered above also doesn’t highlight some of the more positive dimensions of institutional collaborations such as those that exist in this project. These include the value added to institutions such as VNU to be linked to international institutions operating at a very high professional level in areas of high priority. Benefits arising include not just the training, the exposure, the technology transfers and specific collaborative initiatives (as important as they are), but the ongoing association with internationally recognized institutions and the potential for VNU, and other Vietnamese partners, to rely on those relationships to link themselves into wider networks of academics, researchers and practitioners.

Implementation Strategies

The broader issue that the points raised above leads to is the absence in this project of clear strategies on how to enhance and make better use of capacity, at multiple levels, in pursuit of the development objective articulated for the project. One manifestation of this is what could be described as a ‘research-implementation gap’ in the project. The experience with the Cua Dat hydro power plant serves as an example as PECC1 researched the construction problem with the dam and carried out a simulation of what would happen if the dam broke. What the experience highlighted though was the gap between research/awareness raising and implementation of ‘appropriate’ responses which may be obstructed for political or bureaucratic reasons.

Arguably, if the Development Objective for Phase II (‘Reduced risks at pilot programme study sites thanks to increased geohazard awareness and preparation’) had been used as the starting point for this particular initiative, different strategies may have been deployed with community engagement as a starting point and broader, multi-faceted approaches beyond the research and subsequent awareness raising.

In conclusion, the project experience has reflected the fact that while geo-disasters and climate change are substantive ‘political’ priorities in Vietnam, CD is not a priority in the same way. In this case, this led to a focus on a clear substantive priority – geo-disasters and climate change (the ‘what’) with relatively limited regard to capacity development (the ‘how’).  Interventions supported focused primarily on needs articulated by the implementing partner (mainly research and training) but seemingly not informed by broader contextual or capacity analyses, or even assessments of internal factors that could potentially affect implementation or sustainability. Furthermore, not much regard was given to different possible modalities for capacity development with ‘training’ being the usual default.  In the process, the project did enhance the capacity of individuals, and to a certain extent participating institutions in research, outreach and awareness raising, which did lead to discussion of relevant issues in local communities and national fora. And while only so much can be covered by a ‘project’, one wonders if more could have been achieved, particularly at the level of institutional and community benefits if project stakeholders had taken a more strategic approach to addressing relevant capacity issues before and during implementation.

# Annexes

## References

- Desk appraisal of  Project proposal: Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, NORAD, April 4, 2008

- NORAD comments on VNU Revised Project Proposal, April 28, 2008

- Appropriation Document (SRV-2806, Geo-Disasters in Vietnam), Royal Norwegian Embassy, Hanoi , 2008

- Agreed Project Summary,  Description of the Project (SRV-07/056 – Capacity Building for Mitigation and Adaptation of Geo- Disasters Related to Environment and Energy Development in Vietnam)

- Annual Report of the Programme, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, VNU-NGI, Hanoi, May 2009

- Annual Report of the Programme, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, VNU-NGI, Hanoi, June 2010

- Annual Report of the Programme, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, VNU-NGI, Hanoi, May 2011

- Annual Report of the Programme,Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, VNU-NGI, Hanoi, May 2012

- End Review of Program, Ueli Meier & Hoang Hong Hanh, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, SRV-07/056, Final Report, Oslo and Hanoi, 24 June 2011

- Final Report of Phase I, Programme SRV 07/056, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, VNU-NGI, March 2012

- Programme Proposal for Phase II Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, VNU, April 2012

- Annual Report of the Programme – Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, Phase II, VNU-NGI, May 2013

- Annual Report of the Programme – Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, Phase II, VNU-NGI, Hanoi, May 2014.

## Scorecard

| # Scoring against Questions established for the evaluation |  |  | Geo-disaster Project |  |
| --- | --- | --- | --- | --- |
|  |  |  | Score 1-4 where 1 is negligible or very low and 4 is high. If the question not applicable to project score n.a. | Score 1-4 for how important to success in achieving outcomes was presence or absence of factor (4 = essential; 1 = little or no significance) |
| Overarching Question | Detailed question | Scoring |  |  |
| 1) CD intervention Addresses a stated national priority in the recipient country (priority sector and/or the needs of a priority population) | Does the CD intervention address a genuine national priority? | Clearly stated and justified national priority scores 4. Is clearly not a priority scores 1 | 4 | 4 |
|  | Is this a politically Urgent priority | Scores 4 high-up the political agenda e.g. because of public pressure or fear of not dealing with it leading to political problem | 4 | 4 |
|  | Does the intervention address the needs of a particular priority population - How/why is this population a priority | Scores 4 if targeted towards a particular group with clear priority, e.g. the poor. Scores 1 if untargeted | 4 | 4 |
| 2) CD intervention Addresses a clearly identified capacity constraint that the country did not have the capacity to address itself and does not duplicate support being provided elsewhere | Capacity constraint identified and specified at national policy level - clearly a felt-need at national level | Scores 4 if a clear statement in a major national policy document. Scores 1 if only mentioned in catch all phrases | 4 | 4 |
|  | Sub-question on felt-need: Where did the original identification of the CD constraint come from? Was it first identified by national government, the institution itself or an external player? | Scores 4 if a clear statement in a major national government policy document. Scores 1 if only mentioned in catch all phrases or clearly donor inspired | 4 | 4 |
|  | Capacity constraint real and well specified but was not a felt need of the institution | Scores 4 if both the institution and the national government identified the constraint and considered it important. Scores 1 if was externally identified and then sold nationally | 4 | 4 |
|  | What are the largest capacity constraints in the sector Support does not duplicate work of others | Scores 4 if corresponds to the most important constraints with no duplication, scores 1 if constraint was not key and/or duplication of work of others | This question not scored but informs answers on other points of the priority of the constraints addressed |  |
| 3) CD intervention Addresses a priority for Norway | Addresses a priority for Norway | Scores 4 if a clear statement in a Norway policy document at time of project. Scores 1 if only mentioned in catch all phrases | 4 | 4 |
| 4) Competencies of donor and external implementing/TA partner (if any) | Was the subject matter area of the intervention one where the where the donor has strong competencies? | Scores 4 if high competency, 1 if no particular experience of area and no strong back-up from Norad or experienced partners | 4 | 4 |
|  | Does the donor know the country and institutional context well? | Scores 4 if knows well, 1 if little or no experience and knowledge | 4 | 4 |
|  | Does the donor know the target institution(s) well? | Scores 4 if knows well, 1 if little or no experience and knowledge | 3 | 4 |
|  | Does the external implementing partner know the target institution well | Scores 4 if knows well, 1 if little or no experience and knowledge | 4 | 4 |
| 5) Was the intervention designed with1 | Full involvement of national government | Scores 4 if high involvement. 1 if little or no involvement | 3 | 3 |
|  | Full involvement of target institutions | Scores 4 if high involvement. 1 if little or no involvement | 4 | 4 |
|  | Other local stakeholders | Scores 4 if there was wide consultation with non-core stakeholders and 1 if consultation was limited to the government and the institution. | 2 | 3 |
| 6) Was there a comprehensive capacity needs assessment for a) the sector/area of work and b) the institution. | Was there an initial comprehensive capacity needs assessment | Scores 4 if there was a comprehensive assessment. 1 if there was no assessment at all | 2 | 3 |
|  | Did later phases factor in capacity needs assessment /take information. from earlier phases | Scores 4 if information was recorded and good account taken of that information | 2 | 3 |
|  | Was the assessment appropriate to the scale and nature of the intervention | Scores 4 if the resources committed to CD needs assessment were appropriate to the scale and complexity of the intervention. n.a. if there was no assessment | 2 | 3 |
|  | Were the findings of the assessment applied in the intervention | Scores 4 if there was good account taken of needs assessment data. n.a. if there was no assessment | 2 | 3 |
|  | Were national stakeholders appropriately involved in the capacity needs assessment | Scores 4 if there was appropriate involvement of all relevant stakeholders. Scores 1 if there was no involvement or no needs assessment | 2 | 3 |
| 7) Important context-specific factors for the CD intervention to contribute to its objectives identified and taken account of in design and implementation working with them rather than changing them if this is not the direct purpose of the CD or changing them if they are a direct impediment to CD achieving goals (e.g. trainees cannot do anything with their training) | National culture (e.g. hierarchical, male dominated, importance of tribal or party allegiances - much communication outside formal channels, importance or lack of importance of law and of formalised policies; Institutions have or do not have a lot of freedom) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis | 2 | 4 |
|  | Institutional culture (e.g. hierarchical/ command, consultative, consensus, units compartmentalised, networked, informal networks more important than structural relationships, bureaucratic (form filling), rule based) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis | 2 | 3 |
|  | HR systems and possibilities for advancement and reward | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis | 1 | 2 |
|  | Financial systems and budget allocation (e.g. budget not performance related, budget does not mean funds available, authority for expenditure) | Scores 4 if comprehensive context analysis and taken into account in design and implementation. Scores 1 if no analysis or no account taken of analysis | 1 | 2 |
|  | Were the specific incentives and disincentives to achieving the planned CD identified? What was actually done to build on them in the case of incentives or offset them in the case of disincentives? | Scores 4 if identified and taken fully into account in design and implementation. Scores 1 if no analysis or no account taken of analysis | 1 | 2 |
| 8) Was the full complexity for the CD in achieving outcomes recognised and addressed in design and implementation |  | Scores 4 if elements of complexity identified, mapped and taken fully into account in design and implementation. Scores 3 if implicitly recognised and addressed. Scores 1 if no analysis or no account taken of analysis | 2 | 3 |
| 9) Theory of Change (ToC) | Was there an explicit or implicit Theory of Change - How adequate was it | Scores 4 if the ToC was explicit and adequate, 3 if it was implicit and adequate. 1 if no ToC and implicit ToC weak | 1 | 1 |
|  | Quality of the ToC: -Realistic, making realistic assumptions (assessments of pre-conditions) along the lines of contribution including those related to the overall and the institutional context) -Unpacks link between institutional capacity and performance and performance and development effectiveness - Identifies milestones and key assumptions to be monitored | Scores 4 if satisfies all criteria, 1 if ToC did not exist implicitly and did not satisfy conditions | 1 | 1 |
| 10) The design and implementation strategies were informed by clear rationales to address the priority capacity issues identified |  | Scores 4 if a clear identification of issues and how to be addressed. Scores 1 if little evidence that there was any consciousness of issues | 1 | 3 |
| 11) Consideration of alternative potential CD approaches/modalities. responsive to recipients’ needs and informed by a clear understanding of the implementation context | Alternative modalities: Choice of modality, e.g. training, technical advice, exposure through work experience visits, etc. to alternatives, system design and transfer, conditional financial support - a complementary mix. What was the evidence that alternative modalities were examined and choices made | Scores 4 if alternative modalities for overcoming the constraint were evidently examined and acted on. Scores 1 if there was little consideration of modalities and modality not appropriate | 2 | 2 |
|  | Sub-question - cost implications were considered in modality choice | Scores 4 if costs were clearly considered and a factor in the choices made. Scores 1 if they were not considered and the modality was not cost -efficient | 1 | 2 |
| 12) The choice of partners were responsive to recipients’ needs and informed by a clear understanding of the implementation context | Alternative implementation partners with relevant experience. If the implementation partner was a twinning partner was there examination of consultant firms, TCDC or a national institution. | Scores 4 if there was evident consideration of the pros and cons of different partners and good choices. Scores 1 if a partner was chosen without any evidence of consideration and it was a poor partner | 3 | 3 |
|  | Technical twinning (not implementation) was there a net contribution of twinning over other modalities such as consultant firms, TCDC or a national institution. | Scores 4 if there was evident consideration of the pros and cons of different technical twinning partners and good choices. Scores 1 if a partner was chosen without any evidence of consideration and it was a poor partner | 3 | 3 |
| 13) Choice of time frame and sequencing: a concentrated support to change or a longer term and more evolutionary approach. What was the evidence that alternative modalities were examined and considered choices made |  | Scores 4 if there was evident consideration of the pros and cons and choice well based. Scores 1 if a choice made without any evidence of consideration and it was a poor choice | 2 | 3 |
| 14) The design drew on experience elsewhere | Identification of specific relevant experiences/evidence that informed the design | Scores 4 if there was evident consideration of experience elsewhere and it was acted on. Scores 1 if there was no account of evidence from elsewhere and this led to major deficiencies | 3 | 3 |
| 15) Implementation strategy drew on experience elsewhere | Choice of consultants with relevant experience | Scores 4 if the expertise brought in had relevant experience. Scores 1 if clearly did not have relevant experience | 2 | 2 |
| 16) Key factors for financial accountability were: a) identified and considered in the design and b) addressed in the implementation, while maintaining focus and not becoming excessive? | Were well identified in the design | Scores 4 if well identified in design. Scores 1 if little or no specification | 2 | 3 |
|  | As implemented were suitable to government accountability mechanisms | Scores 4 if as implemented well suited to government systems. Scores 1 if unrelated to government systems | 3 | 3 |
|  | Met Norway's requirements | Scores 4 if as implemented fully met Norway's requirements. Scores 1 if completely failed to meet requirements | 3 | 3 |
|  | Covered all essential aspects | Scores 4 if provided good accountability on use of money by purpose as well as category of expenditure and against budget. Scores 1 if failed to provide coverage of key aspects | 3 | 3 |
| 19) M&E framework appropriate and applied | Was there an M&E framework well designed/appropriate - Not excessively heavy well linked to milestones on immediate outcomes not just delivery of outputs such as persons trained. | Scores 4 if well designed M&E framework in place. Scores 4 if in place, appropriate and applied. Scores 1 if non existent | 2 | 2 |
|  | Were the findings of M&E applied, to make management decisions and adjustments in budgets, activities and timeframes by Norway? | Scores 4 if well considered and applied. Scores 1 if little M&E and/or not applied | 2 | 2 |
|  | Were the findings of M&E applied for accountability of implementers | Scores 4 if performance on M&E reported results was used vigorously e.g. withholding payment. Scores 1 if little or no direct use | 4 | 4 |
|  | Were the findings of M&E applied, to make management decisions and adjustments in budgets, activities and timeframes by the implementers? | Scores 4 if well considered and applied. Scores 1 if little M&E and/or not applied | 2 | 2 |
|  | Were the findings of M&E applied for wider learning | Scores 4 if evidently disseminated and used. Scores 2 if nothing disseminated for wider learning from M&E. Scores 1 if other information disseminated ignoring M&E findings | 2 | 3 |
| 20) Adaptive management: Were there any significant changes in the intervention during implementation based on evidence, especially to better achieve outcomes or make outcomes more relevant? |  | Scores 4 if major changes made on the basis of evidence or no evidence there was need for changes that were not made. Scores 2 if no changes on the basis of evidence. Scores 1 if evidence ignored | 3 | 3 |
| 21) Buy-in to the objectives and modalities of the intervention Target institutions and local stakeholders sense of ownership of the intervention | Was the intervention implemented with the national authorities in the driving seat? | Scores 4 if all major decisions taken by national authorities. Scores 1 if national authorities had little or no voice in the CD | 3 | 3 |
|  | Buy-in to the objectives and modalities of the intervention - Political level. Does the national government feel it owns the intervention? | Scores 4 for very evident support in decisions, actions and time given not just words. 1 if no evidence of support 2 if support but do not understand or fully agree on what is to be achieved | 2 | 3 |
|  | Buy-in to the objectives and modalities of the intervention - Institutional leadership level | Scores 4 if very enthusiastic and committed, clearly understanding what is to be achieved. 1 if cynical and uncommitted | 4 | 4 |
|  | Buy-in to the objectives and modalities of the intervention -Direct Counterparts | Scores 4 if very enthusiastic and committed, clearly understanding what is to be achieved. 1 if cynical and uncommitted | 4 | 4 |
|  | Do the direct beneficiaries feel they own the intervention (for these projects direct beneficiaries are the trainees) | Scores 4 clear commitment to the intervention and its follow-through by all and they think of it as their project. Scores 1 if regarded as something entirely external even if useful in some respects | 3 | 3 |
| 22) Internal and external champions for the CD identified and real | External senior national bureaucratic and political | Scores 4 if they are able to influence strongly at the right level and clearly committed. 1 if do not exist in any real way | 3 | 2 |
|  | Internal senior management | Scores 4 if clearly identifiable who in senior management taking a real lead and they are able to and do provide good leadership. 1 if do not exist in any real way | 4 | 4 |
| 23) Support and guidance for a) selection; b) design and c) implementation of CD interventions - (Embassy and other government staff) | Have staff received adequate support and guidance (comments, guidelines, training, contact point for advice) for CD as distinct from technical elements | Scores 4 if support levels high and accessible. Scores 1 if little or no support | 1 | 3 |
|  | Did the staff look for support on CD | Scores 4 if staff actively looked for support. Scores 1 if staff did not seek CD support | 1 | 3 |
|  | Did Norway have sufficiently flexible procedures to respond to adaptive project design and management needs of CD | Scores 4 if procedures flexible to respond to needs of CD with major change if needed. Scores 1 if no flexibility at all | 3 | 3 |
|  | Did Norway welcome or tend to respond negatively to suggestions for change during implementation | Scores 4 if fully open to suggestions. Scores 1 if a closed mind to changes | 3 | 3 |
| 24) National Government procedures and attitudes | Does the government have sufficiently flexible procedures to respond to adaptive management needs of CD. | Scores 4 if fully flexible and procedures and facilitates change. Scores 1 if will not accept change | 2 | 2 |
|  | Does the government welcome or tend to respond negatively to suggestions for change during implementation | Scores 4 if facilitates change in response to well justified requests. Scores 1 if will not accept change | 2 | 2 |
| 25) ) Support and guidance for a) selection; b) design and c) implementation of CD interventions - InternationalImplementing agencies | Have staff received adequate support and guidance (comments, guidelines, training, contact point for advice) for CD as distinct from technical elements | Scores 4 if support levels high and accessible. Scores 1 if little or no support | 1 | 3 |
|  | Did the staff look for support on CD | Scores 4 if staff actively looked for support. Scores 1 if staff did not seek CD support | 1 | 3 |
| 26) ) Support and guidance for a) selection; b) design and c) implementation of CD interventions - Norwegian Twinning partners | Have staff received adequate support and guidance (comments, guidelines, training, contact point for advice) for CD as distinct from technical elements | Scores 4 if support levels high and accessible. Scores 1 if little or no support | 1 | 3 |
|  | Did the staff look for support on CD | Scores 4 if staff actively looked for support. Scores 1 if staff did not seek CD support | 1 | 3 |

| Results and Their Sustainability |  | Score 1-4 where 1 is negligible or very low and 4 is high. If the question not applicable to project score n.a. |  |
| --- | --- | --- | --- |
| 29) Capacity of the target institution(s) | Evidence that the Capacity of the Partner Institution (s) has a) improved and b) improvement was in line with targets and c) commensurate with the resources deployed. d) Was the improvement sufficient to deliver on the intended or essentialprerequisite for enhanced delivery of results by the institution? | Scores 4 if satisfies criteria a, b, c, and d. 1 if satisfies none of the 4 criteria | 3 |
|  | Evidence that the assisted institution has achieved progress on its intended outcomes as a result of its improved capacity | Scores 4 Improvement was entirely due to capacity. Scores 2 if no improvement and Scores 1 if there was a deterioration | 3 |
|  | Evidence of the interventions contribution to the outcomes for capacity and delivery by the institution (both capacity and delivery could improve or deteriorate for reasons little linked to the intervention) | Scores 4 Improvement was entirely due to CD. Scores 2 if no contribution and Scores 1 if there was a deterioration due to e.g. resources being diverted by the CD away from delivery by the Institution | 3 |
| 30) Evidence of specific CD outcomes having continued or are likely to be continued | Extent to which internal conditions exist to support continuation of CD outcomes: e.g. -Stability of staffing (e.g. has the change relied on just a few individuals; and if they go, how will that affect sustainability of outcomes?) -Internal incentives/motivation to maintain and build on the change? | Scores 4 if there are no significant internal barriers to continuation of outcomes and a clear internal commitment. Scores 1 if there is little interest in continuation | 3 |
|  | Extent to which national external conditions exist for the outcomes to continue, e.g.: - Budget allocation (have costs of the institution gone up and can this be sustained)? - Continuation of a positive external environment, e.g. supportive policies and ongoing support from key stakeholders? | Scores 4 if there will very evidently be budget and necessary changes by government, etc. etc. If this unlikely or there are clearly other priorities, scores 1 | 3 |
|  | For twinning: evidence that the twinning relationship will continue beyond the end of donor funding | If no twinning N.A. If both the twinning institution and the national institution very clearly committed to working together in the absence of supplementary financing scores 4. Scores 3 if committed and some medium-term finance has been located. Scores 1 if no connection likely (e.g. if TA all consultants and no real interchange with twinning partner) | 1 |
| 31) Unintended effects of the CD) positive and negative | Positive effects, if any, can include such things as wider pool of policy trained people for civil service | Scores 4 if very extensive and 1 if none | 1 |
|  | Negative effects, if any, (can include such factors as diverting resources from areas of greater priority - making systems more elaborate without being more effective or being parallel systems) | Scores 4 if none and 1 if very extensive | 4 |

Appropriation Document (SRV-2806, Geo-Disasters in Vietnam), Royal Norwegian Embassy, Hanoi, 2008, p.2.

The desk appraisal of the initial project proposal by Norad referred to short-comings in the coordination and cooperation among on-going programs and activities on geo-disaster mitigation while cautioning that how the proposed project would relate to them and add value was not well defined.

Ministry of Foreign Affairs, Press release 6 Oct. 2011 (http://www.regjeringen.no/en/dep/ud/selected- topics/development_cooperation.html).

Norwegian policy on the prevention of humanitarian crises, MFA Report 9 (2007- 2008) to the Storting.

UiO’s Faculty of Geology, became involved in the project in Phase II through a dialogue with Vietnamese partners on the idea of developing a Centre of Excellence (COE) for Geohazard Mitigation. They also provided lectures in Hanoi and Oslo on the impact of climate change. In Phase I, the Norwegian Water Resources and Energy Directorate (NVE) did some initial capacity building on climate change, participated in flood‐related field investigations, and trained Vietnamese students on hydrological simulation, flood mapping and early warning.

End Review of Program, Ueli Meier & Hoang Hong Hanh, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, SRV-07/056, Final Report, Oslo and Hanoi, 24 June 2011, p.9.

Ibid, p.18

Ibid, p.19

Norwegian Water Resources and Energy Directorate - NVE was a primary partner in Phase I but was no longer involved in Phase II when UiO was engaged.

Annual Report of the Programme – Capacity Building and Technology Transfer for Mitigation of Geohazards in Vietnam in the Context of Climate Change, Phase II, VNU-NGI, Hanoi, May 2014, p. 10.

End Review of Program, Ueli Meier & Hoang Hong Hanh, Capacity Building for Mitigation and Adaptation of Geodisasters Related to Environment and Energy Development in Vietnam, SRV-07/056, Final Report, Oslo and Hanoi, 24 June 2011, p. 20.

Ibid, p. 20.

The review team was told that Norad no longer has the position of ‘Institutional Capacity Building Advisor’ which it had in headquarters up until several years ago. It was not clear to the team what the absence of that position has meant in terms of advisory support or guidance on capacity development in overseas projects.